## Slide 1
RTC+B Tack Force
Update
Matt Mereness
RTCBTF
November 1, 2023

## Slide 2: RTCBTF Update
TAC awareness of deadline for RTC-SOC NPRR1204 :
  Sequence of seven meetings Sept-Dec
  Sep 8- RTCBTF Initial review of RTC-SOC whitepaper
    ERCOT release of draft NPRR language estimated for Sep 22 (sent Sep 27)
    Comments to whitepaper and/or draft NPRR due Sep 27 (1 set of comments received Oct 2)
  Oct 5- RTCBTF review of feedback on whitepaper and/or NPRR language
    Effective discussion of SOC for RUC and SCED (no changes to DAM)
    Discussion revolved around gaining understanding and potential changes
    MP comments yielded at least one change in SCED design
    RTCBTF desire for more high-level descriptions or examples (ERCOT to consider)
  Oct 10 - Released NPRR1204 for RTC-SOC
  Oct 12- PRS initial review and seek urgency for RTC-SOC NPRR
  Nov 1- RTCBTF review to discuss/reconcile any issues
    2 sets of comments filed
  Nov 9- PRS approval
  Dec 4- TAC approval
  Dec 19- Board approval
Today’s RTCBTF meeting is dedicated to focus on NPRR1204 Comments received
Potentially add December 6th meeting after WMS to address any emerging items and/or set stage for 2024 review priorities.

## Slide 3: Appendix
- Scope of RTC+B Program
- Review of RTCBTF Charter
- Plans for Meetings and Review Cycles
- Types of Work and Scheduling

## Slide 4: Scope of RTC+B Program
Reminder the scope the Program is limited to:
  RTC (NPRR1007-1013)
  Single Model Batteries (NPRR1014)
  RTC State of Charge modeling in SCED and RUC (NPRR1204)
Current estimated cost and timeline is $50M with target delivery in 2026
  ERCOT also recognizes the potential challenges and constraints with other efforts, but is committed to continuing forward progress on the RTC+B program.

## Slide 5: Review of RTCBTF Charter Program
Who: Participation in RTCBTF shall consist of ERCOT stakeholders, PUCT Staff, the Independent Market Monitor (IMM), Office of Public Utility Counsel (OPUC), and ERCOT Staff.
What/Why: Established to coordinate and review the necessary ERCOT and Market Participant activities to mitigate risk and support the successful implementation of the RTC+B Program. This will include, but is not limited to:
  Coordinating timelines for interface requirements and testing,
  Providing the forum for any analysis or policy decisions (such as parameter values)
  Coordinating market readiness and cutover activities,
  Review of draft Nodal Protocol Revision Requests (NPRRs) necessary to successfully implement the program within the identified timeframes, and discussing other details as needed.
Where: Hybrid meeting (in-person and remote)
When: As needed, but primarily monthly, until RTC+B implemented and stabilized

## Slide 6: Plans for Meetings and Review Cycles
Objective is to present concepts or issues that need to be resolved for an effective implementation and drive towards consensus.
Lessons learned from RTCTF:
  Initial concept presented by ERCOT staff
  Comments and alternatives presented by MPs
  RTCTF consensus achieved or escalated to TAC for a vote to decide the matter.
Plan to continue to the “pens-down” scope approach
  RTC Key Principles were approved to lay foundation of NPRR1007-1013
    Consolidated Key Principles: https://www.ercot.com/files/docs/2020/04/01/RTC_Key_Principle_Quick_Reference.docx
    Library of Key Principles: https://www.ercot.com/mktrules/puctDirectives/rtCoOptimization
  Battery Key Topic Concepts approved to lay foundation of NPRR1014
    https://www.ercot.com/mktrules/keypriorities/bes
  RTC State-of-Charge accounting concept/NPRR to be developed without expanding timeline or costs RTC+B Program beyond current estimates (need December 2023 Board approval).

## Slide 7: Types of RTCBTF Work and Scheduling
Recognition of “unfinished” RTCTF issues:
Parameters for Ancillary Service proxy offers
ASDCs for use in Reliability Unit Commitment (RUC) studies
Any needed discussion on triggers for initiating off-cycle SCED executions
  Largely driven by ERCOT Operator desk procedures and discretion today
Consideration of NPRR for allowing real-time updates to offers in current Real-Time Market and future with RTC.
Framework for periodic analysis comparing RTC and the current ORDC design – KP 1.1(8)
Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3))
Additional review of transmission constraint max. shadow price values
Operation Procedures (e.g., removing SASM and HASL/LASL)
Business Practice Manuals (e.g., changes to COP and telemetry)
Mapping of bill determinants to extracts and reporting for developing shadow settlement
Changes to ICCP handbook, and documentation for non-ICCP market submissions
Market trials/training/annual seminar engagement
Any details MPs need for designing their control systems
Other issues identified:
Scaling Factor for RegU and RegD - should be dynamic or static?
Non-Spin awards for Combined Cycle unfired ducts - should use on-line or off-line offers
Energy Storage Resource dispatch in RUC – SOC consideration
Determine if for a combined cycle, the Steam Turbine without ducts fired is considered frequency responsive
Self-provision of Non-Spin for Non-Controllable Load Resources
DRRS awards in RT or only Self provision from DAM award
Inclusion of firm load shed in the pricing run
Various protocol references need to be updated
Re-visit the Overage Charge in case of No DAM run scenario. How to control that trades do not exceed the 60% rule for RRS and 50% rule for ECRS in the RTM clearing?
Now/2023 Problems
2024 Problems
2025 Problems