## Slide 1
Project Update
November 9, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  NPRR1026 Self-Limiting Facilities Go-Live Information
  Major Projects
  2023 Release Targets
  2024 Release Targets
  Additional Project Status Information
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1201 – Limitations on Resettlement Timeline and Default Uplift Exposure Adjustments
    NPRR1204 – Considerations of State of Charge with Real-Time Co-Optimization Implementation
    NPRR1209 – Board Priority – State Of Charge Ancillary Service Failed Quantity Allocations under NPRR1149
  Technology Working Group (TWG)
    Next meeting date is TBD
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 November Off-Cycle Release – 11/1/2023 Complete
  LPGRR070 – Discontinuation of Interval Data Recorder (IDR) Meter Weather Sensitivity Process
  NPRR1163 – Related to LPGRR070
  NPRR1136 – Updates to Language Regarding a QSE Moving A/S Responsibility Between Resources
  NPRR1175 – Revisions to Market Entry Financial Qualifications and Continued Participation Requirements
  NPRR1189 – Updates to Language to Clarify the Allowable Regulation A/S Trades
  OBDRR048 – Implementation of Operating Reserve Demand Curve (ORDC) Multi-Step Price Floor
2023 November Off-Cycle Release – 11/2/2023 In Stabilization
  EMS Upgrade
2023 November Off-Cycle Release – 11/17/2023 In Flight
  SCR824 – Increase File Size and Quantity Limits for RIOO Attachments
2023 November Off-Cycle Release – 11/19/2023 and 12/1/2023 In Flight
  NPRR1026(a) – BESTF-7 Self-Limiting Facilities [RIOO portion]
  NPRR1164 – Black Start and Isochronous Control Capable Identification
  PGRR081 – Related to NPRR1026, BESTF-7 Self-Limiting Facilities
  RRGRR033 – Related to NPRR1164, Black Start and Isochronous Control Capable Identification
2023 December Release – R6 – 12/5/2023-12/7/2023 In Flight
  SCR807 – Increase CRR Transaction Capability
  SCR816 – CRR Auction Bid Credit Enhancement
  SCR822 – Create Daily Energy Storage Integration Report and Dashboard
  NOGRR249(a) – Communication of System Operating Limit Exceedances [GridGeo portion]
2023 December Off-Cycle Release – 12/12/2023 In Flight
  NPRR1153 – ERCOT Fee Schedule Changes
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Self-Limiting Facilities (SLF) Background
The NPRR1026 project gated to Execution on 10/11/2023. ERCOT now estimates the following dates:
  “RIOO changes for SLF facilities are scheduled to become available on 11/19/2023”
  “SLF’s can be in operation on 3/1/2024” (assuming no schedule changes)
  “Reporting changes (effectively the go-live of NPRR1026) are planned to be live 3/28/2024” and should be able to provide a report for the month of March 2024
Assuming the above estimates hold ….. this means that a few days after the end March 2024 ----- we can run the report providing information for the month of March 2024. The report will show which SLFs (if any) have exceeded their SLF limits. Therefore, it may be acceptable to allow self-limiting facilities to go into operation on 3/1/2024 ----- since we should have the capability to evaluate March performance with the new monthly report starting 4/1/2024.

## Slide 5: Impact to “In-Flight” SLFs
Developers that have previously submitted “SLF” for a project prior to the RIOO SLF changes going live in December 2023 ------ will need to go back into RIOO and submit responses to the new SLF questions on the new SLF panels. Failure to going back into RIOO ---- post the RIOO SLF changes going live ------ will likely delay the Resource’s Commercial Operation Date (COD).
For new Resource projects that are entering RIOO data for the first time after the RIOO SLF changes have been implemented in December 2023 ----- they will fill out the new SLF section as they progress through the process.
When the RIOO changes for SLF facilities become available (estimated to be in early December 2023), ERCOT plans to send out a Market Notice reminding interconnections requests that previous identified the request as an SLF ----- need to be updated by the requestor in RIOO.
Note that at this time, no SLFs can be in operation prior to the first day of the month ---- that will be able to be reviewed and reported on by the new monthly report --- (currently expected to be in place for March, 2024).

## Slide 6: Major Projects

## Slide 7: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 NPRR1135 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR1154 LPGRR070 NPRR1163 NPRR1136 NPRR1175 NPRR1189 OBDRR048 EMS Upgrade SCR824 | SCR807 SCR816 SCR822 NOGRR249(a) NPRR1026(a) NPRR1164 NPRR1026(a) NPRR1164 PGRR081 RRGRR033 NPRR1153
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1020(a) – EPS Metering portion
NPRR1026(a) – SLF – RIOO portion
NPRR1096(b) – ECRS portion
NOGRR249(a) – GridGeo portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,995,1004,1006,1007,1019,1023,1030,1032,1034,1057, 1077,1105, 1111,1128,1131 SCRs: 799,805,810,818,819 PGRRs: 066,076,088,091,094,099,103 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
E
E
E
E
E
E
11/2
7/14
ü
ü
ü
10/1
ü
EMS Upgrade Freeze – July 2023 – Jan. 2024
11/1
6/28
ü
11/17
E
11/19 and 12/1
12/12

## Slide 8: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/25 | February 2/22 | March 3/28 | April 4/25 | May 5/30 | June 6/27
NPRR1040 NPRR1092(b) SCR822 Public API Enhancements | NPRR1132(a) RRGRR032 NOGRR249(b) NPRR1002 NPRR1153 PGRR103 RRGRR023 RRGRR032 RRGRR033 | NPRR1026(b) NPRR1040 NPRR1186 NPRR1026(b) |  | NPRR1149 NPRR1121 NPRR1090 NPRR962 NPRR1196 Forecast Presentation Platform | NPRR1002 RRGRR023
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1026(b) – SLF – Reporting portion
NPRR1092(b) – Limit RUC Opt-Out Provision
NPRR1132(a) – Operating Limits in Cold and Hot Conditions – RIOO portion
NOGRR249(b) – MIS posting
E
E
E
E
E
E
E
E
P
P
Q1 – RIOO
P
July 7/25 | August 8/22 | September 9/26 | October 10/24 | TX SET 5.0 11/10 | December 12/11-12/12
 | SCR813 |  |  | NPRR1095 SCR817 SCR823 RMGRR172 | 
R7
R8
R9
R10
R11
E
E
E
E
E
P
E
2/1
3/1

## Slide 9: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
RTC | NPRR1007-NPRR1014, Single Model, State of Charge | Planning | Project has restarted
SCR820 | Operator Real-Time Messaging During Emergency | Planning | Go-Live target is TBD
NPRR945 | Net Metering Requirements | Not Started | Start delayed due to an internal project dependency
NPRR1004 | Load Distribution Factor Process Update | Not Started | ERCOT is aware of interest in getting these implemented The DRRS IA is now complete and has been loaded in the ERCOT portfolio management system. We are now assessing these items for potential inclusion in 2024 project plans.
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing restart date options
NPRR1058 | Resource Offer Modernization | Not Started | Assessing start date options
NPRR1091 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | 
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Assessing start date options
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Assessing start date options
SCR805 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | Assessing start date options
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | Targeting Q1 2024 start
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Increasing granularity for SCED disclosure reporting
Red Text: New additions and updates

## Slide 10: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1201 | Limitations on Resettlement Timeline and Default Uplift Exposure Adjustments | 2024 | 4080 | $40k-$70k, 4-6 months Impacted System(s): CMM, S&B
NPRR1204 | Considerations of State of Charge with Real-Time Co-Optimization Implementation | 2023 | 235 | $750k-$1M Combine with RTC+B – funding is already included in the RTC+B budget REGULATORY Impacted System(s): MMS, EMS
NPRR1209 | Board Priority – State Of Charge Ancillary Service Failed Quantity Allocations under NPRR1149 | 2023 | 3780 | $100k-$150k, 6-9 months Merge with NPRR1149 – targeted for May 2024 go-live Impacted System(s): EMS, MMS
SCR825 | ERCOT Voice Communications Aggregation | TBD | TBD | More time needed to complete IA
Recommendations for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3820
Next available 2024 Rank in Business Strategy = 4080
Next available Rank in Regulatory = 380

## Slide 11: Technology Working Group (TWG)
Next TWG meeting date is TBD