## Sheet1
Market Coordination Meeting (MCT) and Texas SET Meeting Notes / Action Items
2023-10-19
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes September 20, 2023--MCT
| No changes were made to the notes. | The Vice Chair will have these posted to the August 16, 2023 and September 20, 2023 meeting page key documents.
Review Initial Draft -- Texas SET 5.0 Training Presentation
It was noted that the Texas SET V5.0 Orientation is scheduled for January 8, 2024
The group would like to have the Texas SET V5.0 training document as soon as possible. The cut over plan will be in a different document.
Other items
No "Other Items" were discussed.
Meeting NotesSeptember 20, 2023--TX SET
See MCT for August meeting notes No September meeting.
ERCOT Updates
Market Test Flight Some discussion was held related to LP&L and the February Market Flight Test. | ERCOT presented the update. It was agreed to bring the conversation regarding a blackout for LP&L in the February 2024 Market Test Flight at RMS.
TDSPs reviewing / updating Production Documents | ERCOT requested that the TDSPs review and update, if needed, their Testing to Production Checklist at the following link. https://www.ercot.com/services/rq/lse/trt/
MIS API | This is on target for the 11/6/2023 - 11/10/2023 testing. Those wanting to test need to request the testing digital certificate from ERCOT by 11/1/2023. The requests do not go through each company's USA.
Retail Mobile Generation Discussion
The Chair gave an update from the meeting held Tuesday October 10, 2023. A workshop will be held on 11/16/2023 for further discussion. | Centerpont Energy shared a document for Mobile Generation Deployed they shared at the Tuesday October 10th Mobile Generation meeting. --ERCOT speculated that we might be able to get the added REF~JH~M Meter Role code into the Texas SET V5.0 timeline. --It was agreed that the change would need a Change Control for the Implementation Guide and updates made to the Retail Market Guide (RMG) as opposed to having to create a System Change Request (SCR). --The group will check with ERCOT to see if a change to the Nodal Protocols Settlement section is needed. --Speculation was that the Public Utility Commission of Texas (PUCT) rule making would only cover the "what to do"; then the Market will address the how to make the change.
Other Items
Lubbock Update | The Chair conducted a discussion related to Lubbock and the Mass Customer List CSV file. The Chair and TXU will work together to make changes; then bring those back for discussion.
Next Meeting-- WebEx Only | 2023-11-15
Attendees F-T-F
Attendees Webex
Amy Sue Stirland LP&L | Kathryn Thurman ERCOT
Angela Ghormley Calpine | Kathy Scott Centerpoint Energy
Bill Snyder AEP | Kimberly Mack Centerpoint Energy
Carolyn Reed Centerpoint Energy | Kyle Patrick NRG
Chris Dominguez | Laura Gomez LP&L
Dailey Smith LP&L | Lauren Damen Reliangt
Darrell Miller ESG | Mark Pepdjonovic ESG
Dave Michelsen ERCOT | Monica Jones-Centerpoint Energy
Deb Belin Earth Etch | Paul Yockey ERCOT
Diana Rehfeldt TNMP | Sam Pak ONCOR
Eric Lotter - GridMonitor | Sarah Heselmeyer ERCOT
Frank Nunes vERTEXoNE | Sheri Wiegand Vistra
Gary Walcott TNMP | Steve Pliler Vistra
Jeff Chen Centerpoint Energy | Toni Bean Centerpoint Energy
Jesse Macias AEP | Viviana Valdez LP&L
Jordan Troublefield ERCOT