## Slide 1: Transition to Retail Competition
November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  | 
6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25
Final Resolution to
City Council
December 12th
814_20
Create to ERCOT
COMPLETE
MCL
to REPs & Brokers
COMPLETE
Customer Choice
Jan 5 – Feb 15 @ 5pm
REPs submit 814_16 MVIs (MMRD)
DREP Assign
2/19 – 3/1
Rev: November 6, 2023
End to End
Transaction Testing
Historical Data to ERCOT
In Progress
Market Ops # LIVE
January 5th
866-949-5862
REP/Customer Workshops
Jan 5th
3pm - 8pm
Jan 6th
10am – 4pm
REP/Customer Workshops
Jan 22
3pm - 8pm
Jan 23
3pm - 8pm
REP/Customer Workshop
Feb 10th
10am – 4pm
Last Chance for Customer Choice
Feb 17 – Mar 3
814_16 MVI (MMRD+1)
Market
Go
LIVE
March 4
(meter cycle #2)
Thru
April 1
(meter cycle #1)
Transition Customers to REPs on cycle date
Send 867_04
1 DAY HOLD
Feb 16th
Hold all MVIs
Move final 30% customers to ERCOT
Complete by Dec 11th
Current LP&L Tariff
Delivery Service Tariff