## Slide 1
Project Update
December 15, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  Major Projects
  2023 Release Targets
  2024 Release Targets
  Additional Project Status Information
  Priority/Rank Recommendations for Revision Requests with Impacts
    None
  Technology Working Group (TWG)
    Meeting on 12/14/2023
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 November Off-Cycle Release – 11/2/2023 In Stabilization
  EMS Upgrade
2023 November Off-Cycle Release – 11/19/2023 and 12/1/2023 Complete
  NPRR1026(a) – BESTF-7 Self-Limiting Facilities [RIOO portion]
  NPRR1164 – Black Start and Isochronous Control Capable Identification
  PGRR081 – Related to NPRR1026, BESTF-7 Self-Limiting Facilities
  RRGRR033 – Related to NPRR1164, Black Start and Isochronous Control Capable Identification
2023 December Release – R6 – 12/5/2023-12/7/2023 Complete
  SCR807 – Increase CRR Transaction Capability
  SCR816 – CRR Auction Bid Credit Enhancement
  SCR822 – Create Daily Energy Storage Integration Report and Dashboard
  NOGRR249(a) – Communication of System Operating Limit Exceedances [GridGeo portion]
2023 December Off-Cycle Release – 12/19/2023 In Flight
  SCR824 – Increase File Size and Quantity Limits for RIOO Attachments
2023 December Off-Cycle Release – 12/20/2023 In Flight
  NPRR1153 – ERCOT Fee Schedule Changes
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Major Projects

## Slide 5: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 NPRR1135 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR1154 LPGRR070 NPRR1163 NPRR1136 NPRR1175 NPRR1189 OBDRR048 EMS Upgrade SCR824 | SCR807 SCR816 SCR822 NOGRR249(a) NPRR1026(a) NPRR1164 PGRR081 RRGRR033 NPRR1153
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1020(a) – EPS Metering portion
NPRR1026(a) – SLF – RIOO portion
NPRR1096(b) – ECRS portion
NOGRR249(a) – GridGeo portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,995,1004,1006,1007,1019,1023,1030,1032,1034,1057, 1077,1105, 1111,1128,1131 SCRs: 799,805,810,818,819 PGRRs: 066,076,088,091,094,099,103 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
11/2
7/14
ü
ü
ü
10/1
ü
EMS Upgrade Freeze – July 2023 – Jan. 2024
11/1
6/28
ü
12/19
E
11/19 and 12/1
12/20

## Slide 6: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/25 | February 2/22 | March 3/28 | April 4/25 | May 5/30 | June 6/27
NPRR1092(b) Public API Enhancements | NPRR1132(a) RRGRR032 NOGRR249(b) | NPRR1040 NPRR1186 NPRR1026(b) |  | NPRR1149 NPRR1121 NPRR1090 NPRR962 NPRR1196 Forecast Presentation Platform | NPRR1002 RRGRR023 SCR819 NPRR1111
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1026(b) – SLF – Reporting portion
NPRR1092(b) – Limit RUC Opt-Out Provision
NPRR1132(a) – Operating Limits in Cold and Hot Conditions – RIOO portion
NOGRR249(b) – MIS posting
E
E
E
E
E
E
E
E
P
P
P
P
July 7/25 | August 8/22 | September 9/26 | October 10/24 | TX SET 5.0 11/10 | December 12/11-12/12
 | SCR813 |  |  | NPRR1095 SCR817 SCR823 RMGRR172 | NPRR1023
R7
R8
R9
R10
R11
E
E
E
E
E
P
E
2/1
3/1
NS
P
P
NS
NS

## Slide 7: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR945 | Net Metering Requirements | Not Started | Start delayed due to an internal project dependency
NPRR1004 | Load Distribution Factor Process Update | Not Started | Analyzing a March 2024 start
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing start date options
NPRR1058 | Resource Offer Modernization | Not Started | Assessing start date options
NPRR1091 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | Assessing start date options
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Assessing start date options
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Analyzing a February 2024 start
NPRR1171 | Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Not Started | Assessing options – 600+ hours of vendor labor required
SCR799 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | Analyzing a July 2024 start
SCR805 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | Assessing start date options
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Increasing granularity for SCED disclosure reporting
Red Text: New additions and updates

## Slide 8: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
SCR825 | ERCOT Voice Communications Aggregation | TBD | TBD | More time needed to complete IA
Recommendations for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3820
Next available 2024 Rank in Business Strategy = 4090
Next available Rank in Regulatory = 380

## Slide 9: Technology Working Group (TWG)
TWG meeting held on 12/14/2023
Agenda: