## Slide 1
Quarterly Stability Assessment Requirements
Jenifer Fernandes
ERCOT
Resource Integration Working Group
December 20, 2023

## Slide 2: Quarterly Stability Assessment
Planning Guide 5.3.5
  Every generation interconnection request is required to be studied as part of a Quarterly Stability Assessment according to synchronization date.
Planning Guide 5.3.5 (2)- timeline for the QSA is in accordance with the following table:
Planning Guide 5.3.5 (4): states the prerequisites to be satisfied prior to the large generator being included in the QSA.
Generator Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Prerequisites for QSA
Completed and approved FIS All studies must be completed and finalized. Steady state study, Short circuit study, Dynamics study, Facilities study.
Completed and approved reactive study
Signed SGIA Signed SGIA should include the correct MW amount, inverter type and description of the POIB/POI
Financial commitment
Notice to Proceed
RIOO-Create substation details "Planning" commitment level complete? Received Planning 6.9 substation details in RIOO-IS. Refer to Entering Resource Registration Data in RIOO-IS.
Collector System Model [(.raw + .seq) OR .OLR files are accepted] IRR's only. BESS currently optional but recommended. Included as an attachment in a zip folder labeled “Collector System Model” in RIOO-IS.

## Slide 4: Prerequisites for QSA
Collector System Template (https://www.ercot.com/files/docs/2020/06/30/Collector_System_Template.zip) IRR's only. BESS currently optional but recommended. Included as an attachment in a zip folder labeled “Collector System Model” in RIOO-IS.
PSSE Dynamics Model
Model Quality Test Package for PSSE (PGRR075)
TSAT Dynamic Model TSAT Dynamic Model for UDM (User defined model) should have the same performance as the PSSE Dynamic Model.
Model Quality Test Package for TSAT UDM (PGRR102)
TSAT Dynamic Data Approved by ERCOT Operations? Reviewed and approved by ERCOT Operations.
PSCAD Model (.psc or .pscx files are accepted)
Model Quality Test Package for PSCAD received?
PSCAD Unit Model Validation received?

## Slide 5: Prerequisites for QSA
PSSE, PSCAD models and model quality tests validated for usability by ERCOT DSD? To be reviewed and approved by ERCOT once Dynamics Study is approved and PSCAD Dynamic model and MQT are received.
Air permit from TCEQ (if required)
Declaration of water adequacy (if not IRR)

## Slide 6: Notes on QSA
Following changes to the model after FIS studies are complete may affect the projects QSA qualification:
  Inverter changes.
  Changes to the dynamic model after stability study is finalized.
    Parameter changes.
    Topology changes.
  COD is changed and the case that would be used to do FIS study base on new COD is 2 case years or more different that original FIS study case year.
Inform the lead TSP and ERCOT early of the changes to determine if restudies are required ahead of the QSA.

## Slide 7: Questions?
Thank you!