## Slide 1
Project Update
January 11, 2024
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  Major Projects
  2023 Releases
  2024 Release Targets
  Additional Project Status Information
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1208 – Creation of Invoice Report
    SCR825 – ERCOT Voice Communications Aggregation
  Technology Working Group (TWG)
    Meeting held on 12/14/2023
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 December Off-Cycle Release – 12/19/2023 Complete
  SCR824 – Increase File Size and Quantity Limits for RIOO Attachments
2023 December Off-Cycle Release – 12/20/2023 Complete
  NPRR1153 – ERCOT Fee Schedule Changes
2024 January Off-Cycle Release – 1/1/2024 Complete
  PGRR098(a) – Consideration of Load Shed in Transmission Planning Criteria
    Section 4.1.1.8
2024 January Release – R1 – 1/25/2024 In Flight
  NPRR1092(b) – Reduce RUC Offer Floor and Limit RUC Opt-Out Provision
    “Limit RUC Opt-Out Provision” portion
2024 February Off-Cycle Release – 2/1/2024 In Flight
  Public API Enhancements
  Ancillary Service Responsibility Telemetry Changes for ESRs
    See ROS/WMS materials and Market Notices for more information
2024 February Release – R2 – 2/22/2024 In Flight
  NPRR1132(a) – Communicate Operating Limitations during Cold and Hot Weather Conditions
  RRGRR032 – Related to NPRR1132
  NOGRR249(b) – Communication of System Operating Limit Exceedances
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Major Projects
Other Project Highlights

## Slide 5: 2023 Releases – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 NPRR1135 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR1154 LPGRR070 NPRR1163 NPRR1136 NPRR1175 NPRR1189 OBDRR048 EMS Upgrade SCR824 | SCR807 SCR816 SCR822 NOGRR249(a) NPRR1026(a) NPRR1164 PGRR081 RRGRR033 NPRR1153
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1020(a) – EPS Metering portion
NPRR1026(a) – SLF – RIOO portion
NPRR1096(b) – ECRS portion
NOGRR249(a) – GridGeo portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,995,1004,1006,1007,1019,1030,1032,1034,1057, 1077,1105,1111, 1128,1131 SCRs: 799,805,810,818,819 PGRRs: 066,076,088,091,094,099,103 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
11/2
7/14
ü
ü
ü
10/1
ü
EMS Upgrade Freeze – July 2023 – Jan. 2024
11/1
6/28
ü
12/19
11/19 and 12/1
12/20

## Slide 6: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/25 | February 2/22 | March 3/28 | April 4/25 | May 5/30 | June 6/27
NPRR1092(b) PGRR098(a) Public API Enhancements ESR Telemetry | NPRR1132(a) RRGRR032 NOGRR249(b) | NPRR1040 NPRR1186 NPRR1026(b) |  | NPRR1149 NPRR1121 NPRR1090 NPRR962 NPRR1196 Forecast Presentation Platform | NPRR1002 RRGRR023 SCR819 NPRR1111
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1026(b) – SLF – Reporting portion
NPRR1092(b) – Limit RUC Opt-Out Provision
NPRR1132(a) – Operating Limits in Cold and Hot Conditions – RIOO portion
NOGRR249(b) – MIS posting
PGRR098(a) – Section 4.1.1.8
E
E
E
E
E
E
E
ü
E
E
E
E
E
P
July 7/25 | August 8/22 | September 9/26 | October 10/24 | TX SET 5.0 11/10 | December 12/11-12/12
 | SCR813 |  |  | NPRR1095 SCR817 SCR823 RMGRR172 | NPRR1023
R7
R8
R9
R10
R11
E
E
E
E
E
E
E
2/1
3/1
I
P
P
P
P
1/1

## Slide 7: Additional Project Status Information
RR | Description | Proj Phase | Additional Detail
NPRR945 | Net Metering Requirements | Not Started | Likely to start soon as an O&M effort
NPRR1004 | Load Distribution Factor Process Update | Not Started | Analyzing a March 2024 start
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing start date options
NPRR1058 | Resource Offer Modernization | Not Started | Analyzing a July 2024 start
NPRR1091 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | Assessing start date options – 160 hours of vendor labor required
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Analyzing a July 2024 start
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Analyzing a February 2024 start
NPRR1139 | Adjustments to Capacity Shortfall Ratio Share for IRRs | Not Started | Analyzing an April 2024 start
NPRR1171 | Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Not Started | Assessing options – 600+ hours of vendor labor required
PGRR088 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Not Started | RIOO portion likely to be O&M
SCR799 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | Analyzing a July 2024 start
SCR805 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | Assessing start date options
Red Text: New additions and updates

## Slide 8: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1170 | Capturing Natural Gas Delivery Information for Natural Gas Generation Resources | N/A | N/A | Revised IA: <$5k O&M Previous IA: $75k-$125k, 6-9 months
NPRR1208 | Creation of Invoice Report | TBD | TBD | $40k-$60k, 4-6 months Impacted System(s): Reporting
NPRR1213 | Allow DGRs and DESRs on Circuits Subject to Load Shed to Provide ECRS | TBD | TBD | More time needed to complete IA
SCR825 | ERCOT Voice Communications Aggregation | TBD | TBD | $150k-$350k, 7-10 months Impacted System(s): Registration, EMS, MMS, Integration, Telecom
Recommendations for…
PPL Rank Information
Next available 2024 Rank in Business Strategy = 4090
Next available Rank in Regulatory = 380

## Slide 9: Technology Working Group (TWG)
TWG meeting held on 12/14/2023
Agenda: