## Approach
Contents of this Spreadsheet: |  |  |  | Summary Counts
| 3 tabs |  |  | Complete | 43 | 32.09%
| 1 | Explanatory information |  | In-Flight | 25 | 18.66%
| 2 | Recent Revision Requests List |  | On Hold | 9 | 6.716%
| 3 | ProjectCenter - PPM export |  | Not Started | 57 | 42.54%
|  |  |  | Total | 134 | 100%
Definitions
"Recent Revision Requests" = 2022 Aging Revision Request list updated for new items and latest status
Review Timeline:
February 2024 PRS
Explanation of project list (contents, definitions, approach to review, etc.)
General discussion - may not need a deep dive into the list this month
March 2024 PRS
Discuss "Not Started" items that ERCOT sees as candidates to be worked in the next few months
PRS discussion on High Priority Revision Requests
April 2024 PRS
TBD - if needed
Review updates to the data in this spreadsheet
Added and populated a "Revised Prioritization Recommendation" column in the "Prev List - Not Started" tab
Populated the "Prioritization Category Recommendation" column in the "New Items - Not Started" tab
Populated the "High / Medium / Low" column in the "New Items - Not Started" tab
Updated "ERCOT Recommendation" column to group related scenarios
Highlighted noteworthy changes in yellow
Review ERCOT category recommendations
Resolve any open questions from the June PRS discussion
Homework for March 2024 PRS meeting:
Market Participants
Refamiliarize yourself with the contents of the "Recent Revision Requests" tab
Consider which items need to be considered High Priority
Consider whether any "Not Started" or "On Hold" items may not longer be necessary based on developments since the time of their original approval
ERCOT
Continue populating the "Notes" column
Highlight projects that have conflicts with critical in-flight efforts and therefore are candidates to be worked 12 months (or more) in the future
Highlight projects that have limited conflicts with critical in-flight efforts and therefore are candidates to start in upcoming months

## Recent Revision Requests
|  | REVISION REQUEST PRIORITIZATION | [7 empty] | Total Count = 134 |  | Start here: Filter on "Not Started" and "On Hold"
Group | Target Start | Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Notes | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA)
Grid | 2020-01-01 | Revision Requests | 2020 | 2880 |  |  | SCR804 | PPL | 2019-10-08 | ERCOT GridGeo Access for Transmission Operators | Complete | $400k - $600k | 6 - 12 months | Complete | Grid Ops Systems | 94% | 28%
Markets | 2020-03-01 | Revision Requests | 2020 | 2630 |  |  | NPRR905 | PPL | 2019-02-12 | CRR Balancing Account Resettlement | Complete | $60k - $80k | 4 - 6 months | Complete | S&B | 72% | 0%
Other | 2020-03-01 | Revision Requests | 2020 | 2930 |  |  | NPRR902 | PPL | 2019-12-10 | ERCOT Critical Energy Infrastructure Information | Complete | $150k - $225k | 6 - 9 months | Complete | Reporting | 55% | 0%
Grid | 2020-05-01 | Base Operations | 2019 | 230 |  |  | PGRR070 | PPL | 2019-06-11 | Revised Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability Assessments | Complete | $100k - $150k | 12 - 18 months | Complete | Reporting | 100% | 0%
Markets | 2020-05-01 | Revision Requests | 2020 | 2990 |  |  | NPRR998 | PPL | 2020-04-14 | ERS Deployment and Recall Messages | Complete | $15k - $25k | 3 - 5 months | Complete | MMS | 77% | 0%
Other | 2020-07-01 | Regulatory | 2020 | 240 | 1 - Regulatory | 1 - High | NPRR978 | PPL | 2020-02-11 | Alignment with Amendments to PUCT Substantive Rule 25.505 | Complete | $65k-$95k | 6 - 8 months | Complete | Reporting | 53% | 0%
Other | 2020-07-01 | Regulatory | 2020 | 250 | 1 - Regulatory | 1 - High | SCR806 | PPL | 2020-02-11 | Adding QSE and DME Information to Disclosure Reports | Complete | $65k-$95k | 4 - 6 months | Complete | Reporting | 100% | 0%
Grid | 2020-07-01 | Revision Requests | 2020 | 2980 | 2 - High Priority | 1 - High | NPRR974 | PPL | 2020-02-01 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | Complete | $50k-$80k | 5-7 months | Previously flagged as "High Priority" | Reporting | 62% | 0% | DAIP, MMS, External Public
Grid | 2020-11-01 | Regulatory | 2020 | 300 | 1 - Regulatory | 1 - High | NOGRR195 | PPL | 2020-08-01 | Generator Voltage Control Tolerance Band | Complete | $30k-$50k | 4-6 months | Complete | EMS | 67% | 0% | EMS, BI & Data Analytics
Grid | 2020-12-01 | Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 1 | Complete | $300k-$450k | 9-12 months | Complete | NMMS | 100% | 76% | NMMS
Grid | 2020-12-01 | Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 2 | Complete | $300k-$450k | 9-12 months | Complete | NMMS | 100% | 76% | NMMS
Grid | 2021-01-13 | Revision Requests | 2020 | 3080 |  |  | SCR811 | PPL | 2020-10-13 | Integrate Solar (PVGR) Forecasts and Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation | Complete | $60k-$90k | 5-7 months | Complete | MMS | 76% | 35% | MMS, EMS
Markets | 2021-04-13 | Revision Requests | 2021 | 2705 |  |  | NPRR1051 | PPL | 2021-02-09 | Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k-$20k | 3-5 months | Complete | MMS | 100% | 0% | Market Operation Systems
Markets | 2021-07-26 | Revision Requests | 2021 | 3340 |  |  | NPRR1081 | PPL | 2021-06-28 | Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | Complete | MMS | 45% | 0% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Retail | 2021-09-01 | Revision Requests | 2021 | 1440 |  |  | SCR815 | PPL | 2021-08-19 | MarkeTrak Administrative Enhancements | Complete | $350k - $550k | 15 - 20 months | Complete | Retail | 98% | 0%
Grid | 2021-10-01 | Revision Requests | 2020 | 2910 | 5 - Consider When Efficiencies Exist With Another Effort | 1 - High | SCR800 | PPL | 2019-12-01 | Addition of DC Tie Ramp to GTBD Calculation | Complete | $30k-$50k | 3-5 months | Complete | EMS | 38% | 0% | EMS, Data Management, MMS, BI & Data Analytics
Grid | 2021-10-01 | Revision Requests | 2020 | 3040 | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | SCR809 | PPL | 2020-06-01 | Changes to External Telemetry Validations in Resource Limit Calculator | Complete | $40k-$60k | 4-6 months | Complete | EMS | 83% | 0% | EMS, BI & Data Analytics
Markets | 2021-10-01 | Base Operations | 2021 | 3320 |  |  | LPGRR068 | PPL | 2021-06-08 | Add BUSLRG and BUSLRGDG Profile Types | Complete | $20k - $40k | 3 - 6 months | Complete | BI & Data Analytics | 53% | 0%
Grid | 2021-11-02 | Revision Requests | 2019 | 2770 | 2 - High Priority | 1 - High | NPRR939 | PPL | 2019-10-01 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k-$100k | 5-7 months | Previously flagged as "High Priority" | MMS | 70% | 0% | MMS, DAIP, Integration
Grid | 2021-12-01 | Regulatory | 2022 | 320 | 1 - Regulatory | 1 - High | NPRR1108 | PPL | 2022-04-28 | ERCOT Shall Approve or Deny All Resource Outage Requests | Complete | $275k-$375k | 7-10 months | Complete | OS | 58% | 27% | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems
Markets | 2022-01-01 | Revision Requests | 2021 | 3350 |  |  | SCR814 | PPL | 2021-10-28 | Point-to-Point (PTP) Obligation Bid Interval Limit | Complete | $10k-$25k | 3 - 5 months | Complete | MMS | 100% | 0% | Market Operation Systems
Markets | 2022-03-10 | Regulatory | 2022 | 330 | 1 - Regulatory | 1 - High | NPRR1120 | PPL | 2022-03-31 | Create Firm Fuel Supply Service | Complete | $250k-$400k | 9-12 months | Complete | S&B | 70% | 0% | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Markets | 2022-03-21 | Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 2 - Medium | NPRR1020a | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - EPS Metering | Complete | $175k-$225k | 8-12 months | Complete | EPS Meter | 86% | 0% | EPS Meter
Grid | 2022-07-01 | Regulatory | 2022 | 325 | 1 - Regulatory | 1 - High | NPRR1097 | PPL | 2022-03-31 | Create Resource Forced Outage Report | Complete | $20k-$40k | 3-5 months | Complete | Reporting | 90% | 0% | Data Management & Analytic Systems, ERCOT Website and MIS Systems
Grid | 2022-07-01 | Revision Requests | 2021 | 3250 | 3 - Consider When Resources are Available | 1 - High | SCR812 | PPL | 2020-12-08 | Create Intermittent Renewable Generation Integration Report | Complete | $30k-$60k | 5-7 months | Complete | Reporting | 68% | 0% | DAIP, Reporting
Grid | 2022-08-01 | Revision Requests | 2021 | 3330 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1063 | PPL | 2021-08-19 | Dynamic Rating Transparency | Complete | $15k - $25k | 3 - 4 months | Complete | MIS | 100% | 0% | ERCOT Website and MIS Systems
Grid | 2022-09-01 | Revision Requests | 2021 | 3290 | 3 - Consider When Resources are Available | 1 - High | NPRR1040 | PPL | 2021-02-09 | Compliance Metrics for Ancillary Service Supply Responsibility | Execution | $20k-$30k | 3-5 months | In Flight | BI & Data Analytics | 90% | 0% | Data Management & Analytic Systems
Grid | 2023-04-03 | Revision Requests | 2023 | 3730 |  |  | SCR820 | PPL | 2022-11-03 | Operator Real-Time Messaging During Emergency | Planning | $750k - $1.25M | 18 - 24 months | In Flight | Grid Ops Systems | 98% | 0%
Markets | 2023-04-03 | Revision Requests | 2023 | 3770 |  |  | NPRR1154 | PPL | 2023-01-26 | Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | Complete | $40k - $70k | 5 - 7 months | Complete | S&B | 89% | 0% | S&B, Data Management & Analytic Systems
Markets | 2023-05-01 | Revision Requests | 2022 | 3630 |  |  | NPRR1112 | PPL | 2022-09-15 | Elimination of Unsecured Credit Limits | Complete | $10k - $20k | 3 - 5 months | Complete | CMM | 100% | 0%
Grid | 2023-06-01 | Revision Requests | 2020 | 2870 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR962 | PPL | 2019-10-01 | Publish Approved DC Tie Schedules | Execution | $15k-$30k | 3-4 months | In Flight | Reporting | 86% | 0% | DAIP, BI & Data Analytics
Markets | 2023-06-01 | Revision Requests | 2021 | 3360 | 2 - High Priority | 1 - High | NPRR1090 | PPL | 2021-10-28 | ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Execution | $15k - $25k | 3 - 5 months | Previously flagged as "High Priority" | MMS | 71% | 0% | Data Management & Analytic Systems, Market Operation Systems
Markets | 2023-06-01 | Revision Requests | 2022 | 3590 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1121 | PPL | 2022-07-14 | Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Execution | $25k - $45k | 3 - 5 months | In Flight | Reporting | 85% | 0% | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems
Grid | 2023-06-01 | Revision Requests | 2023 | 3720 |  |  | NPRR1136 | PPL | 2022-09-15 | Updates to Language Regarding a QSE Moving Ancillary Service Responsibility Between Resources | Complete | $15k - $25k | 3 - 5 months | Complete | MMS | 100% | 0%
Markets | 2023-07-01 | Regulatory | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1007 | PPL | 2020-12-08 | Real-Time Co-Optimization (RTC) | Planning | $50M-$55M | 3.5-4.5 years | Part of RTC+B | MMS | 53% | 24% | MMS, EMS, Integration, DAIP, S&B, NMMS, CMM, OTS, Registration
Grid | 2023-07-01 | Revision Requests | 2020 | 3015 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1014 | PPL | 2020-12-08 | BESTF-4 Energy Storage Resource Single Model | Planning | $3.5M-$4.5M | 2-3 years | Part of RTC+B | EMS | 60% | 49% | EMS, MMS, DAIP, S&B, OS, Integration, NMMS, RIOO, Registration
Markets | 2023-07-01 | Revision Requests | 2022 | 3005 | 2 - High Priority | 1 - High | NPRR1092 | PPL | 2022-04-28 | Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Execution | $50k - $100k | 4 - 6 months | Previously flagged as "High Priority" | MMS | 100% | 0% | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems
Grid | 2023-07-01 | Revision Requests | 2023 | 3595 |  |  | NPRR1186 | Pending Board Approval | TBD | Implement consideration of ESR SOC in ERCOT tools and studies | Execution | $500k - $700k | 7 - 10months | In Flight | MMS | 64% | 25%
Grid | 2023-07-03 | Regulatory | 2023 | 360 | 1 - Regulatory | 1 - High | NOGRR249 | PPL | 2023-10-12 | Communication of System Operating Limit Exceedances | Execution | $100k - $150k | 5 - 7 months | In Flight
Grid | 2023-07-03 | Revision Requests | 2020 | 3010 |  |  | NPRR1026 | PPL | 2020-12-08 | BESTF-7 Self-Limiting Facilities | Execution | $200k-$250k | 7-10 months | In Flight | RIOO | 58% | 0% | RIOO-RS, EMS, OTS, DAIP, External Public
Other | 2023-07-03 | Revision Requests | 2023 | 3790 |  |  | NPRR1153 | PPL | 2023-03-23 | ERCOT Fee Schedule Changes | Complete | $20k - $30k | 3 - 5 months | Complete | RIOO
Grid | 2023-08-01 | Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | SCR813b | PPL | 2021-10-28 | NMMS Jointly-Rated Equipment Coordination Confirmation | Planning | $100k - $150k | 5 - 7 months | In Flight | NMMS | 100% | 40% | Network Management Systems
Other | 2023-08-01 | Revision Requests | 2023 | 3620 |  |  | SCR822 | PPL | 2022-09-15 | Create Daily Energy Storage Integration Report and Dashboard | Execution | $60k - $90k | 4 - 6 months | In Flight | BI & Data Analytics | 44% | 0%
Grid | 2023-09-01 | Regulatory | 2023 | 340 | 1 - Regulatory | 1 - High | NPRR1132 | PPL | 2023-01-26 | Communicate Operating Limitations during Cold and Hot Weather Conditions | Complete | $65k - $95k | 4 - 6 months | Complete | RIOO | 49% | 0%
Grid | 2023-12-01 | Revision Requests | 2022 | 3570 | 2 - High Priority | 2 - Medium | SCR819 | PPL | 2022-03-31 | Improving IRR Control to Manage GTC Stability Limits | Planning | $40k - $60k | 4 - 6 months | Previously flagged as "High Priority" | EMS | 70% | 0% | Energy Management Systems, Market Operation Systems
Markets | 2024-01-01 | Revision Requests | 2022 | 3500 | 3 - Consider When Resources are Available | 1 - High | NPRR1023 | PPL | 2021-04-13 | Change to CRR Repossession Process | Planning | $250k - $350k | 10 - 14 months | Roadmap - CRR | CRR | 100% | 65% | Congestion Revenue Rights (CRR)
Markets | 2024-03-01 | Revision Requests | 2021 | 3270 | 3 - Consider When Resources are Available | 2 - Medium | NPRR945 | PPL | 2020-12-08 | Net Metering Requirements | Not Started | $10k-$20k | 3-4 months | O&M | RIOO | 64% | 0% | RIOO-RS, External Public
Markets | 2024-04-01 | Revision Requests | 2021 | 3210 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1004 | PPL | 2020-08-01 | Load Distribution Factor Process Update | Not Started | $45k-$65k | 5-7 months | Resources confirmed for Target Start | MMS | 41% | 0% | MMS, Integration, DAIP, External Public
Markets | 2024-04-01 | Revision Requests | 2023 | 3720 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1131 | PPL | 2022-09-15 | Controllable Load Resource Participation in Non-Spin | Not Started | $100k - $150k | 6 - 9 months | Resources confirmed for Target Start | MMS | 40% | 0% | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems
Markets | 2024-04-01 | Revision Requests | 2023 | 3740 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1139 | PPL | 2022-11-03 | Adjustments to Capacity Shortfall Ratio Share for IRRs | Not Started | $15k - $30k | 3 - 5 months | Resources confirmed for Target Start | S&B | 100% | 0%
Retail | 2024-06-01 | Revision Requests | 2024 | 3600 | 3 - Consider When Resources are Available | 2 - Medium | RMGRR168 | PPL | 2022-09-15 | Modify ERCOT Responsibilities During the Mass Transition | Not Started | $50k - $75k | 5 - 8 months | Resources confirmed for Target Start | Registration | 100% | 0%
Grid | 2024-07-01 | Revision Requests | 2019 | 2710 | 3 - Consider When Resources are Available | 1 - High | SCR799 | PPL | 2019-06-01 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | $150k-$250k | 5-7 months | Revisiting resource requirements | SOTE | 100% | 0% | SOTE
Grid | 2024-10-01 | Revision Requests | 2019 | 2580 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | PGRR066 | PPL | 2018-12-01 | Interconnection Request Cancellation and Creation of Inactive Status | Not Started | $100k-$150k | 4-6 months | Roadmap - RIOO | RIOO | 100% | 0% | Resource Integration
Grid | 2024-10-01 | Revision Requests | 2021 | 3200 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | PGRR076 | PPL | 2020-08-01 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Not Started | $50k-$75k | 6-9 months | Roadmap - RIOO | RIOO | 57% | 0% | Resource Integration, Integration, Data Access & Transparency
Markets | 2025-01-01 | Revision Requests | 2020 | 2850 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR936 | PPL | 2019-10-01 | CRR Account Holder Limits | Not Started | $150k-$250k | 8-10 months | Roadmap - CRR | CRR | 90% | 51% | CRR, DAIP
Grid | 2025-12-01 | Revision Requests | 2023 | 3710 | 3 - Consider When Resources are Available | 1 - High | SCR818b | PPL | 2022-04-28 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started | $300k - $500k | 9 - 12 months |  | NMMS | 100% | 64% | Grid Modeling Systems
Grid | 2026-07-01 | Revision Requests | 2022 | 2530 | 9 - No Action Needed | 2 - Medium | NPRR1098 | PPL | 2022-03-31 | DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | Southern Spirit | BI & Data Analytics | 100% | 0% | Grid Decision Support Systems
Grid | 2026-07-01 | Revision Requests | 2019 | 2530 | 5 - Dependent on Other Project | 2 - Medium | NPRR857 | PPL | 2018-10-01 | Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k-$700k | 12-18 months | Southern Spirit | OS | 53% | 25% | OS, EMS, OTS, WAN, NMMS, External Public, Integration, BI & Data Analytics, REG, Data Access & Transparency, DAIP
Grid | 2026-07-01 | Revision Requests | 2021 | 3280 | 9 - No Action Needed | 2 - Medium | NPRR1034 | PPL | 2021-02-09 | Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k-$70k | 5-7 months | Southern Spirit | BI & Data Analytics | 52% | 0% | Pi, EIS, NoticeBuilder, MIS
Grid | 2030-01-01 | Regulatory | 2022 | 310 | 1 - Regulatory | 1 - High | PGRR099 | PPL | 2022-03-31 | Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | Execution | $20k - $30k | 3 - 5 months | In Flight | RIOO | 100% | 0% | Resource Integration and Ongoing Operations
Markets | 2030-01-01 | Revision Requests | 2022 | 3610 |  |  | NPRR1135 | PPL | 2022-09-15 | Add On-Line Status Check for Resources Telemetering OFFNS for Ancillary Service Imbalance Settlements | Complete | $15k - $25k | 3 - 4 months | Complete | EMS | 100% | 0%
Markets | 2023-07-01 | Revision Requests | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1204 | PPL | 2024-02-01 | Considerations of State of Charge with Real-Time Co-Optimization Implementation | Planning | $750k - $1.0M | N/A | Part of RTC+B | MMS | 96% | 77% | MMS, EMS
Markets |  | Regulatory | 2019 | 220 |  |  | NPRR885 | PPL | 2019-06-11 | Must-Run Alternative (MRA) Details and Revisions Resulting from PUCT Project No_ 46369, Rulemaking Relating to Reliability Must-Run Service | On Hold | $500k - $700k | 8 - 12 months | Keep On Hold | S&B | 29% | 3%
Markets |  | Revision Requests | 2019 | 2510 | 3 - Consider When Resources are Available | 1 - High | NPRR829 | PPL | 2017-10-01 | Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k-$300k | 5-10 months |  | CMM | 26% | 0% | CMM, NMMS, EMS, REG, Integration, DAIP, Data Access & Transparency
Markets |  | Revision Requests | 2019 | 2720 | 2 - High Priority | 1 - High | NPRR904 | PPL | 2019-08-01 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $200k-$300k | 6-9 months | One of multiple SCED pricing run changes. Either bundle or prioritize against other changes to the same process. Previously flagged as "High Priority". | MMS | 85% | 41% | MMS, EMS, BI & Data Analytics, DAIP
Markets |  | Revision Requests | 2019 | 2720 | 2 - High Priority | 1 - High | OBDRR009 | PPL | 2019-08-01 | ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | On Hold | $30k-$50k | 4-6 months | One of multiple SCED pricing run changes. Either bundle or prioritize against other changes to the same process. Previously flagged as "High Priority". | MMS | 40% | 0% | MMS, DAIP, BI & Data Analytics
Markets |  | Revision Requests | 2020 | 2815 | 2 - High Priority | 1 - High | NPRR963 | PPL | 2020-02-01 | Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model) | On Hold | $150k-$200k | 8-12 months | Previously flagged as "High Priority" - perhaps not anymore | Reporting | 31% | 0% | DAIP, S&B, EMS, BI & Data Analytics, Integration
Markets |  | Revision Requests | 2020 | 2890 | 2 - High Priority | 1 - High | NPRR930 | PPL | 2019-10-01 | Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k-$200k | 5-7 months | Previously flagged as "High Priority" | MMS | 74% | 39% | MMS, OS, DAIP, Data Access & Transparency, External Public
Grid |  | Revision Requests | 2020 | 3010 | 2 - High Priority | 1 - High | NPRR987 | PPL | 2020-06-01 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | On Hold | $150k-$200k | 6-9 months | Previously flagged as "High Priority" | MMS | 34% | 9% | MMS, S&B, EMS, Integration, BI & Data Analytics, DAIP
Markets |  | Revision Requests | 2020 | 3020 | 3 - Consider When Resources are Available | 1 - High | NPRR1006 | PPL | 2020-06-01 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | $140k-$180k | 6-9 months |  | MMS | 62% | 29% | MMS, DAIP, EMS, S&B, BI & Data Analytics
Markets |  | Revision Requests | 2020 | 3030 | 2 - High Priority | 1 - High | NPRR1019 | PPL | 2020-06-01 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k-$140k | 5-7 months | Previously flagged as "High Priority" | MMS | 98% | 44% | MMS, BI & Data Analytics
Grid | 2023-07-01 | Revision Requests | 2020 | 3060 | 3 - Consider When Resources are Available | 1 - High | NPRR1002 | PPL | 2020-08-01 | BESTF-5 Energy Storage Resource Single Model Registration and Charging Restrictions in Emergency Conditions | Planning | $100k-$200k | 7-10 months | Roadmap - RIOO | RIOO | 83% | 0% | Resource Integration, Integration, DAIP
Grid |  | Revision Requests | 2018 | 2090 | 5 - Dependent on Other Project | 2 - Medium | NPRR825 | PPL | 2017-12-01 | Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k-$300k | 8-12 months |  | MMS | 82% | 0% | MMS, Data Access & Transparency, DAIP, Integration
Markets |  | Revision Requests | 2020 | 2515 | 3 - Consider When Resources are Available | 1 - High | NPRR1030 | PPL | 2020-08-01 | Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k-$225k | 8-12 months |  | S&B | 74% | 0% | S&B, DAIP, CMM, Integration
Markets |  | Revision Requests | 2019 | 2520 | 9 - No Action Needed | 3 - Low | NPRR841 | PPL | 2018-02-01 | Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Not Started | $60k-$80k | 4-6 months | Candidate for revision/removal? | S&B | 88% | 0% | S&B, Integration, Data Access & Transparency, CRM & Registration System
Grid |  | Revision Requests | 2020 | 2800 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR879 | PPL | 2018-12-01 | SCED Base Point, Base Point Deviation, and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k-$250k | 6-9 months |  | Reporting | 46% | 0% | DAIP, S&B, BI & Data Analytics, EMS, NMMS, Integration
Markets |  | Revision Requests | 2020 | 2840 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR918 | PPL | 2019-10-01 | Validation for PTP Obligations with Links to an Option | Not Started | $30k-$50k | 4-6 months |  | MMS | 57% | 0% | MMS, DAIP, Integration
Markets |  | Revision Requests | 2020 | 2860 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR941 | PPL | 2019-12-01 | Create a Lower Rio Grande Valley Hub | Not Started | $250k-$350k | 6-8 months |  | MMS | 91% | 75% | MMS, DAIP, EMS, External Public
Grid |  | Revision Requests | 2020 | 2900 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | NPRR965 | PPL | 2019-12-01 | GREDP Shutdown Exemption | Not Started | $10k-$20k | 3-5 months |  | BI & Data Analytics | 100% | 0% | BI & Data Analytics
Other |  | Revision Requests | 2020 | 2920 | 3 - Consider When Resources are Available | 2 - Medium | SCR805 | PPL | 2019-12-01 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k-$60k | 4-6 months |  | Reporting | 97% | 0% | DAIP, Data Access & Transparency
Markets |  | Revision Requests | 2020 | 2970 | 3 - Consider When Resources are Available | 2 - Medium | NPRR826 | PPL | 2020-02-01 | Mitigated Offer Caps for RMR Resources | Not Started | $100k-$200k | 6-8 months |  | MMS | 70% | 68% | MMS, DAIP, External Public, Data Access & Transparency
Grid |  | Revision Requests | 2020 | 3000 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR975 | PPL | 2020-06-01 | Load Forecast Model Transparency | Not Started | $75k-$100k | 6-9 months | Candidate for revision/removal? | EMS | 58% | 0% | EMS, DAIP, BI & Data Analytics
Grid |  | Revision Requests | 2020 | 3015 | 9 - No Action Needed | 2 - Medium | NPRR1029 | PPL | 2020-12-08 | BESTF-6 DC-Coupled Resources | Not Started | $800k-$1.2M | 16-24 months |  | EMS | 33% | 36% | EMS, OS, S&B, MMS, RIOO, Integration, DAIP, OTS, NMMS, Registration
Grid |  | Revision Requests | 2022 | 3020 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1105 | PPL | 2021-12-16 | Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months |  | MMS | 55% | 27% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Grid |  | Revision Requests | 2020 | 3050 | 3 - Consider When Resources are Available | 2 - Medium | SCR810 | PPL | 2020-08-01 | EMS System Change to Count DC Ties towards the 2% Constraint Activation Criterion | Not Started | $15k-$25k | 3-5 months |  | EMS | 100% | 0% | EMS
Markets |  | Revision Requests | 2022 | 3195 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1091 | PPL | 2021-12-16 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | One of multiple SCED pricing run changes. Either bundle or prioritize against other changes to the same process. | MMS | 73% | 40% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Markets |  | Revision Requests | 2021 | 3220 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1020b | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - Data Agg | Not Started | $175k-$225k | 8-12 months |  | EPS Meter | 86% | 0% | S&B
Grid |  | Revision Requests | 2021 | 3230 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR1035 | PPL | 2020-10-13 | DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k-$40k | 3-5 months |  | Reporting | 83% | 0% | DAIP, External Public
Grid |  | Revision Requests | 2021 | 3260 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1032 | PPL | 2020-12-08 | Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k-$150k | 5-8 months |  | MMS | 64% | 32% | MMS, S&B, DAIP, Integration
Markets |  | Revision Requests | 2021 | 3300 | 9 - No Action Needed | 3 - Low | NPRR1054 | PPL | 2021-02-09 | Removal of Oklaunion Exemption Language | Not Started | $10k-$15k | 3-4 months |  | S&B | 50% | 0% | Credit Settlements & Billing Systems, Integration Systems
Markets |  | Revision Requests | 2021 | 3310 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1057 | PPL | 2021-04-13 | Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months |  | MMS | 100% | 0% | Market Operation Systems
Grid |  | Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | PGRR088 | PPL | 2021-06-08 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Not Started | $20k- $40k | 3 - 5 months | O&M | RIOO | 53% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Grid |  | Revision Requests | 2022 | 3520 | 3 - Consider When Resources are Available | 2 - Medium | RRGRR028 | PPL | 2021-08-19 | Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months |  | RIOO | 93% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Grid |  | Revision Requests | 2022 | 3530 | 3 - Consider When Resources are Available | 2 - Medium | PGRR091 | PPL | 2021-08-19 | FIS Application Completion 60-Day Limit | Not Started | $15k - $30k | 3 - 5 months |  | RIOO | 100% | 0% | Resource Integration and Ongoing Operations
Grid |  | Revision Requests | 2022 | 3540 | 3 - Consider When Resources are Available | 2 - Medium | PGRR094 | PPL | 2021-10-28 | Clarify Notification Requirement for Generator Construction Commencement or Completion | Not Started | $10k - $20k | 1 - 2 months |  | RIOO | 100% | 0% | Resource Integration and Ongoing Operations
Grid |  | Revision Requests | 2022 | 3550 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1077 | PPL | 2021-12-16 | Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months |  | RIOO | 46% | 0% | Energy Management Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations
Markets |  | Revision Requests | 2023 | 3715 |  |  | NPRR1058 | PPL | 2022-11-03 | Resource Offer Modernization | Not Started | $100K - $150K | 6 - 8 months |  | MMS | 44% | 0%
Markets |  | Revision Requests | 2023 | 3750 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR1140 | PPL | 2022-11-03 | Recovering Fuel Costs for Generation Above LSL During RUC-Committed Hours | Not Started | $20k - $30k | 3 - 4 months |  | S&B | 100% | 0% | S&B
Grid |  | Revision Requests | 2024 | 3760 |  |  | NPRR1128 | PPL | 2023-01-26 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | $30k - $50k | 3 - 5 months |  | MMS | 64% | 0% | Market Operation Systems, Data Management & Analytic Systems, Channel Management Systems, Content Delivery Systems
Grid |  | Revision Requests | 2024 | 3900 |  |  | NOGRR226 | PPL | 2023-01-26 | Addition of Supplemental UFLS Stages | Not Started | $40k - $60k | 3 - 5 months | Work with NOGRR247 | EMS | 95% | 0% | Energy Management Systems, Grid Decision Support Systems
Grid |  | Revision Requests | 2024 | 4000 |  |  | SCR821 | PPL | 2023-01-26 | Voltage Set Point Target Information for Distribution Generation Resource (DGR) or Distribution Energy Storage Resource (DESR) | Not Started | $25k - $50k | 3 - 5 months |  | EMS | 100% | 0% | Energy Management Systems
Markets |  | Revision Requests | 2024 | 4010 |  |  | NPRR1145 | PPL | 2023-05-11 | Use of State Estimator-Calculated ERCOT-Wide TLFs in Lieu of Seasonal Base Case ERCOT-Wide TLFs for Settlement | Not Started | $50k - $80k | 3 - 6 months |  | S&B | 54% | 0%
Grid |  | Revision Requests | 2024 | 4020 |  |  | PGRR103 | PPL | 2023-10-12 | Establish Time Limit for Generator Commissioning Following Approval to Synchronize | Not Started | $40k-$60k | 4 - 6 months |  | RIOO | 78% | 0%
Markets |  | Revision Requests | 2024 | 4030 |  |  | NPRR1182 | PPL | 2023-10-12 | Inclusion of Controllable Load Resources and Energy Storage Resources in the Constraint Competitiveness Test Process | Not Started | $60k - $90k | 5 - 7 months |  | MMS | 100% | 0%
Other |  | Revision Requests | 2024 | 4040 |  |  | NPRR1183 | PPL | 2023-10-12 | ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without ECEII | Not Started | $50k - $75k | 4 - 6 months |  | ERCOT.com | 52% | 0%
Grid |  | Revision Requests | 2024 | 4050 |  |  | NPRR1171 | PPL | 2023-10-12 | Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Not Started | $350k - $550k | 9 - 12 months | Work with NPRR1213 | MMS | 93% | 50%
Markets |  | Revision Requests | 2024 | 4060 |  |  | NPRR1184 | PPL | 2023-11-30 | Update to Procedures for Managing Interest on Cash Collateral | Not Started | $100k - $150k | 6 - 9 months |  | CMM | 85% | 0%
Markets |  | Revision Requests | 2024 | 4070 |  |  | NPRR1172 | PPL | 2024-02-01 | Fuel Adder Definition, Mitigated Offer Caps, and RUC Clawback | Not Started | $65k - $85k | 4 - 7 months |  | S&B | 35% | 0%
Markets |  | Revision Requests | 2024 | 4080 |  |  | NPRR1201 | PPL | 2024-02-01 | Limitations on Resettlement Timeline and Default Uplift Exposure Adjustments | Not Started | $40k - $70k | 4 - 6 months |  | CMM | 73% | 0%
Other |  | Revision Requests | 2024 | 4090 |  |  | NPRR1208 | Pending Board Approval | TBD | Creation of Invoice Report | Not Started | $40k - $60k | 4 - 6 months |  | Reporting | 91% | 0%
Markets |  | Revision Requests | 2025 | 4500 | 9 - No Action Needed | 2 - Medium | NPRR995 | PPL | 2021-08-19 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k-$1.2M | 20-30 months | Market input needed - Post RTC? | RIOO | 44% | 4% | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations
Other |  | Revision Requests | 2025 | 4510 |  |  | SCR825 | Pending Board Approval | TBD | ERCOT Voice Communications Aggregation | Not Started | $150k-$250k | 7 - 10 months |  | Registration | 38% | 0%
Grid |  | Revision Requests | 2026 | 4700 |  |  | NOGRR215 | PPL | 2023-10-12 | Limit Use of Remedial Action Schemes | Not Started | $1.0M - $1.5M | 12 - 18 months |  | MMS | 67% | 65%
Grid |  | Revision Requests | N/A | N/A |  |  | NOGRR247 | PPL | 2023-10-12 | Change UFLS Stages and Load Relief Amounts | Not Started | <$10k | 1 - 2 months | Work with NOGRR226 | EMS | 83% | 0% | Energy Management Systems, Grid Decision Support Systems
Grid |  | Revision Requests | TBD | TBD |  |  | NPRR1213 | Pending PRS Approval | TBD | Allow DGRs and DESRs on Circuits Subject to Load Shed to Provide ECRS | Not Started | $350k-$450k | 8 - 12 months | Work with NPRR1171 | MMS | 87% | 43%
Markets |  | Revision Requests | TBD | TBD |  |  | NPRR1216 | Pending PRS Approval | TBD | Implementation of Emergency Pricing Program | Not Started | $125k - $175k | 5 - 7 months | Already implemented manually. Significant risk until NPRR is approved and automated. | S&B | 39% | 0%
Grid | 2022-10-01 | Revision Requests | 2020 | 2855 | 2 - High Priority | 1 - High | SCR807 | PPL | 2020-06-01 | Increase CRR Transaction Capability | Execution | $50k-$100k | 5-7 months | Previously flagged as "High Priority" | CRR | 95% | 60% | CRR, Integration
Markets | 2022-10-01 | Revision Requests | 2022 | 2855 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | SCR816 | PPL | 2022-03-31 | CRR Auction Bid Credit Enhancement | Execution | $50k - $80k | 4 - 6 months | Roadmap - CRR | CRR | 100% | 52% | Congestion Revenue Rights (CRR)
Retail | 2022-07-19 | Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | NPRR1095 | PPL | 2022-03-31 | Texas SET V5.0 Changes | Execution | $1.0M - $1.5M | 16 - 20 months | In Flight | Registration | 80% | 0% | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems
Retail | 2022-07-19 | Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | SCR817 | PPL | 2022-03-31 | Related to NPRR1095 MarkeTrak Validation Revisions Aligning with Texas SET V5_0 | Execution | $400k - $600k | 10 - 15 months | In Flight | Retail | 65% | 0% | CRM & Registration Systems, Integration Systems, Retail Systems
Retail | 2022-07-19 | Revision Requests | 2023 | 3700 |  |  | SCR823 | PPL | 2022-11-03 | ERCOT Mass System “County Name” File Updates for Texas SET V5.0 Implementation | Execution | $30k - $40k | N/A | In Flight | Retail | 100% | 0%
Markets | 2023-07-01 | Revision Requests | 2023 | 3780 |  |  | NPRR1149 | PPL | 2023-03-23 | Implementation of Systematic Ancillary Service Failed Quantity Charges | Execution | $120k - $160k | 6 - 8 months | In Flight | S&B | 71% | 0%
Markets |  | Revision Requests | 2023 | 3800 |  |  | NPRR1165 | PPL | 2023-10-12 | Revisions to Requirements of Providing Audited Financial Statements and Providing Independent Amount | Execution | $50k - $100k | 5 - 8 months | In Flight | CMM | 100% | 0%
Markets |  | Securitization | 2021 | 320 |  |  | NPRR1103 | PPL | 2021-12-16 | Securitization – PURA Subchapter M Default Charges | Complete | $1.5M - $2M | 18 - 26 months | Complete | S&B | 74% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems
Markets |  | Securitization | 2022 | 320 |  |  | NPRR1114 | PPL | 2022-03-31 | Securitization – PURA Subchapter N Uplift Charges | Complete | $1.8M - $2.4M | 18 - 24 months | Complete | S&B | 62% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems
Grid |  | Revision Requests | 2022 | 2650 | 2 - High Priority | 1 - High | NPRR1096 | PPL | 2022-03-31 | Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin | Complete | $30k - $50k | 3 - 5 months | Previously flagged as "High Priority" | NDCRC | 65% | 0% | Energy Management Systems, Grid Decision Support Systems, Grid Modeling Systems
Markets |  | Revision Requests | 2019 | 2650 |  |  | NPRR863 | PPL | 2019-02-12 | Creation of ERCOT Contingency Reserve Service (ECRS) | Complete | $2.5M - $3.5M | 20 - 30 months | Complete | MMS | 81% | 60%
Markets |  | Revision Requests | 2019 | 2700 | 4 - Consider When Resources are Available | 1 - High | NPRR917 | PPL | 2019-08-01 | Nodal Pricing for Settlement Only Distribution Generators (SODGs) and Settlement Only Transmission Generators (SOTGs) | Complete | $300k-$400k | 9-12 months | Complete | S&B | 30% | 0% | S&B, Integration, MMS, DAIP, NMMS, CMM, REG, Data Access & Transparency, External Public, BI & Data Analytics
Grid |  | Revision Requests | 2020 | 3070 | 3 - Needed prior to RTC | 1 - High | NPRR1016 | PPL | 2020-08-01 | Clarify Requirements for Distribution Generation Resources (DGRs) and Distribution Energy Storage Resources (DESRs) | Complete | $400k-$550k | 12-18 months | Complete | OS | 41% | 16% | OS, EMS, BI & Data Analytics, DAIP, MMS, REG, NMMS, Integration
Grid |  | Revision Requests | 2020 | 3070 |  |  | PGRR082 | PPL | 2020-12-08 | Revise Planning Guide Section 5 and Establish Small Generation Interconnection Process | Complete | $700k-$900k | 18-24 months | Complete | RIOO | 92% | 0% | RIOO-RS, NMMS, DAIP
Grid |  | Revision Requests | 2021 | 3195 |  |  | NPRR1093 | PPL | 2021-10-28 | Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 9 - 12 months | Complete | MMS | 68% | 29% | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems
Grid |  | Revision Requests | 2022 | 3195 |  |  | NPRR1101 | PPL | 2021-12-16 | Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non-Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve | Complete | $30k - $50k | 3 - 5 months | Complete | BI & Data Analytics | 60% | 0% | Data Management & Analytic Systems, Market Operation Systems
Grid |  | Revision Requests | 2023 | 3810 |  |  | NPRR1164 | PPL | 2023-10-12 | Black Start and Isochronous Control Capable Identification | Complete | $75k - $150k | 6 - 9 months | Complete | NMMS | 46% | 0%
Other |  | Revision Requests | N/A | N/A |  |  | SCR824 | PPL | 2023-11-30 | Increase File Size and Quantity Limits for RIOO Attachments | Complete | <$10k | N/A | Complete | RIOO | 100% | 0%

## ProjectCenter
Project Category | Target Start Year (Priority) | Rank | Revision Request | Project Name | Project Status | Impact Analysis Estimated Cost | Impact Analysis Estimated Time | Impacted Systems
Base Operations | 2019 | 230 | PGRR070 | PGRR070 Revised Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability Assessments | Complete | $100k - $150k | 12 - 18 months | Data Management & Analytic Systems
Base Operations | 2021 | 2705 | NPRR1051 | NPRR1051 Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k - $20k | 3 - 5 months | Market Operation Systems
Base Operations | 2021 | 3320 | LPGRR068 | LPGRR068 Add BUSLRG and BUSLRGDG Profile Types | Complete | $20k - $40k | 3 - 6 months | Data Management & Analytic Systems
Base Operations | 2021 | 3350 | SCR814 | SCR814 Point-to-Point (PTP) Obligation Bid Interval Limit | Execution | $10k - $25k | 3 - 5 months | Market Operation Systems
Base Operations | 2022 | 3630 | NPRR1112 | 434-01 NPRR1112 Elimination of Unsecured Credit Limits | Canceled | $10k - $20k | 3 - 5 months | Credit Management Systems (CMM)
Base Operations | 2023 | 3710 | SCR818a | SCR818 Phase 1 Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Canceled | $300k - $500k | 9 - 12 months | Grid Modeling Systems
Enterprise Improvements | 2019 | 2760 | NPRR484, NPRR867, NPRR887, NPRR907, NPRR985 | 183-02 CMM Phase 2 | On Hold | $1.5M - $2.5M | 18 - 28 months | Congestion Revenue Rights (CRR), Credit Management Systems (CMM), Credit Settlements & Billing Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Regulatory | 2019 | 220 | NPRR885 | 324-01 NPRR885 Must-Run Alternative (MRA) Details and Revisions Resulting from PUCT Project No_ 46369, Rulemaking Relating to Reliability Must-Run Service | On Hold | $500k - $700k | 8 - 12 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems
Regulatory | 2022 | 235 | NPRR863, NPRR1085, NPRR1096, NPRR1148 | 386-01 Creation of ERCOT Contingency Reserve Service (ECRS) | Complete | $1M - $1.5M | 12 - 18 months | Credit Management Systems (CMM), CRM & Registration Systems, Data and Information Products, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Network Management Systems
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-00 RTC-B Program Control | Planning | $12M - $16M | 2.5 - 3.5 years | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-01 RTC-B Grid & Markets | Planning | $22M - $28M | 2.5 - 3.5 years | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-02 RTC-B Commercial Applications | Planning | $5M - $7M | 2.5 - 3.5 years | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-03 RTC-B Integration & Information | Planning | $4M - $6M | 2.5 - 3.5 years | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems
Regulatory | 2020 | 240 | NPRR974, NPRR978, NPRR1048, SCR806 | 345-01 NPRR974 NPRR978 NPRR1048 SCR806 - Alignmt w Amndmnt PUCT SubsRule 25_505_Schedule | Complete | $200k - $300k | 8 - 10 months | Data Management & Analytic Systems, Market Operation Systems
Regulatory | 2020 | 300 | NOGRR195 | 334-04 NOGRR195 Generator Voltage Control Tolerance Band | Complete | $30k - $50k | 4 - 6 months | Data Management & Analytic Systems, Energy Management Systems
Regulatory | 2022 | 310 | PGRR099 | PGRR099 Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | Not Started | $20k - $30k | 3 - 5 months | Resource Integration and Ongoing Operations
Regulatory | 2022 | 315 | NPRR1108 | 388-01 NPRR1108 ERCOT Shall Approve or Deny All Resource Outage Requests | Complete | $300k - $400k | 8 - 12 months | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems
Regulatory | 2022 | 325 | NPRR1097 | 400-01 NPRR1097 Create Resource Forced Outage Report | Complete | $20k - $40k | 3 - 5 months | Data Management & Analytic Systems, ERCOT Website and MIS Systems
Regulatory | 2022 | 330 | NPRR1120 | 394-01 NPRR1120 Create Firm Fuel Supply Service | Complete | $250k - $400k | 9 - 12 months | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Regulatory | 2023 | 340 | NPRR1132 | NPRR1132 Communicate Operating Limitations during Cold and Hot Weather Conditions | Canceled | $65k - $95k | 4 - 6 months | Data Management & Analytic Systems, Grid Decision Support Systems, Resource Integration and Ongoing Operations
Regulatory | 2023 | 360 | NOGRR249 | 444-01 NERC FAC Standard Changes Alignment | Execution | $100k - $150k | 5 - 7 months | Channel Management Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Modeling Systems, Integration Systems
Revision Requests | 2017 | 1820 | SCR789 | 250-01 SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability - Phase 1 Only | Complete | $150k - $250k | 8 - 12 months | Grid Modeling Systems
Revision Requests | 2017 | 1820 | SCR789 | 391-01 SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2 | Complete | $550k - $750k | 12 - 18 months | Grid Modeling Systems
Revision Requests | 2030 | 2020 | NPRR918 | NPRR918 Validation for PTP Obligations with Links to an Option | Not Started | $30k - $50k | 4 - 6 months | Data Management & Analytic Systems, Market Operation Systems
Revision Requests | 2018 | 2090 | NPRR825 | NPRR825 Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k - $300k | 8 - 12 months | Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Revision Requests | 2019 | 2510 | NPRR829 | 351-01 NPRR829 Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k - $300k | 5 - 10 months | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Integration Systems
Revision Requests | 2020 | 2515 | NPRR1030 | NPRR1030 Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k - $225 | 8 - 12 months | Credit Settlements & Billing Systems
Revision Requests | 2019 | 2520 | NPRR841 | NPRR841 Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Not Started | $60k - $80k | 4 - 6 months | Credit Settlements & Billing Systems
Revision Requests | 2022 | 2530 | NPRR1098 | NPRR1098 DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | Grid Decision Support Systems
Revision Requests | 2024 | 2530 | NPRR857 | NPRR857 Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k - $700k | 12 - 18 months | CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Outage Management Systems, Telecom Management Systems
Revision Requests | 2023 | 2580 | PGRR066 | PGRR066 Interconnection Request Cancellation and Creation of Inactive Status | Not Started | $100k - $150k | 4 - 6 months | Grid Modeling Systems, Resource Integration and Ongoing Operations
Revision Requests | 2020 | 2630 | NPRR905 | 339-01 NPRR905 CRR Balancing Account Resettlement | Complete | $60k - $80k | 4 - 6 months | Credit Settlements & Billing Systems
Revision Requests | 2019 | 2650 | NPRR863, NPRR1015, NPRR1079, NOGRR187 | 325-01 NPRR863 FFR Advancement | Complete | $1.5M - $2.5M | 16 - 24 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems, Outage Management Systems
Revision Requests | 2019 | 2710 | SCR799 | SCR799 ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | $150k - $250k | 5 - 7 months | Data Management & Analytic Systems, Outage Management Systems
Revision Requests | 2019 | 2720 | NPRR904, OBDRR009, NPRR1006 | 347-01 NPRR904 Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $370k - $530k | 7 - 10 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2020 | 2765 | NPRR986, NPRR971, NPRR1043 | 338-01 Implementation of NPRR986 BESTF-2 and NPRR971 | Complete | $260k - $390k | 9 - 12 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems
Revision Requests | 2019 | 2770 | NPRR939 | 358-01 NPRR939 Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k - $100k | 5 - 7 months | Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Revision Requests | 2020 | 2800 | NPRR879 | NPRR879 SCED Base Point Base Point Deviation and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k - $250k | 6 - 9 months | Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Integration Systems
Revision Requests | 2020 | 2850 | NPRR936 | NPRR936 CRR Account Holder Limits | Not Started | $150k - $250k | 8 - 10 months | Congestion Revenue Rights (CRR), Data Management & Analytic Systems, Market Operation Systems
Revision Requests | 2022 | 2855 | SCR807, SCR816 | 414-01 SCR807 and SCR816 implementation | Execution | $100k - $180k | 5 - 7 months | Congestion Revenue Rights (CRR), Integration Systems
Revision Requests | 2020 | 2860 | NPRR941 | NPRR941 Create a Lower Rio Grande Valley Hub | Not Started | $250k - $350k | 6 - 8 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2023 | 2870 | NPRR962 | 437-01 NPRR962 Publish Approved DC Tie Schedules | Canceled | $15k - $30k | 3 - 4 months | Data Management & Analytic Systems
Revision Requests | 2020 | 2880 | SCR804 | 209-06 SCR804 ERCOT GridGeo Access for Transmission Operators | Complete | $400k - $600k | 6 - 12 months | Grid Decision Support Systems
Revision Requests | 2020 | 2890 | NPRR930 | 348-01 NPRR930 Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k - $200k | 5 - 7 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Market Operation Systems, Outage Management Systems
Revision Requests | 2020 | 2900 | NPRR965 | NPRR965 GREDP Shutdown Exemption | Not Started | $10k - $20k | 3 - 5 months | Data Management & Analytic Systems
Revision Requests | 2020 | 2910 | SCR800, SCR809 | 382-01 SCR800 and SCR809 Implementation | Complete | $70k - $110k | 6 - 9 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2020 | 2920 | SCR805 | SCR805 Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k - $60k | 4 - 6 months | Data Management & Analytic Systems
Revision Requests | 2020 | 2930 | NPRR902 | 337-01 NPRR902 ERCOT Critical Energy Infrastructure Information | Complete | $150k - $225k | 6 - 9 months | Corporate Systems, Data Management & Analytic Systems
Revision Requests | 2020 | 2970 | NPRR826 | NPRR826 Mitigated Offer Caps for RMR Resources | Not Started | $100k - $200k | 6 - 8 months | Market Operation Systems
Revision Requests | 2020 | 2990 | NPRR998 | 334-03 NPRR998 ERS Deployment and Recall Messages | Complete | $15k - $25k | 3 - 5 months | Integration Systems
Revision Requests | 2022 | 3000 | NPRR975 | NPRR975 Load Forecast Model Transparency | Not Started | $75k - $100k | 6 - 9 months | Data and Information Products, Data Management & Analytic Systems, Energy Management Systems
Revision Requests | 2022 | 3005 | NPRR1092 | 440-01 NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Execution | $50k - $100k | 4 - 6 months | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems
Revision Requests | 2020 | 3010 | NPRR963, NPRR987, NPRR989, NPRR1038, NOGRR204, NOGRR208, OBDRR017, PGRR081 | 353-01 Battery Energy Storage Combo Model Implementation Strategy | On Hold | $600k - $860k | N/A | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Integration Systems, Market Operation Systems, Resource Integration and Ongoing Operations
Revision Requests | 2023 | 3010 | NPRR1026 | 454-01 NPRR1026 BESTF-7 Self-Limiting Facilities | Execution | $100k-$200k | 5 - 8 months | Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Resource Integration and Ongoing Operations
Revision Requests | 2020 | 3015 | NPRR1014 | NPRR1014 BESTF-4 Energy Storage Resource Single Model | Canceled | $3.5M - $4.5M | 2 - 3 years | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Integration Systems, Market Operation Systems, Network Management Systems, Outage Management Systems, Resource Integration and Ongoing Operations
Revision Requests | 2020 | 3015 | NPRR1029 | NPRR1029 BESTF-6 DC-Coupled Resources | Not Started | $800k - $1.2M | 16 - 24 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Outage Management Systems, Resource Integration and Ongoing Operations
Revision Requests | 2022 | 3020 | NPRR1105 | NPRR1105 Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2020 | 3030 | NPRR1019 | 349-01 NPRR1019 Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k - $140k | 5 - 7 months | Data Management & Analytic Systems, Market Operation Systems
Revision Requests | 2020 | 3040 | SCR809 | 359-01 SCR809 Changes to External Telemetry Validations in Resource Limit Calculator | Canceled | $40k - $60k | 4 - 6 months | Data Management & Analytic Systems, Energy Management Systems
Revision Requests | 2023 | 3050 | NPRR1002,NPRR1132,NPRR1153 | 456-01 RIOO-IS_RS ESR-Single Model & Validation Rules Update | Planning | $400k - $700k | 9 - 12 months | Grid Modeling Systems
Revision Requests | 2020 | 3050 | SCR810 | SCR810 EMS System Change to Count DC Ties towards the 2 Percent Constraint Activation Criterion | Not Started | $15k - $25k | 3 - 5 months | Energy Management Systems
Revision Requests | 2022 | 3060 | NPRR1002, RRGRR023 | Single Model Registration for ESRs | Canceled | $100k - $200k | 7 - 10 months | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Revision Requests | 2020 | 3070 | NPRR917, NPRR1016, NPRR1052, NPRR1065, NOGRR212, PGRR082, RRGRR026 | 354-01 DGR DESR Implementation Strategy | Complete | $1.1M - $1.45M | N/A | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2020 | 3080 | SCR811 | 360-01 Integrate Solar Forecasts and SCR811 Implementation | Complete | $120k - $180k | 5 - 7 months | Data Management & Analytic Systems, Energy Management Systems, Forecasting Systems, Market Operation Systems
Revision Requests | 2021 | 3125 | NPRR1093, NPRR1101 | 384-01 NPRR1093 Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 10 - 14 months | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems
Revision Requests | 2022 | 3195 | NPRR1091 | NPRR1091 Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2023 | 3200 | PGRR076 | PGRR076 Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Not Started | $50k - $75k | 6 - 9 months | Data Management & Analytic Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations
Revision Requests | 2021 | 3210 | NPRR1004 | NPRR1004 Load Distribution Factor Process Update | Not Started | $45k - $65k | 5 - 7 months | Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Revision Requests | 2022 | 3220 | NPRR1020a | 393-01 NPRR1020 - EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | Complete | $175k - $225k | 8 - 12 months | Credit Settlements & Billing Systems
Revision Requests | 2021 | 3220 | NPRR1020b | NPRR1020 - Data Agg - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | Not Started | $175k - $225k | 8 - 12 months | Credit Settlements & Billing Systems
Revision Requests | 2021 | 3230 | NPRR1035 | NPRR1035 DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k - $40k | 3 - 5 months | Data Management & Analytic Systems
Revision Requests | 2021 | 3250 | SCR812 | 410-01 SCR812 Create Intermittent Renewable Generation Integration Report | Complete | $30k - $60k | 5 - 7 months | Data Management & Analytic Systems
Revision Requests | 2021 | 3260 | NPRR1032 | NPRR1032 Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k - $150k | 5 - 8 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Revision Requests | 2023 | 3270 | NPRR945 | 436-01 NPRR945 Net Metering Requirements | Not Started | $10k - $20k | 3 - 4 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Model Administration, Resource Integration and Ongoing Operations
Revision Requests | 2021 | 3280 | NPRR1034 | NPRR1034 Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k - $70k | 5 - 7 months | Content Delivery Systems, Data Management & Analytic Systems, Market Operation Systems
Revision Requests | 2021 | 3290 | NPRR1040 | 411-01 NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility | Execution | $20k - $30k | 3 - 5 months | Data Management & Analytic Systems
Revision Requests | 2021 | 3300 | NPRR1054 | NPRR1054 Removal of Oklaunion Exemption Language | Not Started | $10k - $15k | 3 - 4 months | Credit Settlements & Billing Systems, Integration Systems
Revision Requests | 2024 | 3310 | NPRR1057 | NPRR1057 Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months | Market Operation Systems
Revision Requests | 2021 | 3330 | NPRR1063 | NPRR1063 Dynamic Rating Transparency | Complete | $15k - $25k | 3 - 4 months | ERCOT Website and MIS Systems
Revision Requests | 2021 | 3340 | NPRR1081 | 377-01 NPRR1081 Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Revision Requests | 2021 | 3360 | NPRR1090 | 433-01 NPRR1090 ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Canceled | $15k - $25k | 3 - 5 months | Data Management & Analytic Systems, Market Operation Systems
Revision Requests | 2022 | 3500 | NPRR1023 | 460-01 NPRR1023 Change to CRR Repossession Process | Initiation | $250k - $350k | 10 - 14 months | Congestion Revenue Rights (CRR)
Revision Requests | 2022 | 3510 | PGRR088 | PGRR088 Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Not Started | $20k- $40k | 3 - 5 months | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Revision Requests | 2023 | 3510 | SCR813a | SCR813 NMMS Jointly-Rated Equipment Coordination Confirmation | Canceled | $100k - $150k | 5 - 7 months | Network Management Systems
Revision Requests | 2022 | 3520 | RRGRR028 | RRGRR028 Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Revision Requests | 2022 | 3530 | PGRR091 | PGRR091 FIS Application Completion 60-Day Limit | Not Started | $15k - $30k | 3 - 5 months | Resource Integration and Ongoing Operations
Revision Requests | 2022 | 3540 | PGRR094 | PGRR094 Clarify Notification Requirement for Generator Construction Commencement or Completion | Not Started | $10k - $20k | 1 - 2 months | Resource Integration and Ongoing Operations
Revision Requests | 2022 | 3550 | NPRR1077 | NPRR1077 Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months | Energy Management Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations
Revision Requests | 2024 | 3570 | SCR819, NPRR1111 | 415-01 SCR819 Improving IRR Control to Manage GTC Stability Limits | Planning | $40k - $60k | 4 - 6 months | Energy Management Systems, Market Operation Systems
Revision Requests | 2023 | 3590 | NPRR1121 | 435-01 NPRR1121 Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Canceled | $25k - $45k | 3 - 5 months | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems
Revision Requests | 2023 | 3595 | NPRR1186 | 453-01 Implement consideration of ESR SOC in ERCOT tools and studies | Execution | $500k - $700k | 7 - 10months | Energy Management Systems
Revision Requests | 2024 | 3600 | RMGRR168 | RMGRR168 Modify ERCOT Responsibilities During the Mass Transition | Not Started | $50k - $75k | 5 - 8 months | CRM & Registration Systems
Revision Requests | 2022 | 3610 | NPRR1135 | NPRR1135 Add On-Line Status Check for Resources Telemetering OFFNS for Ancillary Service Imbalance Settlements | Complete | $15k - $25k | 3 - 4 months | Energy Management Systems
Revision Requests | 2023 | 3620 | SCR822 | 449-01 SCR822 Create Daily Energy Storage Integration Report and Dashboard | Execution | $60k - $90k | 4 - 6 months | Channel Management Systems, Content Delivery Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems
Revision Requests | 2023 | 3700 | NPRR1095, SCR817 | 409-01 TX SET 5_0 and SCR817 | Execution | $1.4M - $2.1M | 16 - 20 months | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems
Revision Requests | 2023 | 3710 | SCR818b | SCR818 Phase 2 Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started |  |  | Grid Modeling Systems
Revision Requests | 2023 | 3715 | NPRR1058 | NPRR1058 Resource Offer Modernization | Not Started | $100K - $150K | 6 - 8 months | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Market Operation Systems
Revision Requests | 2023 | 3720 | NPRR1131 | NPRR1131 Controllable Load Resource Participation in Non-Spin | Not Started | $100k - $150k | 6 - 9 months | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems
Revision Requests | 2023 | 3720 | NPRR1136 | NPRR1136 Updates to Language Regarding a QSE Moving Ancillary Service Responsibility Between Resources | Canceled | $15k - $25k | 3 - 5 months | Market Operation Systems
Revision Requests | 2023 | 3730 | SCR820 | 430-01 SCR820 Operator Real-Time Messaging During Emergency | Planning | $750k - $1.25M | 18 - 24 months | Channel Management Systems, ERCOT Website and MIS Systems, Grid Operations Support Systems
Revision Requests | 2023 | 3740 | NPRR1139 | NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs | Not Started | $15k - $30k | 3 - 5 months | Credit Settlements & Billing Systems
Revision Requests | 2023 | 3750 | NPRR1140 | NPRR1140 Recovering Fuel Costs for Generation Above LSL During RUC-Committed Hours | Not Started | $20k - $30k | 3 - 4 months | Credit Settlements & Billing Systems
Revision Requests | 2024 | 3760 | NPRR1128 | NPRR1128 Allow FFR Procurement up to FFR Limit Without Proration | Not Started | $30k - $50k | 3 - 5 months
Revision Requests | 2023 | 3770 | NPRR1154 | 431-01 NPRR1154 Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | Execution | $40k - $70k | 5 - 7 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems
Revision Requests | 2023 | 3780 | NPRR1149, NPRR1121, NPRR1090, NPRR962 | 451-01 NPRR1149, NPRR1121, NPRR1090, NPRR962 | Execution | $120k - $160k | 6 - 8 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Market Operation Systems
Revision Requests | 2023 | 3790 | NPRR1153 | NPRR1153 ERCOT Fee Schedule Changes | Canceled | $20k - $30k | 3 - 5 months | Channel Management Systems, ERCOT Website and MIS Systems, Resource Integration and Ongoing Operations
Revision Requests | 2024 | 3900 | NOGRR226 | NOGRR226 Addition of Supplemental UFLS Stages | Not Started | $40k - $60k | 3 - 5 months
Revision Requests | 2024 | 4000 | SCR821 | SCR821 Voltage Set Point Target Information for DGR or DESR | Not Started | $25k - $50k | 3 - 5 months | Energy Management Systems
Revision Requests | 2024 | 4010 | NPRR1145 | NPRR1145 Use of EMS Calculated ERCOT-Wide TLFs in Lieu of Seasonal Base Case ERCOT-Wide TLFs for Settlement | Not Started | $50k - $80k | 3 - 6 months | Channel Management Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems
Revision Requests | 2025 | 4500 | NPRR995 | NPRR995 RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k - $1.2M | 20 - 30 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations
Securitization | 2021 | 330 | NPRR1103, NPRR1114 | 379-01 Securitization - Subchapter N | Complete | $700k - $1M | 9 - 12 months | Channel Management Systems, Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems
Securitization | 2022 | 340 | NPRR1103, NPRR1114 | 421-01 Securitization Phase 2A- Maine Invoice and Credit Exposure | Complete | $300k - $500k | 8 - 12 months | Channel Management Systems, Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems
Technical Health | 2021 | 1440 | SCR815 | 376-01 MarkeTrak Upgrade & Enhancements | Complete | $350k - $550k | 15 - 20 months | Database Management Systems, ERCOT Website and MIS Systems, Infrastructure Systems, Integration Systems, Retail Systems
Technical Health | 2022 | 3000 | SCR813b | 450-01 NMMS IMM Schema upgrade to CIM 16 | Planning | $1.0M - $1.5M | 18 - 24 months | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Modeling Systems

## Prev List - Complete or Active (hidden)
REVISION REQUEST PRIORITIZATION - Previous List - Projects Complete or In-Flight | [14 empty] | Count = 10
Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2020 | 300 | 1 - Regulatory | 1 - High | NOGRR195 | PPL | 2020-08-01 | Generator Voltage Control Tolerance Band | Complete | $30k-$50k | 4-6 months | EMS | 67% | 0% | EMS, BI & Data Analytics | Implemented 2021-R1
Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 1 | Complete | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS | Single IA - split into multiple projects Phase 1 implemented in July 2021
Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 2 | Planning | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS | Single IA - split into multiple projects Phase 2 target implementation in late 2022
Revision Requests | 2019 | 2700 | 4 - Consider When Resources are Available | 1 - High | NPRR917 | PPL | 2019-08-01 | Nodal Pricing for Settlement Only Distribution Generators (SODGs) and Settlement Only Transmission Generators (SOTGs) | Complete | $300k-$400k | 9-12 months | S&B | 30% | 0% | S&B, Integration, MMS, DAIP, NMMS, CMM, REG, Data Access & Transparency, External Public, BI & Data Analytics | DGR/DESR Implementation - 2022-R1
Revision Requests | 2019 | 2770 | 2 - High Priority | 1 - High | NPRR939 | PPL | 2019-10-01 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k-$100k | 5-7 months | MMS | 70% | 0% | MMS, DAIP, Integration | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 2910 | 5 - Consider When Efficiencies Exist With Another Effort | 1 - High | SCR800 | PPL | 2019-12-01 | Addition of DC Tie Ramp to GTBD Calculation | Complete | $30k-$50k | 3-5 months | EMS | 38% | 0% | EMS, Data Management, MMS, BI & Data Analytics | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 2980 | 2 - High Priority | 1 - High | NPRR974 | PPL | 2020-02-01 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | Complete | $50k-$80k | 5-7 months | DAIP | 62% | 0% | DAIP, MMS, External Public | Implemented 2021-R3 | Can NPRR975 be worked alongside NPRR974?
Revision Requests | 2020 | 3040 | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | SCR809 | PPL | 2020-06-01 | Changes to External Telemetry Validations in Resource Limit Calculator | Complete | $40k-$60k | 4-6 months | EMS | 83% | 0% | EMS, BI & Data Analytics | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 3070 | 3 - Needed prior to RTC | 1 - High | NPRR1016 | PPL | 2020-08-01 | Clarify Requirements for Distribution Generation Resources (DGRs) and Distribution Energy Storage Resources (DESRs) | Complete | $400k-$550k | 12-18 months | OS | 41% | 16% | OS, EMS, BI & Data Analytics, DAIP, MMS, REG, NMMS, Integration | DGR/DESR Implementation - 2022-R1
Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - EPS Metering | Execution | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | EPS Meter | Single IA - split into multiple projects Specific resources were available for this portion of NPRR1020

## Prev List - Not Started (hidden)
REVISION REQUEST PRIORITIZATION - Previous List - Projects Not Started | [15 empty] | Count = 29
Category | Priority | Rank | Prioritization Category | Revised Prioritization Recommendation | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Contact (Remove before sending to PRS) | ERCOT Recommendation | ERCOT Comments / Additional Detail | PRS Comments
Revision Requests | 2018 | 2090 | 6 - Dependent on Other Project | 5 - Dependent on Other Project | 2 - Medium | NPRR825 | PPL | 2017-12-01 | Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k-$300k | 8-12 months | MMS | 82% | 0% | MMS, Data Access & Transparency, DAIP, Integration | Maggio | 9 - TBD | Dependent on internal ERCOT project with no clear timeline Partial delivery in Oct. 2018
Revision Requests | 2019 | 2510 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR829 | PPL | 2017-10-01 | Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k-$300k | 5-10 months | CMM | 26% | 0% | CMM, NMMS, EMS, REG, Integration, DAIP, Data Access & Transparency | Ruane | 9 - TBD | We would like to get this On Hold effort going again in 2022 but we need to figure out resource constraints with Securitization and the Treasury Management project first
Revision Requests | 2020 | 2515 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR1030 | PPL | 2020-08-01 | Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k-$225k | 8-12 months | S&B | 74% | 0% | S&B, DAIP, CMM, Integration | Ruane | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Lower priority then Securitization Manual workaround in place to monitor market activity
Revision Requests | 2019 | 2520 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR841 | PPL | 2018-02-01 | Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Not Started | $60k-$80k | 4-6 months | S&B | 88% | 0% | S&B, Integration, Data Access & Transparency, CRM & Registration System | Ruane | 6 - Candidate for deletion |  | Consider filing an NPRR to strike the grey-boxes for NPRR841 (or let RTC NPRRs strike it)
Revision Requests | 2019 | 2530 | 6 - Dependent on Other Project | 5 - Dependent on Other Project | 2 - Medium | NPRR857 | PPL | 2018-10-01 | Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k-$700k | 12-18 months | OS | 53% | 25% | OS, EMS, OTS, WAN, NMMS, External Public, Integration, BI & Data Analytics, REG, Data Access & Transparency, DAIP | Various | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2019 | 2580 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | PGRR066 | PPL | 2018-12-01 | Interconnection Request Cancellation and Creation of Inactive Status | Not Started | $100k-$150k | 4-6 months | RIOO | 100% | 0% | Resource Integration | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete ERCOT can keep the existing manual workaround until resources are available
Revision Requests | 2019 | 2710 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | SCR799 | PPL | 2019-06-01 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | $150k-$250k | 5-7 months | SOTE | 100% | 0% | SOTE | Huang | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Material impact on EMS Production Support team Low probability of fitting this into the plan in advance of the EMS Upgrade system freeze
Revision Requests | 2019 | 2720 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR904 | PPL | 2019-08-01 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $200k-$300k | 6-9 months | MMS | 85% | 41% | MMS, EMS, BI & Data Analytics, DAIP | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2019 | 2720 | 2 - High Priority | 2 - High Priority | 1 - High | OBDRR009 | PPL | 2019-08-01 | ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | On Hold | $30k-$50k | 4-6 months | MMS | 40% | 0% | MMS, DAIP, BI & Data Analytics | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2020 | 2800 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR879 | PPL | 2018-12-01 | SCED Base Point, Base Point Deviation, and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k-$250k | 6-9 months | DAIP | 46% | 0% | DAIP, S&B, BI & Data Analytics, EMS, NMMS, Integration | Billo | 3 - 2023 project candidate | Moved to 2023 - this cleared resources for higher priority reporting efforts such as NPRR1097, NPRR1040, and SCR812
Revision Requests | 2020 | 2815 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR963 | PPL | 2020-02-01 | Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model) | On Hold | $150k-$200k | 8-12 months | DAIP | 31% | 0% | DAIP, S&B, EMS, BI & Data Analytics, Integration | Sharma | 3 - 2023 project candidate | Battery Energy Storage (BES) PR353-01 component This work that can't be fit into the plan until after ECRS implementation
Revision Requests | 2020 | 2840 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR918 | PPL | 2019-10-01 | Validation for PTP Obligations with Links to an Option | Not Started | $30k-$50k | 4-6 months | MMS | 57% | 0% | MMS, DAIP, Integration | Sharma | 3 - 2023 project candidate | This NPRR introduces hourly submission validation versus current peak load value based validation.
Revision Requests | 2020 | 2850 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR936 | PPL | 2019-10-01 | CRR Account Holder Limits | Not Started | $150k-$250k | 8-10 months | CRR | 90% | 51% | CRR, DAIP | Sharma | 3 - 2023 project candidate | CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2020 | 2855 | 4 - Consider When Resources are Available | 2 - High Priority | 1 - High | SCR807 | PPL | 2020-06-01 | Increase CRR Transaction Capability | Not Started | $50k-$100k | 5-7 months | CRR | 95% | 60% | CRR, Integration | Sharma | 1 - Planned for 2022 start | Q3 2022 start CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2020 | 2860 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR941 | PPL | 2019-12-01 | Create a Lower Rio Grande Valley Hub | Not Started | $250k-$350k | 6-8 months | MMS | 91% | 75% | MMS, DAIP, EMS, External Public | Maggio | 7 - Market input requested | Consistent with the August 2020 discussion, this is lower priority and can be reconsidered when critical efforts are complete
Revision Requests | 2020 | 2870 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR962 | PPL | 2019-10-01 | Publish Approved DC Tie Schedules | Not Started | $15k-$30k | 3-4 months | DAIP | 86% | 0% | DAIP, BI & Data Analytics | Maggio | 7 - Market input requested | Impact is relatively low and limited to reporting. Data seems useful but the usefulness is dependent on the market participants' points of view.
Revision Requests | 2020 | 2890 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR930 | PPL | 2019-10-01 | Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k-$200k | 5-7 months | MMS | 74% | 39% | MMS, OS, DAIP, Data Access & Transparency, External Public | Maggio | 7 - Market input requested | Partially implemented. Remaining component has a work-around that's a behavior rule for QSEs.
Revision Requests | 2020 | 2900 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | NPRR965 | PPL | 2019-12-01 | GREDP Shutdown Exemption | Not Started | $10k-$20k | 3-5 months | BI & Data Analytics | 100% | 0% | BI & Data Analytics | Billo | 9 - TBD | Consider bundling this with NPRR879 which also has a BI & Data Analytics portion that impacts GREDP.
Revision Requests | 2020 | 2920 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | SCR805 | PPL | 2019-12-01 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k-$60k | 4-6 months | DAIP | 97% | 0% | DAIP, Data Access & Transparency | Billo | 7 - Market input requested
Revision Requests | 2020 | 2970 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR826 | PPL | 2020-02-01 | Mitigated Offer Caps for RMR Resources | Not Started | $100k-$200k | 6-8 months | MMS | 70% | 68% | MMS, DAIP, External Public, Data Access & Transparency | Maggio | 7 - Market input requested | Priority is less clear due to not currently having any RMR contracts in place.
Revision Requests | 2020 | 3000 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR975 | PPL | 2020-06-01 | Load Forecast Model Transparency | Not Started | $75k-$100k | 6-9 months | EMS | 58% | 0% | EMS, DAIP, BI & Data Analytics | Billo | 9 - TBD | ERCOT is evaluating options for replacing the A3 and A6 models.
Revision Requests | 2020 | 3010 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR987 | PPL | 2020-06-01 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | On Hold | $150k-$200k | 6-9 months | MMS | 34% | 9% | MMS, S&B, EMS, Integration, BI & Data Analytics, DAIP | Sharma | 3 - 2023 project candidate | Battery Energy Storage (BES) PR353-01 component "ESR Contribution to PRC" already in-flight targeting 2022-R5 This row represents the remaining work that can't be fit into the plan until after ECRS implementation
Revision Requests | 2020 | 3020 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR1006 | PPL | 2020-06-01 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | $140k-$180k | 6-9 months | MMS | 62% | 29% | MMS, DAIP, EMS, S&B, BI & Data Analytics | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2020 | 3030 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR1019 | PPL | 2020-06-01 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k-$140k | 5-7 months | MMS | 98% | 44% | MMS, BI & Data Analytics | Maggio | 7 - Market input requested | Partially implemented. Remaining component has a work-around that's a behavior rule for QSEs.
Revision Requests | 2020 | 3050 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | SCR810 | PPL | 2020-08-01 | EMS System Change to Count DC Ties towards the 2% Constraint Activation Criterion | Not Started | $15k-$25k | 3-5 months | EMS | 100% | 0% | EMS | Huang | 9 - TBD | This SCR adds logic to ERCOT’s EMS system to remove the flag that indicates to the ERCOT Operator that a unit representing a DC Tie does not count toward the 2% criterion for activating transmission constraints
Revision Requests | 2020 | 3060 | 3 - Needed prior to RTC | 3 - Consider When Resources are Available | 1 - High | NPRR1002 | PPL | 2020-08-01 | BESTF-5 Energy Storage Resource Single Model Registration and Charging Restrictions in Emergency Conditions | On Hold | $100k-$200k | 7-10 months | RIOO | 83% | 0% | Resource Integration, Integration, DAIP | Blevins | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Battery Energy Storage (BES) PR353-01 component "Charging Restrictions in Emergency Conditions" already in-flight targeting 2022-R5 This row is a potential stand-alone project to run alongside RARF Replacement to leverage resources as they become free for development and testing by end of 2022
Revision Requests | 2021 | 3200 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | PGRR076 | PPL | 2020-08-01 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Not Started | $50k-$75k | 6-9 months | RIOO | 57% | 0% | Resource Integration, Integration, Data Access & Transparency | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2021 | 3210 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR1004 | PPL | 2020-08-01 | Load Distribution Factor Process Update | Not Started | $45k-$65k | 5-7 months | MMS | 41% | 0% | MMS, Integration, DAIP, External Public | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | IMM has asked about the status of this RR MMS impacts
Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - Data Agg | Not Started | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | S&B | Ruane | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Data Agg portion of NPRR1020 Same solution is available with current EPS meter configuration schemes EPS Metering portion is already in-flight

## New Items - Complete or Active (hidden)
REVISION REQUEST PRIORITIZATION - New Items - Projects Complete or In-Flight | [14 empty] | Count = 12
Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2022 | 310 | 1 - Regulatory |  | PGRR099 | PPL | 2022-03-31 | Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | Execution | $20k - $30k | 3 - 5 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations
Securitization | 2021 | 320 | 1 - Regulatory |  | NPRR1103 | PPL | 2021-12-16 | Securitization – PURA Subchapter M Default Charges | Execution | $1.5M - $2M | 18 - 26 months | S&B | 74% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | Manual solution implemented Automation project expected to start later in 2022
Securitization | 2022 | 320 | 1 - Regulatory |  | NPRR1114 | PPL | 2022-03-31 | Securitization – PURA Subchapter N Uplift Charges | Execution | $1.8M - $2.4M | 18 - 24 months | S&B | 62% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | Implemented late March 2022 Currently in Stabilization Included NPRR1122, NPRR1123, and NPRR1125
Regulatory | 2022 | 320 | 1 - Regulatory |  | NPRR1108 | PPL | 2022-04-28 | ERCOT Shall Approve or Deny All Resource Outage Requests | Execution | $275k-$375k | 7-10 months | OS | 58% | 27% | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems | Target implementation - 2022-R4
Regulatory | 2022 | 330 | 1 - Regulatory |  | NPRR1120 | PPL | 2022-03-31 | Create Firm Fuel Supply Service | Planning | $250k-$400k | 9-12 months | S&B | 70% | 0% | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems | Expected implementation in Q4 2022
Revision Requests | 2021 | 2705 |  |  | NPRR1051 | PPL | 2021-02-09 | Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k-$20k | 3-5 months | MMS | 100% | 0% | Market Operation Systems | Implemented 2021-R3
Revision Requests | 2020 | 3010 |  |  | NPRR1026 | PPL | 2020-12-08 | BESTF-7 Self-Limiting Facilities | Execution | $200k-$250k | 7-10 months | RIOO | 58% | 0% | RIOO-RS, EMS, OTS, DAIP, External Public | RIOO portion is in progress
Revision Requests | 2020 | 3070 |  |  | PGRR082 | PPL | 2020-12-08 | Revise Planning Guide Section 5 and Establish Small Generation Interconnection Process | Complete | $700k-$900k | 18-24 months | RIOO | 92% | 0% | RIOO-RS, NMMS, DAIP | DGR/DESR Implementation - 2022-R1
Revision Requests | 2020 | 3080 |  |  | SCR811 | PPL | 2020-10-13 | Integrate Solar (PVGR) Forecasts and Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation | Complete | $60k-$90k | 5-7 months | MMS | 76% | 35% | MMS, EMS | Implemented 2021-R3
Revision Requests | 2021 | 3195 |  |  | NPRR1093 | PPL | 2021-10-28 | Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 9 - 12 months | MMS | 68% | 29% | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2021 | 3340 |  |  | NPRR1081 | PPL | 2021-06-28 | Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | MMS | 45% | 0% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Manual solution implemented on 7/1/2021 Automation completed in September 2021
Revision Requests | 2021 | 3350 |  |  | SCR814 | PPL | 2021-10-28 | Point-to-Point (PTP) Obligation Bid Interval Limit | Complete | $10k-$25k | 3 - 5 months | MMS | 100% | 0% | Market Operation Systems | Implemented 2022-R3 Currently in Stabilization

## New Items - Not Started (hidden)
REVISION REQUEST PRIORITIZATION - New Items - Projects Not Started | [14 empty] | Count = 34
Category | Priority | Rank | Prioritization Category Recommendation | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Contact (Remove before sending to PRS) | ERCOT Recommendation | ERCOT Comments / Additional Details | PRS Comments
Regulatory | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1007 | PPL | 2020-12-08 | Real-Time Co-Optimization (RTC) | On Hold | $50M-$55M | 3.5-4.5 years | MMS | 53% | 24% | MMS, EMS, Integration, DAIP, S&B, NMMS, CMM, OTS, Registration | Maggio | 9 - TBD | Pending further direction from PUCT Represents NPRRs 1007-1013, NOGRR211, and OBDRR020
Regulatory | 2022 | 325 | 1 - Regulatory | 1 - High | NPRR1097 | PPL | 2022-03-31 | Create Resource Forced Outage Report | Not Started | $20k-$40k | 3-5 months | DAIP | 90% | 0% | Data Management & Analytic Systems, ERCOT Website and MIS Systems | Huang | 1 - Planned for 2022 start | Q3 2022 start Need to implement by end of 2022 to meet PUCT target Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2022 | 2530 | 9 - No Action Needed | 2 - Medium | NPRR1098 | PPL | 2022-03-31 | DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | BI & Data Analytics | 100% | 0% | Grid Decision Support Systems | Various | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2022 | 2650 | 2 - High Priority | 1 - High | NPRR1096 | PPL | 2022-03-31 | Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin | Not Started | $30k - $50k | 3 - 5 months | NDCRC | 65% | 0% | Energy Management Systems, Grid Decision Support Systems, Grid Modeling Systems | Billo | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | ECRS portion - 2023 Non-Spin portion - 2022 candidate
Revision Requests | 2022 | 2855 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | SCR816 | PPL | 2022-03-31 | CRR Auction Bid Credit Enhancement | Not Started | $50k - $80k | 4 - 6 months | CRR | 100% | 52% | Congestion Revenue Rights (CRR) | Sharma | 1 - Planned for 2022 start | Q3 2022 start CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2022 | 3005 | 2 - High Priority | 1 - High | NPRR1092 | PPL | 2022-04-28 | Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Not Started | $50k - $100k | 4 - 6 months | MMS | 100% | 0% | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | "Reduce RUC Offer Floor" change implemented on 5/13/2022 This project implements the "Limit RUC Opt-Out Provision" portion
Revision Requests | 2020 | 3015 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1014 | PPL | 2020-12-08 | BESTF-4 Energy Storage Resource Single Model | Not Started | $3.5M-$4.5M | 2-3 years | EMS | 60% | 49% | EMS, MMS, DAIP, S&B, OS, Integration, NMMS, RIOO, Registration | Sharma | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | NPRR was written with RTC design. This work can't be fit in to the plan until after EMS upgrade.
Revision Requests | 2020 | 3015 | 9 - No Action Needed | 2 - Medium | NPRR1029 | PPL | 2020-12-08 | BESTF-6 DC-Coupled Resources | Not Started | $800k-$1.2M | 16-24 months | EMS | 33% | 36% | EMS, OS, S&B, MMS, RIOO, Integration, DAIP, OTS, NMMS, Registration | Sharma | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | NPRR was written with RTC design. This work can't be fit in to the plan until after EMS upgrade.
Revision Requests | 2022 | 3020 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1105 | PPL | 2021-12-16 | Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months | MMS | 55% | 27% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2022 | 3195 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1091 | PPL | 2021-12-16 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | MMS | 73% | 40% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2021 | 3230 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR1035 | PPL | 2020-10-13 | DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k-$40k | 3-5 months | DAIP | 83% | 0% | DAIP, External Public | Maggio | 7 - Market input requested | Impact is relatively low and limited to reporting. Data seems useful but the usefulness is dependent on the market participants' points of view.
Revision Requests | 2021 | 3250 | 3 - Consider When Resources are Available | 1 - High | SCR812 | PPL | 2020-12-08 | Create Intermittent Renewable Generation Integration Report | Not Started | $30k-$60k | 5-7 months | DAIP | 68% | 0% | DAIP, Reporting | Billo | 1 - Planned for 2022 start | Q3 2022 start Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2021 | 3260 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1032 | PPL | 2020-12-08 | Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k-$150k | 5-8 months | MMS | 64% | 32% | MMS, S&B, DAIP, Integration | Maggio | 3 - 2023 project candidate | Addresses a known operational issue/inefficiency
Revision Requests | 2021 | 3270 | 3 - Consider When Resources are Available | 2 - Medium | NPRR945 | PPL | 2020-12-08 | Net Metering Requirements | Not Started | $10k-$20k | 3-4 months | RIOO | 64% | 0% | RIOO-RS, External Public | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2021 | 3280 | 9 - No Action Needed | 2 - Medium | NPRR1034 | PPL | 2021-02-09 | Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k-$70k | 5-7 months | Pi | 64% | 0% | Pi, EIS, NoticeBuilder, MIS | Various | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2021 | 3290 | 3 - Consider When Resources are Available | 1 - High | NPRR1040 | PPL | 2021-02-09 | Compliance Metrics for Ancillary Service Supply Responsibility | Not Started | $20k-$30k | 3-5 months | BI & Data Analytics | 90% | 0% | Data Management & Analytic Systems | Billo | 1 - Planned for 2022 start | Q3 2022 start Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2021 | 3300 | 9 - No Action Needed | 3 - Low | NPRR1054 | PPL | 2021-02-09 | Removal of Oklaunion Exemption Language | Not Started | $10k-$15k | 3-4 months | S&B | 50% | 0% | Credit Settlements & Billing Systems, Integration Systems | Ruane | 8 - Work into other projects where possible | Not urgent Work this into other projects where possible
Revision Requests | 2021 | 3310 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1057 | PPL | 2021-04-13 | Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months | MMS | 100% | 0% | Market Operation Systems | Maggio | 3 - 2023 project candidate | Impact is relatively low and would like to address this issue, even though it's a low probability event
Revision Requests | 2021 | 3330 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1063 | PPL | 2021-08-19 | Dynamic Rating Transparency | Not Started | $15k - $25k | 3 - 4 months | MIS | 100% | 0% | ERCOT Website and MIS Systems | Blevins | 1 - Planned for 2022 start | Q4 2022 start Posting the proposed information will increase transparency of these changes and thereby improve Market Participants’ ability to assess and hedge risk
Revision Requests | 2021 | 3360 | 2 - High Priority | 1 - High | NPRR1090 | PPL | 2021-10-28 | ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Not Started | $15k - $25k | 3 - 5 months | MMS | 71% | 0% | Data Management & Analytic Systems, Market Operation Systems | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Impact is relatively low and would like to address this issue.
Revision Requests | 2022 | 3500 | 3 - Consider When Resources are Available | 1 - High | NPRR1023 | PPL | 2021-04-13 | Change to CRR Repossession Process | Not Started | $250k - $350k | 10 - 14 months | CRR | 100% | 65% | Congestion Revenue Rights (CRR) | Sharma | 3 - 2023 project candidate | CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | PGRR088 | PPL | 2021-06-08 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Not Started | $20k- $40k | 3 - 5 months | RIOO | 53% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Desired to start after completion of NMMS Tech Health project - Q1 2023
Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | SCR813 | PPL | 2021-10-28 | NMMS Jointly-Rated Equipment Coordination Confirmation | Not Started | $100k - $150k | 5 - 7 months | NMMS | 100% | 40% | Network Management Systems | Blevins | 3 - 2023 project candidate | Desired to start after completion of NMMS Tech Health project - Q1 2023
Revision Requests | 2022 | 3520 | 3 - Consider When Resources are Available | 2 - Medium | RRGRR028 | PPL | 2021-08-19 | Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months | RIOO | 93% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3530 | 3 - Consider When Resources are Available | 2 - Medium | PGRR091 | PPL | 2021-08-19 | FIS Application Completion 60-Day Limit | Not Started | $15k - $30k | 3 - 5 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3540 | 3 - Consider When Resources are Available | 2 - Medium | PGRR094 | PPL | 2021-10-28 | Clarify Notification Requirement for Generator Construction Commencement or Completion | Not Started | $10k - $20k | 1 - 2 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3550 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1077 | PPL | 2021-12-16 | Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months | RIOO | 46% | 0% | Energy Management Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3570 | 2 - High Priority | 2 - Medium | SCR819 | PPL | 2022-03-31 | Improving IRR Control to Manage GTC Stability Limits | Not Started | $40k - $60k | 4 - 6 months | EMS | 70% | 0% | Energy Management Systems, Market Operation Systems | Billo | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | This SCR will improve the dispatch of Base Points to Resources to account for the ramping of uncurtailed IRRs and will reduce the chance of violating Generic Transmission Limits (GTLs)
Revision Requests | 2022 | 3590 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1121 | Pending PUCT Approval |  | Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Not Started | $25k - $45k | 3 - 5 months | DAIP | 85% | 0% | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Impact is relatively low and limited to reporting. Would like to address this manual process.
Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | NPRR1095 | PPL | 2022-03-31 | Texas SET V5.0 Changes | Not Started | $1.0M - $1.5M | 16 - 20 months | Registration | 80% | 0% | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems | Ruane | 1 - Planned for 2022 start | Q3 2022 start Align with restart of MCT Requirement defining in 2022 Development underway in 2023 Testing and Go-live expected in first half of 2024
Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | SCR817 | PPL | 2022-03-31 | Related to NPRR1095 MarkeTrak Validation Revisions Aligning with Texas SET V5_0 | Not Started | $400k - $600k | 10 - 15 months | Retail | 65% | 0% | CRM & Registration Systems, Integration Systems, Retail Systems | Ruane | 1 - Planned for 2022 start | Q3 2022 start Align with restart of MCT Requirement defining in 2022 Development underway in 2023 Testing and Go-live expected in first half of 2024
Revision Requests | 2023 | 3710 | 3 - Consider When Resources are Available | 1 - High | SCR818 | PPL | 2022-04-28 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started | $300k - $500k | 9 - 12 months | NMMS | 100% | 64% | Grid Modeling Systems | Blevins | 1 - Planned for 2022 start | Q4 2022 start Desired to be split into two efforts: 1 - NMMS data collection (Q4 2022 start) 2 - MOD data collection and software enhancements (Q2 2023 start)
Revision Requests | 2023 | 3720 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1131 | Pending Board Approval |  | Controllable Load Resource Participation in Non-Spin | Not Started | $100k - $150k | 6 - 9 months | MMS | 40% | 0% | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems | Sharma | 3 - 2023 project candidate | Target 2023 start after ECRS implementation Revisit if there is an increase in the number of CLRs that are qualified to participate in Non-Spin
Revision Requests | 2025 | 4500 | 9 - No Action Needed | 2 - Medium | NPRR995 | PPL | 2021-08-19 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k-$1.2M | 20-30 months | RIOO | 44% | 4% | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations | Blevins | 9 - TBD | 2025 Priority