## Slide 1
Project Update
February 8, 2024
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2024 Release Targets
  Major Projects
  Additional Project Status Information
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1213 – Allow DGRs and DESRs on Circuits Subject to Load Shed to Provide ECRS
  Technology Working Group (TWG)
    Meeting planned for 2/15/2024
  Aging Revision Request Project Review
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2024 January Release – R1 – 1/25/2024 Complete
  NPRR1092(b) – Reduce RUC Offer Floor and Limit RUC Opt-Out Provision
    “Limit RUC Opt-Out Provision” portion
2024 February Off-Cycle Release – 2/1/2024 Complete
  Ancillary Service Responsibility Telemetry Changes for ESRs
2024 February Off-Cycle Release – 2/16/2024 In Flight
  Public API Enhancements
2024 February Release – R2 – 2/22/2024 In Flight
  NPRR1132(a) – Communicate Operating Limitations during Cold and Hot Weather Conditions
  RRGRR032 – Related to NPRR1132
  NOGRR249(b) – Communication of System Operating Limit Exceedances
2024 March Off-Cycle Release – 3/1/2024 In Flight
  NPRR1026(b) – Self-Limiting Facilities reporting
2024 March Release – R3 – 3/28/2024 In Flight
  NPRR1040 – Compliance Metrics for Ancillary Service Supply Responsibility
2024 April Off-Cycle Release – 4/1/2024 In Flight
  NPRR1165 – Revisions to Requirements of Providing Audited Financial Statements and Providing Independent Amount
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/25 | February 2/22 | March 3/28 | April 4/25 | May 5/30 | June 6/27
NPRR1092(b) PGRR098(a) Public API Enhancements ESR Telemetry | NPRR1132(a) RRGRR032 NOGRR249(b) Public API Enhancements | NPRR1040 NPRR1186 NPRR1026(b) | NPRR1165 | NPRR1149 NPRR1121 NPRR1090 NPRR962 NPRR1196 SCR819 NPRR1111 Forecast Presentation Platform | NPRR1002 RRGRR023 SCR819 NPRR1111 NPRR1186
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1026(b) – SLF – Reporting portion
NPRR1092(b) – Limit RUC Opt-Out Provision
NPRR1132(a) – Operating Limits in Cold and Hot Conditions – RIOO portion
NOGRR249(b) – MIS posting
PGRR098(a) – Section 4.1.1.8
E
E
E
E
E
E
E
E
ü
ü
ü
E
E
E
E
P
July 7/25 | August 8/22 | September 9/26 | October 10/24 | TX SET 5.0 11/10 | December 12/11-12/12
 | SCR813 |  |  | NPRR1095 SCR817 SCR823 RMGRR172 | NPRR1023
R7
R8
R9
R10
R11
E
E
E
E
E
E
2/1
3/1
P
P
P
E
1/1
2/16
4/1
E
Mid-June
To Mid-June
Various effective dates for these items

## Slide 5: Major Projects
Other Project Highlights

## Slide 6: Additional Project Status Information
RR | Description | Proj Phase | Additional Detail
NPRR1004 | Load Distribution Factor Process Update | Not Started | Analyzing an April 2024 start
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Analyzing an April 2024 start
NPRR1139 | Adjustments to Capacity Shortfall Ratio Share for IRRs | Not Started | Analyzing an April 2024 start
SCR799 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | Analyzing a July 2024 start
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Market input requested to determine if these are High Priority compared to other Not Started and On Hold items
NPRR1058 | Resource Offer Modernization | Not Started | 
NPRR1091 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | 
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | 
NPRR1171 | Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Not Started | 
SCR805 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | 
Red Text: New additions and updates

## Slide 7: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1213 | Allow DGRs and DESRs on Circuits Subject to Load Shed to Provide ECRS | 2024 | 4050 | $350k-$450k, 8-12 months Impacted System(s): MMS, Data Warehouse, EMS Most efficient if implemented with NPRR1171 Consider pairing with NPRR1171 by assigning same Priority/Rank
Recommendations for…
PPL Rank Information
Next available 2024 Rank in Business Strategy = 4100
Next available Rank in Regulatory = 380

## Slide 8: Technology Working Group (TWG)
Next TWG meeting to be held on 2/15/2024
Agenda is TBD

## Slide 9: Aging Revision Request Project Review
The “Aging Revision Request” list used in 2022 has been updated for recent activity and will be posted prior to the February PRS meeting
Preliminary ERCOT comments will be included on many line items
Primary discussion at February PRS will be the structure of the posted file and ERCOT’s initial comments
Follow-up discussion to be held at the March PRS:
  Identify High Priorities
  Items that may have a pathway to implementation in the next 6-12 months
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,989,995,1004,1006,1007,1019,1020(b),1029,1030,1032,1034,1038, 1057,1058,1077,1091,1098,1105,1128,1131 SCRs: 799,805,810,818 PGRRs: 066,076,088,091,094,099,103 Other: OBDRR009,OBDRR017,RRGRR028