## Slide 1
Resource Integration Topics
Jenifer Fernandes
ERCOT
Resource Integration Working Group
Feb 21, 2024

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic/PSCAD Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test and Unit Model Validation required
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM and should include MQT

## Slide 4: RIOO-IS and RARF
RARF forms will no longer be used starting in 2024. Some repower projects may need to use RARF forms.
New release on 2/22 for NPRR1132 (Communicate Operating Limitations during Cold and Hot Weather Conditions) and RIOO Multi Tech Release.

## Slide 5: GINR MISC
Number of Units consistent between studies, models & MQT and full registration.
  Restudies might be required if there are changes between studies and full registration model.

## Slide 6: Self-Limiting Facilities 1
Work will be completed in March 2024 for the report for the ERM and IMM in 3.8.7 (3)
  (3) On a monthly basis, ERCOT will report to the Reliability Monitor and IMM any instance where a Self-Limiting Facility’s actual MW Injections exceeded the MW Injection limit or where actual MW Withdrawals exceeded the MW Withdrawal limit established in the Resource Registration data for the Self-Limiting Facility, based on the telemetry of the injection and withdrawal values provided by the QSE for the registered generator or ESS in the Self-Limiting Facility, as described in Section 3.9.1, Current Operating Plan (COP) Criteria, and in Section 6.5.5.2, Operational Data Requirements, or based on the meter data at the Point of Interconnection (POI) or Point of Common Coupling (POCC) for the Self-Limiting Facility.
  If ERCOT determines that a Self-Limiting Facility connected at transmission voltage has exceeded either its MW Injection limit or its MW Withdrawal limit established in the Resource Registration data by more than the greater of 5 MW or 3% of the limit, the Self-Limiting Facility shall submit a new generation interconnection request based on the installed MW capacity of the individual Resource(s) and shall deregister as a Self-Limiting Facility at the completion of the generation interconnection process. The Self-Limiting Facility shall be subject to the established MW Injection limit and any established MW Withdrawal limit until the generation interconnection process has been completed.
NP 3.8.7 Self-Limiting Facility should be un-grey boxed March 1, 2024.

## Slide 7: Self-Limiting Facilities 2
TSP’s will receive an email whether response is Yes or No:
Subject: Substation CORVETTE_PV Self-Limiting Facility Details
Body: Substation SUBNAME has the following Self-Limiting Facility details
    This substation is scheduled:
    • For Production Load Date: 09/30/2028
    • Self-Limiting Facility: No or Yes
    • Injection Limit: 111 - only if Yes
    • Withdrawal Limit: 99 - only if Yes
    Sincerely,
    ERCOT Resource Services
This email is to satisfy 3.8.7 (1)
(1) A Resource Entity or Interconnecting Entity (IE) for a Self-Limiting Facility may establish a MW Injection or MW Withdrawal limit by submitting an attestation in a form designated by ERCOT through the Resource Registration process. The Resource Entity or IE shall simultaneously provide a copy of the attestation to the interconnecting Transmission and/or Distribution Service Provider (TDSP). All registered generators or Energy Storage Systems (ESSs) within a Self-Limiting Facility shall be represented by a single Resource Entity and a single QSE.

## Slide 8: Active RR’s
PGRR112 - Dynamic Data Model and Full Interconnection Study (FIS) Deadline for Quarterly Stability Assessment – in review at ROS.

## Slide 9: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 10: Questions?
Thank you!