## Wind Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2024-07-31 | 2002-10-23 | Wind | WT | 3 | 2024 | No
[6 empty] | 19INR0117 | Roadrunner Crossing Wind SLF | Eastland | 2024-08-22 | 2021-04-17 | Wind | WT | 128 | 2024 | Yes
[6 empty] | 21INR0515 | Roadrunner Crossing Wind II SLF | Eastland | 2024-08-23 | 2020-04-17 | Wind | WT | 126.72 | 2024 | Yes
[6 empty] | 20INR0040 | Montgomery Ranch Wind | Foard | 2024-09-01 | 2022-03-22 | Wind | WT | 200.2 | 2024 | Yes
[6 empty] | 24INR0632 | Cedro Hill Wind Repower | Webb | 2024-12-28 | 2009-09-09 | Wind | WT | 9.93 | 2024 | Yes
[6 empty] | 21INR0240 | La Casa Wind | Stephens | 2025-03-22 | 2023-09-07 | Wind | WT | 148.4 | 2025 | Yes
[6 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2025-03-31 | 2017-12-13 | Wind | WT | 197.01 | 2025 | No
[6 empty] | 20INR0217 | CAROL wind | Potter | 2025-04-17 | 2020-09-11 | Wind | WT | 165.42 | 2025 | Yes
[6 empty] | 22INR0517 | Ray Gulf Wind | Wharton | 2025-06-30 | 2022-05-13 | Wind | WT | 207 | 2025 | No
[6 empty] | 19INR0054 | Monte Cristo 1 Wind | Hidalgo | 2025-08-20 | 2023-05-09 | Wind | WT | 234.5 | 2025 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2024-03-20 | 38998.01 | 38998.01 | 0 | 0 | 0
2024-04-20 | 38998.01 | 38998.01 | 0 | 0 | 0
2024-05-20 | 38998.01 | 38998.01 | 0 | 0 | 0
2024-06-20 | 38998.01 | 38998.01 | 0 | 0 | 0
2024-07-20 | 39001.01 | 38998.01 | 0 | 3 | 0
2024-08-20 | 39255.73 | 38998.01 | 254.72 | 3 | 0
2024-09-20 | 39455.93 | 38998.01 | 454.92 | 3 | 0
2024-10-20 | 39455.93 | 38998.01 | 454.92 | 3 | 0
2024-11-20 | 39455.93 | 38998.01 | 454.92 | 3 | 0
2024-12-20 | 39465.86 | 38998.01 | 464.85 | 3 | 0
2025-01-20 | 39465.86 | 38998.01 | 464.85 | 3 | 0
2025-02-20 | 39465.86 | 38998.01 | 464.85 | 3 | 0
2025-03-20 | 39811.27 | 38998.01 | 613.25 | 200.01 | 0
2025-04-20 | 39976.69 | 38998.01 | 778.67 | 200.01 | 0
2025-05-20 | 39976.69 | 38998.01 | 778.67 | 200.01 | 0
2025-06-20 | 40183.69 | 38998.01 | 778.67 | 407.01 | 0
2025-07-20 | 40183.69 | 38998.01 | 778.67 | 407.01 | 0
2025-08-20 | 40418.19 | 38998.01 | 1013.17 | 407.01 | 0

## Solar Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 23INR0144 | Galactic Solar | Grayson | 2024-03-01 | 2022-08-12 | Solar | PV | 205.2 | 2024 | No
[6 empty] | 21INR0395 | SunRay | Uvalde | 2024-06-04 | 2021-07-06 | Solar | PV | 203.5 | 2024 | Yes
[6 empty] | 21INR0303 | Mandorla Solar | Milam | 2024-06-29 | 2022-09-19 | Solar | PV | 254 | 2024 | Yes
[6 empty] | 22INR0283 | Peregrine Solar | Goliad | 2024-07-01 | 2021-06-19 | Solar | PV | 301.3 | 2024 | Yes
[6 empty] | 22INR0354 | XE Murat [Adlong] Solar | Harris | 2024-07-26 | 2022-03-04 | Solar | PV | 60.36 | 2024 | Yes
[6 empty] | 21INR0353 | Big Elm Solar | Bell | 2024-08-09 | 2022-09-01 | Solar | PV | 200.29 | 2024 | Yes
[6 empty] | 23INR0026 | Baker Branch Solar | Lamar | 2024-08-19 | 2022-02-14 | Solar | PV | 469.42 | 2024 | Yes
[6 empty] | 23INR0385 | Camp Creek Solar SLF | Robertson | 2024-08-31 | 2023-07-15 | Solar | PV | 165.6 | 2024 | No
[6 empty] | 19INR0134 | Cottonwood Bayou Solar | Brazoria | 2024-09-07 | 2019-11-13 | Solar | PV | 351.4 | 2024 | Yes
[6 empty] | 19INR0155 | Morrow Lake Solar | Frio | 2024-09-16 | 2019-08-29 | Solar | PV | 201.1 | 2024 | Yes
[6 empty] | 20INR0248 | DAMAZO (Second Division) SOLAR | Brazoria | 2024-09-17 | 2020-10-14 | Solar | PV | 100.2 | 2024 | Yes
[6 empty] | 21INR0424 | Tierra Bonita Solar | Pecos | 2024-09-26 | 2022-09-08 | Solar | PV | 306.9 | 2024 | Yes
[6 empty] | 23INR0114 | True North Solar | Falls | 2024-09-30 | 2023-04-20 | Solar | PV | 238.8 | 2024 | Yes
[6 empty] | 22INR0335 | Estonian Solar | Delta | 2024-10-31 | 2021-08-12 | Solar | PV | 202.5 | 2024 | Yes
[6 empty] | 23INR0180 | Jackalope Solar | San Patricio | 2024-10-31 | 2021-09-30 | Solar | PV | 155.68 | 2024 | Yes
[6 empty] | 21INR0368 | Eliza Solar | Kaufman | 2024-11-01 | 2022-08-04 | Solar | PV | 151.7 | 2024 | Yes
[6 empty] | 23INR0089 | Donegal Solar | Dickens | 2024-11-30 | 2022-07-25 | Solar | PV | 204.2 | 2024 | No
[6 empty] | 20INR0216 | Starr Solar Ranch | Starr | 2024-12-01 | 2020-10-01 | Solar | PV | 136.73 | 2024 | Yes
[6 empty] | 21INR0220 | Maleza Solar | Wharton | 2024-12-01 | 2021-01-27 | Solar | PV | 254.94 | 2024 | Yes
[6 empty] | 23INR0084 | Lavaca Bay Solar | Matagorda | 2024-12-04 | 2022-06-15 | Solar | PV | 243.46 | 2024 | Yes
[6 empty] | 21INR0490 | Samson Solar 2 | Lamar | 2024-12-15 | 2020-08-27 | Solar | PV | 203 | 2024 | Yes
[6 empty] | 24INR0208 | Eastbell Milam Solar II | Milam | 2024-12-20 | 2023-10-25 | Solar | PV | 151.04 | 2024 | Yes
[6 empty] | 24INR0023 | Compadre Solar | Hill | 2024-12-25 | 2022-11-12 | Solar | PV | 406.14 | 2024 | Yes
[6 empty] | 21INR0223 | Tulsita Solar | Goliad | 2024-12-31 | 2022-09-19 | Solar | PV | 256.2 | 2024 | Yes
[6 empty] | 22INR0356 | Jungmann Solar | Milam | 2024-12-31 | 2022-02-15 | Solar | PV | 40.21 | 2024 | No
[6 empty] | 22INR0511 | Gransolar Texas One | Milam | 2024-12-31 | 2022-06-13 | Solar | PV | 50 | 2024 | Yes
[6 empty] | 23INR0021 | Hornet Solar | Swisher | 2024-12-31 | 2021-12-06 | Solar | PV | 602.37 | 2024 | Yes
[6 empty] | 23INR0044 | Parliament Solar | Waller | 2024-12-31 | 2022-05-26 | Solar | PV | 484.56 | 2024 | Yes
[6 empty] | 23INR0070 | Chillingham Solar | Bell | 2024-12-31 | 2022-02-04 | Solar | PV | 352.39 | 2024 | Yes
[6 empty] | 24INR0477 | Barrett Solar | Rains | 2024-12-31 | 2023-10-05 | Solar | PV | 127.5 | 2024 | No
[6 empty] | 23INR0111 | GULF STAR SOLAR | Wharton | 2025-01-02 | 2021-10-01 | Solar | PV | 451.63 | 2025 | Yes
[6 empty] | 23INR0150 | Cradle Solar | Brazoria | 2025-01-02 | 2023-03-15 | Solar | PV | 225 | 2025 | No
[6 empty] | 23INR0007 | Outpost Solar | Webb | 2025-01-07 | 2022-01-11 | Solar | PV | 517.3 | 2025 | Yes
[6 empty] | 22INR0257 | Corazon Solar Phase II | Webb | 2025-01-12 | 2020-08-04 | Solar | PV | 203.9 | 2025 | No
[6 empty] | 23INR0054 | Tanglewood Solar | Brazoria | 2025-01-16 | 2022-11-01 | Solar | PV | 250.96 | 2025 | Yes
[6 empty] | 21INR0379 | Ash Creek Solar | Hill | 2025-01-31 | 2022-11-11 | Solar | PV | 417.74 | 2025 | Yes
[6 empty] | 22INR0455 | Blue Sky Sol | Crockett | 2025-02-15 | 2022-02-01 | Solar | PV | 101.2 | 2025 | Yes
[6 empty] | 20INR0230 | Markum Solar | McLennan | 2025-02-28 | 2021-06-28 | Solar | PV | 161.54 | 2025 | Yes
[6 empty] | 21INR0256 | Amsterdam Solar | Brazoria | 2025-03-01 | 2022-02-17 | Solar | PV | 509.88 | 2025 | No
[6 empty] | 21INR0391 | Grandslam Solar | Atascosa | 2025-03-01 | 2021-01-29 | Solar | PV | 121.89 | 2025 | No
[6 empty] | 20INR0086 | Arroyo Solar | Cameron | 2025-03-02 | 2021-09-28 | Solar | PV | 180 | 2025 | Yes
[6 empty] | 20INR0208 | Signal Solar | Hunt | 2025-03-15 | 2020-10-23 | Solar | PV | 51.79 | 2025 | Yes
[6 empty] | 16INR0049 | Nazareth Solar | Castro | 2025-03-24 | 2023-06-07 | Solar | PV | 204 | 2025 | Yes
[6 empty] | 24INR0093 | Oriana Solar | Victoria | 2025-04-06 | 2023-02-27 | Solar | PV | 181 | 2025 | No
[6 empty] | 22INR0203 | Delilah Solar 2 | Lamar | 2025-04-15 | 2020-12-22 | Solar | PV | 317.58 | 2025 | Yes
[6 empty] | 21INR0393 | Orange Grove Solar | Jim Wells | 2025-04-30 | 2022-06-08 | Solar | PV | 130.6 | 2025 | Yes
[6 empty] | 24INR0031 | Stoneridge Solar | Milam | 2025-04-30 | 2023-05-15 | Solar | PV | 201.6 | 2025 | Yes
[6 empty] | 23INR0035 | Starling Solar | Gonzales | 2025-05-09 | 2021-12-03 | Solar | PV | 123 | 2025 | Yes
[6 empty] | 20INR0091 | Fagus Solar Park SLF | Childress | 2025-05-15 | 2019-02-21 | Solar | PV | 519.46 | 2025 | Yes
[6 empty] | 23INR0045 | GP Solar | Van Zandt | 2025-05-15 | 2021-12-29 | Solar | PV | 121.97 | 2025 | Yes
[6 empty] | 19INR0110 | Azalea Springs Solar | Angelina | 2025-05-31 | 2023-09-14 | Solar | PV | 181 | 2025 | No
[6 empty] | 23INR0047 | Charger Solar | Refugio | 2025-05-31 | 2021-06-05 | Solar | PV | 406.77 | 2025 | Yes
[6 empty] | 23INR0058 | Erin Solar | Wharton | 2025-05-31 | 2023-03-22 | Solar | PV | 202.5 | 2025 | No
[6 empty] | 23INR0091 | Cascade Solar | Brazoria | 2025-06-01 | 2023-04-17 | Solar | PV | 254.2 | 2025 | Yes
[6 empty] | 24INR0070 | Sypert Branch Solar Project | Milam | 2025-06-01 | 2023-10-12 | Solar | PV | 261.15 | 2025 | Yes
[6 empty] | 24INR0075 | Blue Bird Solar | Johnson | 2025-06-01 | 2024-01-18 | Solar | PV | 1004 | 2025 | No
[6 empty] | 24INR0166 | Stillhouse Solar | Bell | 2025-06-01 | 2023-06-07 | Solar | PV | 212.51 | 2025 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 23INR0160 | Grimes County Solar | Grimes | 2025-06-15 | 2022-06-23 | Solar | PV | 210 | 2025 | Yes
2024-03-20 | 23619.23 | 23414.23 | 0 | 205 | 0 | 20INR0203 | Pine Forest Solar | Hopkins | 2025-06-29 | 2020-07-29 | Solar | PV | 305 | 2025 | No
2024-04-20 | 23619.43 | 23414.23 | 0 | 205.2 | 0 | 24INR0038 | SP Jaguar Solar | McLennan | 2025-06-30 | 2022-09-12 | Solar | PV | 300 | 2025 | Yes
2024-05-20 | 23619.43 | 23414.23 | 0 | 205.2 | 0 | 21INR0341 | Space City Solar | Wharton | 2025-07-01 | 2021-01-06 | Solar | PV | 609.74 | 2025 | Yes
2024-06-20 | 24076.93 | 23414.23 | 457.5 | 205.2 | 0 | 21INR0344 | Lunis Creek Solar SLF | Jackson | 2025-07-01 | 2021-10-29 | Solar | PV | 617.12 | 2025 | Yes
2024-07-20 | 24438.59 | 23414.23 | 819.16 | 205.2 | 0 | 23INR0118 | Blevins Solar | Falls | 2025-07-01 | 2023-06-17 | Solar | PV | 271.6 | 2025 | Yes
2024-08-20 | 25273.9 | 23414.23 | 1488.87 | 370.8 | 0 | 25INR0052 | SanPat Solar II | San Patricio | 2025-07-01 | 2023-10-18 | Solar | PV | 256.23 | 2025 | Yes
2024-09-20 | 26472.3 | 23414.23 | 2687.27 | 370.8 | 0 | 25INR0081 | SanPat Solar I | San Patricio | 2025-07-01 | 2023-10-18 | Solar | PV | 308.88 | 2025 | Yes
2024-10-20 | 26830.48 | 23414.23 | 3045.45 | 370.8 | 0 | 23INR0040 | Dori BQ Solar | Harris | 2025-07-04 | 2022-12-01 | Solar | PV | 50.42 | 2025 | No
2024-11-20 | 27186.38 | 23414.23 | 3197.15 | 575 | 0 | 23INR0225 | MRG GOODY SOLAR | Lamar | 2025-07-07 | 2023-11-07 | Solar | PV | 171.72 | 2025 | No
2024-12-20 | 30494.92 | 23414.23 | 6337.98 | 742.71 | 0 | 20INR0255 | Renegade Project | Deaf Smith | 2025-07-31 | 2021-01-04 | Solar | PV | 515.66 | 2025 | Yes
2025-01-20 | 32561.45 | 23414.23 | 7975.61 | 1171.61 | 0 | 24INR0141 | Gaia Solar | Navarro | 2025-07-31 | 2023-11-08 | Solar | PV | 152.65 | 2025 | Yes
2025-02-20 | 32824.19 | 23414.23 | 8238.35 | 1171.61 | 0 | 20INR0222 | Tyson Nick Solar | Lamar | 2025-08-01 | 2020-08-28 | Solar | PV | 90.5 | 2025 | No
2025-03-20 | 33891.75 | 23414.23 | 8674.14 | 1803.38 | 0 | 21INR0268 | Greyhound Solar | Ector | 2025-08-08 | 2022-01-15 | Solar | PV | 608.7 | 2025 | No
2025-04-20 | 34722.53 | 23414.23 | 9323.92 | 1984.38 | 0 | 23INR0344 | XE Hermes Solar | Bell | 2025-08-25 | 2023-11-08 | Solar | PV | 100.36 | 2025 | Yes
2025-05-20 | 36277.23 | 23414.23 | 10495.12 | 2367.88 | 0 | 23INR0349 | Tokio Solar | McLennan | 2025-08-25 | 2023-11-06 | Solar | PV | 175.72 | 2025 | Yes
2025-06-20 | 38824.09 | 23414.23 | 11732.98 | 3676.88 | 0 | 23INR0056 | Caliche Mound Solar | Deaf Smith | 2025-08-28 | 2023-10-12 | Solar | PV | 408.21 | 2025 | Yes
2025-07-20 | 41778.11 | 23414.23 | 14464.86 | 3899.02 | 0 | 24INR0139 | Midpoint Solar | Hill | 2025-08-30 | 2023-10-31 | Solar | PV | 103.8 | 2025 | Yes
2025-08-20 | 43468.9 | 23414.23 | 15252.95 | 4801.72 | 0 | 24INR0303 | Erika Solar | Kaufman | 2025-08-31 | 2023-10-12 | Solar | PV | 203.5 | 2025 | No

## Battery Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 24INR0609 | Rodeo Ranch Energy Storage Repowering | Reeves | 2024-04-16 | 2022-02-01 | Battery | BA | 10 | 2024 | Yes
[6 empty] | 22INR0322 | Paleo BESS | Hale | 2024-05-19 | 2021-02-05 | Battery | BA | 200.8 | 2024 | Yes
[6 empty] | 22INR0325 | Dickens BESS | Dickens | 2024-05-30 | 2020-11-02 | Battery | BA | 200.8 | 2024 | Yes
[6 empty] | 22INR0490 | Callisto I Energy Center | Harris | 2024-06-01 | 2022-04-07 | Battery | BA | 206.4 | 2024 | Yes
[6 empty] | 22INR0372 | Hydra BESS | Pecos | 2024-06-12 | 2021-05-08 | Battery | BA | 200.8 | 2024 | Yes
[6 empty] | 23INR0470 | BoCo BESS | Borden | 2024-06-22 | 2022-12-09 | Battery | BA | 155.48 | 2024 | Yes
[6 empty] | 23INR0072 | Tortolas BESS | Brazoria | 2024-06-25 | 2021-07-15 | Battery | BA | 50.3 | 2024 | Yes
[6 empty] | 23INR0460 | GULF STAR STORAGE | Wharton | 2024-06-25 | 2023-03-23 | Battery | BA | 152.74 | 2024 | Yes
[6 empty] | 23INR0363 | River Bend | Fort Bend | 2024-06-27 | 2022-10-18 | Battery | BA | 101.64 | 2024 | Yes
[6 empty] | 23INR0331 | Talitha BESS | Jim Wells | 2024-06-30 | 2022-11-30 | Battery | BA | 61.39 | 2024 | Yes
[6 empty] | 24INR0100 | Sheep Creek Storage | Callahan | 2024-07-01 | 2023-12-21 | Battery | BA | 142.1 | 2024 | Yes
[6 empty] | 22INR0327 | Hummingbird Storage | Denton | 2024-07-10 | 2022-02-23 | Battery | BA | 103.8 | 2024 | Yes
[6 empty] | 22INR0338 | Limousin Oak Storage | Grimes | 2024-07-10 | 2022-04-01 | Battery | BA | 104.62 | 2024 | Yes
[6 empty] | 23INR0403 | Connolly Storage | Wise | 2024-08-15 | 2023-02-27 | Battery | BA | 125.36 | 2024 | Yes
[6 empty] | 24INR0273 | Al Pastor BESS | Dawson | 2024-08-16 | 2023-01-24 | Battery | BA | 103.1 | 2024 | Yes
[6 empty] | 23INR0423 | Camp Creek Storage SLF | Robertson | 2024-08-31 | 2023-07-15 | Battery | BA | 0 | 2024 | No
[6 empty] | 24INR0312 | Wigeon Whistle BESS | Collin | 2024-09-01 | 2022-12-08 | Battery | BA | 122.9 | 2024 | Yes
[6 empty] | 23INR0166 | Great Kiskadee Storage | Hidalgo | 2024-09-06 | 2022-06-30 | Battery | BA | 103.05 | 2024 | Yes
[6 empty] | 24INR0147 | Holy ESS | Harris | 2024-09-21 | 2022-07-29 | Battery | BA | 209.32 | 2024 | Yes
[6 empty] | 22INR0260 | Eliza Storage | Kaufman | 2024-09-27 | 2022-08-04 | Battery | BA | 100.4 | 2024 | Yes
[6 empty] | 24INR0629 | Jade Storage SLF | Scurry | 2024-09-30 | 2024-03-28 | Battery | BA | 0 | 2024 | No
[6 empty] | 22INR0336 | Estonian Storage | Delta | 2024-10-08 | 2021-08-12 | Battery | BA | 101.6 | 2024 | Yes
[6 empty] | 20INR0246 | Ryan Energy Storage | Coryell | 2024-10-21 | 2021-02-18 | Battery | BA | 50 | 2024 | Yes
[6 empty] | 25INR0328 | Longbow BESS | Brazoria | 2024-11-13 | 2023-07-18 | Battery | BA | 180.8 | 2024 | Yes
[6 empty] | 23INR0103 | Burksol BESS | Dickens | 2024-11-30 | 2022-11-17 | Battery | BA | 103.27 | 2024 | Yes
[6 empty] | 22INR0349 | Antlia BESS | Val Verde | 2024-12-01 | 2021-06-05 | Battery | BA | 72.38 | 2024 | Yes
[6 empty] | 22INR0353 | Carina BESS | Nueces | 2024-12-01 | 2021-08-03 | Battery | BA | 154.11 | 2024 | Yes
[6 empty] | 22INR0368 | Padua Grid BESS | Bexar | 2024-12-01 | 2021-11-16 | Battery | BA | 51.1 | 2024 | Yes
[6 empty] | 22INR0388 | Cachi BESS | Guadalupe | 2024-12-01 | 2021-06-11 | Battery | BA | 205.46 | 2024 | No
[6 empty] | 23INR0287 | Avila BESS | Pecos | 2024-12-01 | 2023-02-06 | Battery | BA | 163.86 | 2024 | Yes
[6 empty] | 23INR0290 | Zeya BESS | Galveston | 2024-12-01 | 2023-01-20 | Battery | BA | 255.33 | 2024 | Yes
[6 empty] | 23INR0358 | Castor BESS | Brazoria | 2024-12-01 | 2023-09-15 | Battery | BA | 204.83 | 2024 | Yes
[6 empty] | 24INR0128 | Desna BESS | Brazoria | 2024-12-01 | 2023-09-15 | Battery | BA | 204.84 | 2024 | Yes
[6 empty] | 24INR0329 | XE Murat Storage | Harris | 2024-12-14 | 2023-11-01 | Battery | BA | 62.05 | 2024 | No
[6 empty] | 24INR0405 | Crowned Heron BESS | Fort Bend | 2024-12-15 | 2023-06-26 | Battery | BA | 150 | 2024 | Yes
[6 empty] | 22INR0328 | Inertia BESS | Haskell | 2024-12-31 | 2021-05-04 | Battery | BA | 13 | 2024 | Yes
[6 empty] | 22INR0549 | Tanzanite Storage | Henderson | 2024-12-31 | 2022-07-15 | Battery | BA | 265.8 | 2024 | Yes
[6 empty] | 23INR0419 | SOHO BESS | Brazoria | 2025-01-01 | 2022-12-01 | Battery | BA | 206.32 | 2025 | Yes
[6 empty] | 25INR0162 | SOHO II BESS | Brazoria | 2025-01-01 | 2023-04-15 | Battery | BA | 206.32 | 2025 | Yes
[6 empty] | 24INR0265 | Ironman BESS | Brazoria | 2025-01-13 | 2022-12-15 | Battery | BA | 308.6 | 2025 | Yes
[6 empty] | 22INR0468 | Lower Rio BESS | Hidalgo | 2025-01-15 | 2023-07-10 | Battery | BA | 60.45 | 2025 | Yes
[6 empty] | 23INR0195 | Desert Willow BESS | Ellis | 2025-02-02 | 2023-05-15 | Battery | BA | 154.4 | 2025 | Yes
[6 empty] | 23INR0299 | Anole BESS | Dallas | 2025-02-09 | 2023-04-26 | Battery | BA | 247.1 | 2025 | Yes
[6 empty] | 22INR0417 | Amsterdam Storage | Brazoria | 2025-03-01 | 2022-04-14 | Battery | BA | 201.13 | 2025 | No
[6 empty] | 24INR0306 | Arroyo Storage | Cameron | 2025-03-02 | 2022-08-10 | Battery | BA | 183.76 | 2025 | No
[6 empty] | 22INR0554 | Platinum Storage | Fannin | 2025-03-03 | 2022-11-17 | Battery | BA | 309.53 | 2025 | No
[6 empty] | 23INR0381 | Bexar ESS | Bexar | 2025-03-15 | 2023-07-31 | Battery | BA | 102.6 | 2025 | Yes
[6 empty] | 23INR0219 | Dogfish BESS | Pecos | 2025-04-16 | 2023-06-01 | Battery | BA | 75 | 2025 | Yes
[6 empty] | 25INR0300 | Wizard BESS | Galveston | 2025-04-29 | 2023-08-21 | Battery | BA | 150.82 | 2025 | No
[6 empty] | 23INR0079 | Chillingham Storage | Bell | 2025-05-02 | 2022-02-04 | Battery | BA | 153.93 | 2025 | Yes
[6 empty] | 22INR0540 | Walstrom BESS | Austin | 2025-05-05 | 2023-06-30 | Battery | BA | 200 | 2025 | Yes
[6 empty] | 23INR0354 | Bordertown BESS | Starr | 2025-05-10 | 2022-10-12 | Battery | BA | 106.15 | 2025 | Yes
[6 empty] | 24INR0295 | Lucky Bluff BESS | Erath | 2025-05-31 | 2023-11-08 | Battery | BA | 100.8 | 2025 | Yes
[6 empty] | 24INR0315 | Black Springs BESS | Palo Pinto | 2025-05-31 | 2023-10-18 | Battery | BA | 120.96 | 2025 | Yes
[6 empty] | 23INR0350 | Fort Duncan BESS | Maverick | 2025-06-01 | 2022-12-12 | Battery | BA | 106.15 | 2025 | Yes
[6 empty] | 24INR0281 | Red Egret BESS | Galveston | 2025-06-01 | 2023-06-07 | Battery | BA | 310.58 | 2025 | Yes
[6 empty] | 25INR0467 | Bocanova BESS | Brazoria | 2025-06-01 | 2023-11-14 | Battery | BA | 300.92 | 2025 | Yes
[6 empty] | 24INR0460 | Evelyn Battery Energy Storage System | Galveston | 2025-06-10 | 2023-09-14 | Battery | BA | 451.98 | 2025 | No
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 23INR0401 | Headcamp | Pecos | 2025-06-16 | 2024-02-16 | Battery | BA | 150 | 2025 | No
2024-03-20 | 6311.79 | 6301.84 | 0 | 0 | 9.95 | 21INR0492 | Stockyard Grid Batt | Tarrant | 2025-06-30 | 2022-10-26 | Battery | BA | 150.6 | 2025 | Yes
2024-04-20 | 6321.79 | 6301.84 | 10 | 0 | 9.95 | 24INR0039 | SP Jaguar BESS | McLennan | 2025-06-30 | 2022-09-12 | Battery | BA | 300 | 2025 | Yes
2024-05-20 | 6772.75 | 6301.84 | 411.6 | 0 | 59.31 | 23INR0119 | Blevins Storage | Falls | 2025-07-01 | 2023-06-17 | Battery | BA | 181.3 | 2025 | Yes
2024-06-20 | 7731.2 | 6301.84 | 1340.35 | 0 | 89.01 | 24INR0109 | Oriana BESS | Victoria | 2025-07-02 | 2023-02-27 | Battery | BA | 60.3 | 2025 | Yes
2024-07-20 | 8101.57 | 6301.84 | 1690.87 | 0 | 108.86 | 24INR0196 | Dori BQ BESS | Harris | 2025-07-04 | 2023-05-31 | Battery | BA | 154 | 2025 | No
2024-08-20 | 8369.43 | 6301.84 | 1919.33 | 0 | 148.26 | 21INR0443 | Cottonwood Bayou Storage | Brazoria | 2025-07-07 | 2022-03-18 | Battery | BA | 153.03 | 2025 | Yes
2024-09-20 | 8919.9 | 6301.84 | 2455 | 0 | 163.06 | 25INR0262 | Shepard Energy Storage | Galveston | 2025-07-09 | 2024-01-17 | Battery | BA | 263.2 | 2025 | Yes
2024-10-20 | 9081.49 | 6301.84 | 2606.6 | 0 | 173.05 | 21INR0517 | Tidwell Prairie Storage 1 | Robertson | 2025-07-15 | 2022-11-03 | Battery | BA | 200 | 2025 | Yes
2024-11-20 | 9365.56 | 6301.84 | 2890.67 | 0 | 173.05 | 22INR0555 | TE Smith Storage | Rockwall | 2025-07-15 | 2023-11-08 | Battery | BA | 125.36 | 2025 | Yes
2024-12-20 | 11188.21 | 6301.84 | 4425.92 | 267.51 | 192.94 | 24INR0294 | Citrus Flatts BESS | Cameron | 2025-07-15 | 2023-09-08 | Battery | BA | 100.8 | 2025 | Yes
2025-01-20 | 11969.9 | 6301.84 | 5207.61 | 267.51 | 192.94 | 23INR0343 | Guajillo Energy Storage | Webb | 2025-07-30 | 2021-12-21 | Battery | BA | 204.8 | 2025 | Yes
2025-02-20 | 12371.4 | 6301.84 | 5609.11 | 267.51 | 192.94 | 23INR0494 | Cartwheel BESS 1 | Hopkins | 2025-07-31 | 2023-11-10 | Battery | BA | 156.91 | 2025 | Yes
2025-03-20 | 13168.42 | 6301.84 | 5711.71 | 961.93 | 192.94 | 24INR0140 | Gaia Storage | Navarro | 2025-07-31 | 2023-11-08 | Battery | BA | 76.83 | 2025 | Yes
2025-04-20 | 13394.24 | 6301.84 | 5786.71 | 1112.75 | 192.94 | 24INR0365 | XE Hermes Storage | Bell | 2025-08-25 | 2023-11-08 | Battery | BA | 100.42 | 2025 | Yes
2025-05-20 | 14076.08 | 6301.84 | 6468.55 | 1112.75 | 192.94 | 24INR0302 | Pintail Pass BESS | San Patricio | 2025-08-27 | 2023-05-16 | Battery | BA | 207.18 | 2025 | No
2025-06-20 | 15846.31 | 6301.84 | 7636.8 | 1714.73 | 192.94 | 24INR0138 | Midpoint Storage | Hill | 2025-08-30 | 2023-10-31 | Battery | BA | 52.24 | 2025 | Yes
2025-07-20 | 17522.84 | 6301.84 | 9159.33 | 1868.73 | 192.94
2025-08-20 | 17882.68 | 6301.84 | 9311.99 | 2075.91 | 192.94 | Small Generators | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 22INR0590 | Muenster BESS | Cooke | 2024-12-31 | 2023-07-12 | Battery | BA | 9.9 | 2024 | No
[6 empty] | 22INR0596 | Grizzly Ridge BESS | Hamilton | 2023-05-31 | 2021-10-18 | Battery | BA | 9.95 | 2023 | Yes
[6 empty] | 22INR0602 | Regis Palacios BESS | Matagorda | 2024-07-16 | 2022-10-07 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0498 | Moore Field BESS 2 | Hidalgo | 2024-05-24 | 2022-10-07 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0499 | Laureles BESS | Cameron | 2024-08-15 | 2023-02-16 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0500 | Fort Mason BESS | Mason | 2024-09-30 | 2023-01-10 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0523 | Damon BESS | Brazoria | 2024-09-03 | 2022-10-18 | Battery | BA | 5 | 2024 | Yes
[6 empty] | 23INR0539 | Gregory BESS | San Patricio | 2024-06-11 | 2022-10-07 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0541 | Telview BESS | Fort Bend | 2024-05-31 | 2023-07-10 | Battery | BA | 9.96 | 2024 | Yes
[6 empty] | 23INR0543 | Continental BESS | Starr | 2024-05-17 | 2022-10-06 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0556 | IEP Orchard BESS | Fort Bend | 2024-10-02 | 2023-08-09 | Battery | BA | 9.99 | 2024 | Yes
[6 empty] | 23INR0569 | Weil Tract BESS | Nueces | 2024-05-15 | 2022-12-21 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0603 | IEP Damon BESS | Brazoria | 2024-12-02 | 2023-10-06 | Battery | BA | 9.99 | 2024 | Yes
[6 empty] | 23INR0620 | Falfurrias BESS | Brooks | 2024-06-14 | 2023-04-10 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 24INR0499 | Medina Lake BESS | Bandera | 2024-08-31 | 2023-01-18 | Battery | BA | 9.8 | 2024 | No
[6 empty] | 24INR0588 | Cisco BESS | Eastland | 2024-06-14 | 2023-07-19 | Battery | BA | 9.9 | 2024 | No
[6 empty] | 24INR0610 | Century BESS | Tarrant | 2024-07-11 | 2023-04-14 | Battery | BA | 9.95 | 2024 | Yes
[6 empty] | 24INR0614 | Russek Street BESS | Reagan | 2024-08-02 | 2023-08-03 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 24INR0615 | Pavlov BESS | Matagorda | 2024-08-02 | 2023-08-21 | Battery | BA | 9.9 | 2024 | No
[6 empty] | 24INR0624 | Mainland BESS | Galveston | 2024-05-14 | 2023-08-22 | Battery | BA | 9.9 | 2024 | Yes

## Gas-Combined Cycle Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 22INR0533 | Temple Generation I Repower | Bell | 2022-06-09 | 2012-06-21 | Gas | CC | 67 | 2022 | Yes
[6 empty] | 23INR0524 | Temple II Repower | Bell | 2023-10-15 | 2012-06-21 | Gas | CC | 0 | 2023 | Yes
[6 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2024-06-30 | 2001-03-19 | Gas | CC | 21 | 2024 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2024-03-20 | 43776.709 | 43709.709 | 67 | 0 | 0
2024-04-20 | 43776.709 | 43709.709 | 67 | 0 | 0
2024-05-20 | 43776.709 | 43709.709 | 67 | 0 | 0
2024-06-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-07-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-08-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-09-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-10-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-11-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-12-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-01-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-02-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-03-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-04-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-05-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-06-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-07-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-08-20 | 43797.709 | 43709.709 | 88 | 0 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 23INR0408 | TECO GTG2 | Harris | 2024-05-29 | 2022-10-05 | Gas | GT | 50 | 2024 | Yes
[7 empty] | 24INR0605 | TEXAS GULF SULPHUR REPOWER | Wharton | 2024-06-25 | 2022-03-01 | Gas | GT | 94 | 2024 | Yes
[7 empty] | 23INR0339 | Remy Jade Power Station | Harris | 2024-06-30 | 2022-08-01 | Gas | GT | 408 | 2024 | Yes
[7 empty] | 23INR0506 | Beachwood II Power Station | Brazoria | 2024-08-01 | 2022-08-01 | Gas | GT | 102 | 2024 | Yes
[7 empty] | 24INR0382 | Remy Jade II Power Station | Harris | 2024-11-30 | 2022-08-01 | Gas | GT | 102 | 2024 | No
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
2024-03-20 | 24341.84 | 24341.84 | 0 | 0 | 0 | 0
2024-04-20 | 24347.44 | 24341.84 | 0 | 0 | 5.6 | 0
2024-05-20 | 24401.04 | 24341.84 | 50 | 0 | 9.2 | 0
2024-06-20 | 24911.59 | 24341.84 | 552 | 0 | 17.75 | 0
2024-07-20 | 24911.59 | 24341.84 | 552 | 0 | 17.75 | 0
2024-08-20 | 25013.59 | 24341.84 | 654 | 0 | 17.75 | 0
2024-09-20 | 25013.59 | 24341.84 | 654 | 0 | 17.75 | 0
2024-10-20 | 25013.59 | 24341.84 | 654 | 0 | 17.75 | 0
2024-11-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2024-12-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-01-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-02-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-03-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-04-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-05-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-06-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-07-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0
2025-08-20 | 25115.59 | 24341.84 | 654 | 102 | 17.75 | 0