## Slide 1: ERCOT Secure API Roadmap
Presented by: Brian Brandaw and Balendu Mishra
Date: 4/24/2024

## Slide 2: Secure API Roadmap
Goals and Objectives
Features and Prioritization
Timeline and Milestones
Technical Dependencies

## Slide 3: Goals and Objectives
Modernize API to improve onboarding experience
  Current External Web Service (EWS) interface remains relatively unchanged since Nodal launch 14 years ago.
  Possible scope items include:
    Move from SOAP over HTTPs to REST/JSON
    Adopt a modern authentication and authorization model like Oauth 2.0
Improve effectiveness of outbound messaging
  Current approach relies on SOAP over HTTPs
  Performance and capacity concerns with current method
Implement new features to improve flexibility and protect the infrastructure
  Add support for versioning of services
  Enforce usage guidelines through API Management platform
  Pagination and drill through with flexible query/path parameters
  Contract first approaches like OpenAPI or AsyncAPI specifications

## Slide 4: Goals and Objectives (cont)
Refactor report distribution
  Implement a Claim Check pattern for large reports
  Other changes could include
    “Push model” for data delivery
    Notification of new report availability

## Slide 5: Features and Prioritization
Scope to be determined through a collaborative process
  Survey to TWG ListServ group
  Discussions with Architecture, Operations and Development
  Consultation with Client Services
Proposed scope with prioritization to be presented at future TWG meeting
Trial services will be made available in Q4
  Subset of functionality intended to provide a cross section of the different services
  May be fully functional or may be mocked responses
  Will provide a means for Market Participants to invoke services and validate that their needs would be met
Market Participant feedback through the survey is key!

## Slide 6: Timeline and Milestones (Proposed)
2024
2027
Engagement
Develop
Support
Today
2024
2025
2026
2027
10 days
May 3 - May 17
Survey Open
4.5 days
May 20 - May 24
Compile Survey Results
34.5 days
Jun 3 - Jul 19
Overall Scope and Pilot Defined
49.5 days
7/29 - 10/4
Pilot Development
14.5 days
Sep 15 - Oct 4
Developer Portal Updates
53 days
Oct 8 - Dec 20
Pilot Available
14 days
Jan 6 - Jan 24
Update Scope
63.5 days
Feb 3 - May 1
Initiation Phase
197 days
May 1 - Feb 1
Development Phase
42.5 days
Feb 1 - Apr 1
Testing Phase
87.5 days
Apr 1 - Aug 1
Market Trials
260 days
Aug 15 - Aug 15
Legacy and Current Solutions Coexist
119.5 days
Feb 15 - Aug 1
Transition Support
Survey Published
May 3
Survey Results Presented
May 29
Pilot Begins
Oct 8
Market Trials Begin
Apr 1
Go-Live
Aug 15
Deprecate Legacy Solution
August 15, 2027
Pilot Complete
Dec 20

## Slide 7: Technical Dependencies
ERCOT intends to implement these services using API Management solution
ERCOT team will coordinate closely with RTC+B efforts
  This effort will be running in parallel with RTC+B
  Given the priority of RTC+B it is possible this schedule will need to be adjusted