## Slide 1: Market Coordination Team Update
RMS: May 07, 2024

## Slide 2: April
Reviewed redlines from TXSETCC848 – State or Province Codes will only contain uppercase letters
Reviewed updates to the Texas SET 5.0 Q&A
Reviewed Texas SET v5.0 Implementation Plan

## Slide 3: Texas SET v5.0 Implementation Plan
Tuesday, November 5, 2024
  2:00pm
    1st Market Conference Call – Confirm all MPs are ready to proceed with Texas SET v5.0 Implementation
Wednesday, November 6, 2004
  12:00pm
    CRs suspend sending 650_01 DNP Transactions – Pending DNPs will continue to be worked according to the DNP procedure
  5:00pm
    TDSPs will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs
Thursday, November 7, 2024
  4:00pm
    2nd Market Conference Call – Confirm DNPs are suspended; Roll call for TDSPs only

## Slide 4
Friday, November 8, 2024
  12:00pm
    CRs suspend sending 814 transactions to ERCOT (both EDI and through Retail portion of MIS)
    CRs begin using Safety Net process as needed for submitting MVIs with a requested date of November 8 - November 9
    CRs begin using Emergency Reconnect for non-payment spreadsheet process as needed for submitting Reconnects for Non-Payment
    CRs suspend 814_PC and 650_01 transactions
    TDSPs suspend 814_20 and 650_04 transactions
  1:00pm
    TDSPs suspend 867s and 814 responses as well as 814_PD, 650_02 transactions
    CRs suspend 824 transactions
    TDSPs to log MarkeTrak Issue with ERCOT for Initial County load file
  2:00pm
    3rd Market Conference Call - ERCOT confirmation of transaction suspension. Update on transaction processing.
  4:00pm
    TDSPs suspend 810_02 (810_03MC) transactions
    CRs suspend 820_02 (820_03MC) transactions
    997s suspended for all transactions
    ERCOT shuts down inbound and outbound processing and MarkeTrak

## Slide 5
Saturday, November 9, 2024
  12:00pm
    4th Market Conference Call - MP Migration Status
  6:00pm
    5th Market Conference Call - MP Migration Status
Sunday, November 10, 2024
  10:00am
    6th Market Conference Call - MP Migration Status; Confirm Market Readiness
  5:00pm
    7th Market Conference Call - MP Migration Status; Confirm Market Readiness
Monday, November 11, 2024
  10:00am
    8th Market Conference Call - MP Migration Status
You can find a copy of the Texas SET v5.0 Implementation Plan on the Market Coordination page of ERCOT.com

## Slide 6: Future Meetings
June 11th
July 16th
August 13th