## Slide 1
RTC+B Task Force
Update
Matt Mereness
RTCBTF
May 8, 2024

## Slide 2: Outline
Brief Program update: RTC+B Program Update from April Board T&S
Reminder of RTCBTF Review Cycle
Review of Issues List
Today’s Issues List for Discussion:
  Issue 4 - Verifiable Cost Manual- Change for on-line hydro Resources per Key Principle 1.3(3)
  Issue 3 - Framework for periodic analysis comparing RTC and the current ORDC design
  Issue 20 - Review of the Energy and AS Offer Caps in the context of Current Policy
  Issue 9-10 - Market Readiness and Technical Workshops
  Issue 18 - Placeholder for MPs discussion of AS Demand Curves
Look to complete before 1pm today
Next steps after today’s RTCBTF meeting

## Slide 3: RTC+B Program Update (excerpt from April Board T&S RTC Update)

## Slide 4: Sequence and Potential Dates for Market Trials (dates subject to change while in Planning phase)
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Closed-loop RTC SCED
(QSE offers, SCED binding award and dispatch for 2-3 instances of 2-4 hours)
RTC QSE Telemetry Testing/Check-out
(Individual QSE testing of UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers at least 2 times)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
2 months
2 months
1-2 months
1 month
2-3 months
1-2 months
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
DRAFT

## Slide 5: Plans for Meetings and Review Cycles
Reminder of RTC+B Program Scope
  RTC Key Principles were approved to lay foundation of NPRR1007-1013
    Consolidated Key Principles: https://www.ercot.com/files/docs/2020/04/01/RTC_Key_Principle_Quick_Reference.docx
    Library of Key Principles: https://www.ercot.com/mktrules/puctDirectives/rtCoOptimization
  Battery Key Topic Concepts approved to lay foundation of NPRR1014
    https://www.ercot.com/mktrules/keypriorities/bes
  RTC State-of-Charge accounting in NPRR1204
Objective is to present concepts or issues that need to be resolved for an effective implementation.
  Coordinating timelines for interface requirements and testing,
  Providing the forum for any analysis or policy decisions (such as parameter values)
  Coordinating market readiness and cutover activities,
  Review draft Revision Requests or other artifacts necessary to successfully implement the program within the identified timeframes, and discussing other details as needed.
Lessons learned from RTCTF to avoid being delayed in decisions:
  Meeting #1: Initial concept presented by ERCOT staff
  Meeting #2: Comments and alternatives presented by MPs
  Meeting #3: RTCTF consensus achieved or escalated to TAC for a vote to decide the matter.

## Slide 6: Current Issues List
Link to current issues on today’s meeting page
Closed/green on RUC Capacity Short (added Resolved Worksheet)
- Moving up discussion of interface changes, market trials, details for designing control systems

## Slide 7: Summary of Resolved Issues
Resolved Tab of Issues Workbook:

## Slide 8: Proceed with rest of meeting
Issue 4 - Verifiable Cost Manual- Change for on-line hydro Resources per KP 1.3(3)
  Final review and includes draft language
    No comments received from March RTCBTF presentation
    Confirm concept in Resolved Tab of Issues Sheet
Issue 3 - Framework for periodic analysis comparing RTC and the current ORDC design
  Prior meeting had ERCOT approach to analysis (public Excel tool and internal Python Simulator)
  Today review Luminant’s feedback on Operating Days to be evaluated in RTC Simulator Tool
Issue 20 - Review of the Energy and AS Offer Caps in the context of Current Policy
  First time discussion and will include ESR examples
Issue 9-10 - Market Readiness and Technical Workshops
  Review of past 2 workshops
      RTC+B Technical Workshop - April 18, 2024: 1:00 PM – 4:00 PM
      RTC+B Technical Workshop - May 6, 2024: 1:00 PM – 4:00 PM
Issue 18 - Review of the AS Demand Curves in the context of current policy
  No materials, but time allocated for MPs to share thoughts and next steps
End by 1pm

## Slide 9: Next steps after today’s May 8 RTCBTF meeting
May 15- RTC+B Technical Workshop #3
May 22- TAC Meeting to consider endorsement of concept for Issue 4 Change for Online Hydro (sets stage for ERCOT to submit draft NPRR and VCMRR)
June 6- RTC+B Technical Workshop #4
June 12- RTCBTF (will discuss any recommendations from Technical Workshops)
  Limited series of RTC+B Technical Workshops (April-June 2024)
    Target audience, vendors and IT development/implementation staff (sent to RTCBTF and TWG)
      RTC+B Technical Workshop - April 18, 2024: 1:00 PM – 4:00 PM :
      Overview of ICCP Telemetry/EMS SCADA/AGC changes & ICCP Configurations for parallel testing.
      RTC+B Technical Workshop - May 6, 2024: 1:00 PM – 4:00 PM :
      Finalize approach on ICCP configuration approaches for parallel testing and transition.
      RTC+B Technical Workshop - May 15, 2024: 1:00 PM – 4:00 PM :
      Market Interfaces design specifications (submissions - External API/Market Manager, notifications, and reports)
      RTC+B Technical Workshop - June 6, 2024: 1:00 PM – 4:00 PM :
      Reserved for further discussions if needed and Q&A session.
    Based on the feedback from these workshops, ERCOT will finalize ICCP/Market Interface design specifications and publish draft versions to the ERCOT website.
    This engagement will help QSEs and their vendors start planning their RTC+B systems design and implementation early to align with ERCOT’s RTC+B project implementation timelines which is critical for ERCOT to deliver this project successfully and on time.
    Discussions and artifacts will be highlighted and shared at regular RTCBTF meetings.