## RTCBTF
Id | Source | Issue to resolve | Type | Protocol needed? | Approval | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
1 | RTCTF issue | Parameters for Ancillary Service proxy offers (values for the parameters) | Policy | No | TAC | bar: 2024-08-01 to 2024-10-01
2 | RTCTF issue | ASDCs for use in Reliability Unit Commitment (RUC) studies (values for parameters) | Policy | No | TAC | bar: 2024-12-01 to 2025-02-01
3 | RTCTF issue | Framework for periodic analysis comparing RTC and the current ORDC design – KP 1.1(8) | Analysis | No | No | bar: 2024-04-01 to 2024-06-01
4 | RTCTF issue | Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3)) | Other | VCMRR NPRR | TAC | bar: 2024-03-01 to 2024-05-01
5 | RTCTF issue | Additional review of transmission constraint max. shadow price values (Sec 22 protocols per NPRR1211) | Policy | Yes | Normal process | bar: 2024-09-01 to 2024-11-01
6 | RTCTF issue | Operation Procedures (e.g., removing SASM and HASL/LASL), note to include any needed discussion on triggers for initiating off-cycle SCED execution | Readiness | No | Exisiting processes | bar: 2024-12-01 to 2025-04-01
7 | RTCTF issue | Business Practice Manuals (e.g., changes to COP and telemetry) | Readiness | No | Exisiting processes | bar: 2024-12-01 to 2025-04-01
8 | RTCTF issue | Mapping of bill determinants to extracts and reporting for developing shadow settlement | Readiness | No | No | bar: 2024-11-01 to 2025-01-01
9 | RTCTF issue | Changes to ICCP handbook, and documentation for non-ICCP market submissions | Readiness | No | Existing processes | bar: 2024-05-01 to 2024-10-01
10 | RTCTF issue | Market trials/training/annual seminar engagement (release plans/dates for market trials) | Readiness | No | TAC | bar: 2024-02-01; 2024-05-01 to 2024-12-01
11 | RTCTF issue | Any details MPs need for designing their control systems | Readiness | No | No | bar: 2024-07-01 to 2024-10-01
12 | ERCOT 2023 | Scaling Factor Values for RegU and RegD (ie, ramp sharing as values, dynamic or static?) | Other | No | TAC | bar: 2024-09-01 to 2024-11-01
13 | ERCOT 2023 | How DRRS would work in an RTC paradigm | Other | Yes | TAC | bar: 2024-07-01 to 2024-08-01
14 | ERCOT 2023 | Inclusion of firm load shed in the pricing run - (RTC changes to align with NPRR1081) | Policy | Yes | TAC | bar: 2024-07-01
15 | ERCOT 2023 | Various protocol references need to be updated | Other | Yes | TAC | bar: 2024-07-01; 2025-01-01
16 | ERCOT 2023 | RTC SOC duration parameter discussion | Policy | No | TAC | bar: 2025-01-01 to 2025-03-01
17 | ERCOT 2023 | RUC Capacity Short Calculations with SOC | Policy | NPRR | TAC | bar: 2024-02-01 to 2024-04-01
18 | RTCBTF 1/12/24 | Review of the AS Demand Curves in the context of current policy. | Other | No | No | bar: 2024-02-01 to 2024-06-01
19 | RTCBTF 1/12/24 | Emergency Price Program alignment to RTC (imbedded within NPRR1216, monitor only for RTCBTF) | Policy | Yes | Normal process
20 | RTCBTF 4/10/24 | Review of the Energy and AS Offer Caps in the context of current policy. | Other | No | No | bar: 2024-05-01
Blue is to reflect new or updated dates of review
Gray is to reflect existing review schedule
Green is to reflect completion

## Resolution
Resolved Issues
Id | Source | Issue to resolve | Resolution or next steps
17 | ERCOT 2023 | RUC Capacity Short Calculations with SOC | TAC approval of RUC Capacity Whitepaper at April 2024 TAC. ERCOT has submitted NPRR1236 to support whitepaper.
4 | RTCTF issue | Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3)) | TAC approval of following language at May 2024 TAC: Given that Hydro Resources operating in synchronous condenser mode are not dispatched by SCED, ERCOT proposes setting the Mitigated Offer Cap for all Hydro Resources to RTSWCAP. This will be done in protocol and verifiable cost manual by 1) setting the O&M value in the MOC to RTSWCAP and 2) Setting the heat rate to 0 MMBtu/MWh.