## Wind Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2024-07-31 | 2002-10-23 | Wind | WT | 3 | 2024 | No
[7 empty] | 20INR0155 | Peyton Creek Wind II | Matagorda | 2025-02-14 | 2023-02-27 | Wind | WT | 241.2 | 2025 | Yes
[7 empty] | 21INR0240 | La Casa Wind | Stephens | 2025-03-22 | 2023-09-07 | Wind | WT | 148.4 | 2025 | Yes
[7 empty] | 20INR0217 | CAROL wind | Potter | 2025-04-17 | 2020-09-11 | Wind | WT | 165.42 | 2025 | Yes
[7 empty] | 24INR0627 | Champion Wind Repower | Nolan | 2025-05-09 | 2007-01-19 | Wind | WT | 0.31 | 2025 | Yes
[7 empty] | 22INR0517 | Lane City Wind | Wharton | 2025-06-30 | 2022-05-13 | Wind | WT | 207 | 2025 | No
[7 empty] | 19INR0054 | Monte Cristo 1 Wind | Hidalgo | 2025-08-20 | 2023-05-09 | Wind | WT | 234.5 | 2025 | Yes
[7 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2025-09-01 | 2017-12-13 | Wind | WT | 197.01 | 2025 | No
[7 empty] | 24INR0116 | Hart Wind 2 | Castro | 2025-09-01 | 2023-10-06 | Wind | WT | 166.38 | 2025 | No
[7 empty] | 19INR0022 | Monte Alto I | Willacy | 2025-09-30 | 2020-02-13 | Wind | WT | 141.5 | 2025 | Yes
[7 empty] | 19INR0023 | Monte Alto 2 Wind | Willacy | 2025-09-30 | 2022-03-22 | Wind | WT | 307.9 | 2025 | Yes
[7 empty] | 16INR0104 | Big Sampson Wind | Crockett | 2025-10-04 | 2019-11-08 | Wind | WT | 265.4 | 2025 | Yes
[7 empty] | 23INR0637 | Goodnight Wind II | Armstrong | 2025-11-29 | 2019-08-18 | Wind | WT | 258.3 | 2025 | Yes
[7 empty] | 26INR0113 | Meitner Wind | Gray | 2026-09-17 | 2024-04-19 | Wind | WT | 836.5 | 2026 | No
[7 empty] | 21INR0263 | Monarch Creek Wind | Throckmorton | 2026-10-01 | 2020-08-24 | Wind | WT | 344.41 | 2026 | No
[7 empty] | 20INR0047 | Siete | Webb | 2026-10-31 | 2022-06-30 | Wind | WT | 375.06 | 2026 | Yes
[7 empty] | 22INR0499 | Aquilla Lake 3 Wind | Hill | 2027-04-09 | 2024-01-24 | Wind | WT | 225 | 2027 | Yes
[7 empty] | 24INR0291 | Rubicon Alpha Wind | Haskell | 2027-07-01 | 2024-05-08 | Wind | WT | 225.6 | 2027 | Yes
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
2000 | 160.37 | 160.37 | 0 | 0 | 0 | 0
2001 | 887.97 | 887.97 | 0 | 0 | 0 | 0
2002 | 1058.22 | 1058.22 | 0 | 0 | 0 | 0
2003 | 1255.72 | 1255.72 | 0 | 0 | 0 | 0
2004 | 1372.82 | 1372.82 | 0 | 0 | 0 | 0
2005 | 1967.04 | 1967.04 | 0 | 0 | 0 | 0
2006 | 2703.34 | 2703.34 | 0 | 0 | 0 | 0
2007 | 4266.36 | 4266.36 | 0 | 0 | 0 | 0
2008 | 8154.76 | 8154.76 | 0 | 0 | 0 | 0
2009 | 9080.78 | 9080.78 | 0 | 0 | 0 | 0
2010 | 9531.7 | 9531.7 | 0 | 0 | 0 | 0
2011 | 9663.7 | 9663.7 | 0 | 0 | 0 | 0
2012 | 11137.66 | 11137.66 | 0 | 0 | 0 | 0
2013 | 11286.26 | 11286.26 | 0 | 0 | 0 | 0
2014 | 13178.84 | 13178.84 | 0 | 0 | 0 | 0
2015 | 16376.53 | 16376.53 | 0 | 0 | 0 | 0
2016 | 19001.85 | 19001.85 | 0 | 0 | 0 | 0
2017 | 21248.99 | 21248.99 | 0 | 0 | 0 | 0
2018 | 22632.69 | 22632.69 | 0 | 0 | 0 | 0
2019 | 27219.34 | 27219.34 | 0 | 0 | 0 | 0
2020 | 31127.31 | 31127.31 | 0 | 0 | 0 | 0
2021 | 33928.91 | 33928.91 | 0 | 0 | 0 | 0
2022 | 36906.07 | 36906.07 | 0 | 0 | 0 | 0
2023 | 38694.49 | 38694.49 | 0 | 0 | 0 | 0
2024 | 39453.33 | 39450.33 | 0 | 3 | 0 | 0
2025 | 41786.65 | 39450.33 | 1762.93 | 573.39 | 0 | 0
2026 | 43342.62 | 39450.33 | 2137.99 | 1754.3 | 0 | 0
2027 | 43793.22 | 39450.33 | 2588.59 | 1754.3 | 0 | 0

## Solar Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 23INR0144 | Galactic Solar | Grayson | 2024-03-01 | 2022-08-12 | Solar | PV | 205.2 | 2024 | No
[7 empty] | 23INR0111 | PHOTON SOLAR | Wharton | 2024-08-13 | 2021-10-01 | Solar | PV | 451.63 | 2024 | Yes
[7 empty] | 19INR0155 | Morrow Lake Solar | Frio | 2024-09-16 | 2019-08-29 | Solar | PV | 201.1 | 2024 | Yes
[7 empty] | 20INR0248 | DAMAZO (Second Division) SOLAR | Brazoria | 2024-09-17 | 2020-10-14 | Solar | PV | 100.2 | 2024 | Yes
[7 empty] | 21INR0424 | Tierra Bonita Solar | Pecos | 2024-09-26 | 2022-09-08 | Solar | PV | 306.9 | 2024 | Yes
[7 empty] | 22INR0354 | XE Murat [Adlong] Solar | Harris | 2024-10-04 | 2022-03-04 | Solar | PV | 60.36 | 2024 | Yes
[7 empty] | 23INR0180 | Jackalope Solar | San Patricio | 2024-10-31 | 2021-09-30 | Solar | PV | 155.68 | 2024 | Yes
[7 empty] | 21INR0490 | Samson Solar 2 | Lamar | 2024-11-16 | 2020-08-27 | Solar | PV | 203 | 2024 | Yes
[7 empty] | 22INR0203 | Delilah Solar 2 | Lamar | 2024-11-16 | 2020-12-22 | Solar | PV | 317.58 | 2024 | Yes
[7 empty] | 20INR0230 | Markum Solar | McLennan | 2024-11-22 | 2021-06-28 | Solar | PV | 161.54 | 2024 | Yes
[7 empty] | 20INR0216 | Starr Solar Ranch | Starr | 2024-12-01 | 2020-10-01 | Solar | PV | 136.73 | 2024 | Yes
[7 empty] | 23INR0084 | Lavaca Bay Solar | Matagorda | 2024-12-04 | 2022-06-15 | Solar | PV | 243.46 | 2024 | Yes
[7 empty] | 21INR0368 | Eliza Solar | Kaufman | 2024-12-20 | 2022-08-04 | Solar | PV | 151.7 | 2024 | Yes
[7 empty] | 24INR0208 | Eastbell Milam Solar II | Milam | 2024-12-20 | 2023-10-25 | Solar | PV | 150.6 | 2024 | Yes
[7 empty] | 24INR0023 | Compadre Solar | Hill | 2024-12-25 | 2022-11-12 | Solar | PV | 406.14 | 2024 | Yes
[7 empty] | 22INR0283 | Peregrine Solar | Goliad | 2024-12-30 | 2021-06-19 | Solar | PV | 301.3 | 2024 | Yes
[7 empty] | 21INR0223 | Tulsita Solar | Goliad | 2024-12-31 | 2022-09-19 | Solar | PV | 256.2 | 2024 | Yes
[7 empty] | 22INR0356 | Jungmann Solar | Milam | 2024-12-31 | 2022-02-15 | Solar | PV | 40.21 | 2024 | Yes
[7 empty] | 22INR0511 | Gransolar Texas One | Milam | 2024-12-31 | 2022-06-13 | Solar | PV | 50 | 2024 | Yes
[7 empty] | 23INR0044 | Parliament Solar | Waller | 2024-12-31 | 2022-05-26 | Solar | PV | 484.56 | 2024 | Yes
[7 empty] | 23INR0070 | Chillingham Solar | Bell | 2024-12-31 | 2022-02-04 | Solar | PV | 352.39 | 2024 | Yes
[7 empty] | 23INR0150 | Cradle Solar | Brazoria | 2025-01-02 | 2023-03-15 | Solar | PV | 225 | 2025 | Yes
[7 empty] | 23INR0007 | Outpost Solar | Webb | 2025-01-07 | 2022-01-11 | Solar | PV | 517.3 | 2025 | Yes
[7 empty] | 23INR0054 | Tanglewood Solar | Brazoria | 2025-01-16 | 2022-11-01 | Solar | PV | 250.96 | 2025 | Yes
[7 empty] | 21INR0379 | Ash Creek Solar | Hill | 2025-01-31 | 2022-11-11 | Solar | PV | 417.74 | 2025 | Yes
[7 empty] | 24INR0421 | Swift Air Solar | Ector | 2025-02-12 | 2024-04-30 | Solar | PV | 148.84 | 2025 | Yes
[7 empty] | 22INR0455 | Blue Sky Sol | Crockett | 2025-02-15 | 2022-02-01 | Solar | PV | 101.2 | 2025 | Yes
[7 empty] | 21INR0220 | Maleza Solar | Wharton | 2025-03-01 | 2021-01-27 | Solar | PV | 254.94 | 2025 | Yes
[7 empty] | 21INR0256 | Amsterdam Solar | Brazoria | 2025-03-01 | 2022-02-17 | Solar | PV | 509.88 | 2025 | No
[7 empty] | 20INR0208 | Signal Solar | Hunt | 2025-03-15 | 2020-10-23 | Solar | PV | 51.79 | 2025 | Yes
[7 empty] | 24INR0093 | Oriana Solar | Victoria | 2025-04-06 | 2023-02-27 | Solar | PV | 181 | 2025 | Yes
[7 empty] | 21INR0393 | Orange Grove Solar | Jim Wells | 2025-04-30 | 2022-06-08 | Solar | PV | 130.6 | 2025 | Yes
[7 empty] | 23INR0021 | Hornet Solar | Swisher | 2025-04-30 | 2021-12-06 | Solar | PV | 602.37 | 2025 | Yes
[7 empty] | 24INR0031 | Stoneridge Solar | Milam | 2025-04-30 | 2023-05-15 | Solar | PV | 201.6 | 2025 | Yes
[7 empty] | 20INR0091 | Fagus Solar Park SLF | Childress | 2025-05-15 | 2019-02-21 | Solar | PV | 519.46 | 2025 | Yes
[7 empty] | 23INR0045 | GP Solar | Van Zandt | 2025-05-15 | 2021-12-29 | Solar | PV | 121.97 | 2025 | Yes
[7 empty] | 19INR0110 | Azalea Springs Solar | Angelina | 2025-05-31 | 2023-09-14 | Solar | PV | 181 | 2025 | Yes
[7 empty] | 23INR0058 | Erin Solar | Wharton | 2025-05-31 | 2023-03-22 | Solar | PV | 202.5 | 2025 | No
[7 empty] | 24INR0070 | Sypert Branch Solar Project | Milam | 2025-06-01 | 2023-10-12 | Solar | PV | 261.15 | 2025 | Yes
[7 empty] | 24INR0075 | Blue Bird Solar | Johnson | 2025-06-01 | 2024-01-18 | Solar | PV | 1004 | 2025 | No
[7 empty] | 24INR0166 | Stillhouse Solar | Bell | 2025-06-01 | 2023-06-07 | Solar | PV | 212.51 | 2025 | Yes
[7 empty] | 23INR0035 | Starling Solar | Gonzales | 2025-06-14 | 2021-12-03 | Solar | PV | 123 | 2025 | Yes
[7 empty] | 23INR0160 | Grimes County Solar | Grimes | 2025-06-15 | 2022-06-23 | Solar | PV | 210 | 2025 | Yes
[7 empty] | 21INR0344 | Lunis Creek Solar SLF | Jackson | 2025-07-01 | 2021-10-29 | Solar | PV | 617.12 | 2025 | Yes
[7 empty] | 23INR0118 | Blevins Solar | Falls | 2025-07-01 | 2023-06-17 | Solar | PV | 271.6 | 2025 | Yes
[7 empty] | 24INR0364 | Pitts Dudik II | Hill | 2025-07-01 | 2024-06-13 | Solar | PV | 30.23 | 2025 | No
[7 empty] | 23INR0040 | Dori BQ Solar | Harris | 2025-07-04 | 2022-12-01 | Solar | PV | 50.42 | 2025 | No
[7 empty] | 23INR0225 | MRG GOODY SOLAR | Lamar | 2025-07-07 | 2023-11-07 | Solar | PV | 171.72 | 2025 | No
[7 empty] | 24INR0141 | Gaia Solar | Navarro | 2025-07-31 | 2023-11-08 | Solar | PV | 152.65 | 2025 | Yes
[7 empty] | 20INR0222 | Tyson Nick Solar | Lamar | 2025-08-01 | 2020-08-28 | Solar | PV | 90.5 | 2025 | Yes
[7 empty] | 21INR0268 | Greyhound Solar | Ector | 2025-08-08 | 2022-01-15 | Solar | PV | 608.7 | 2025 | No
[7 empty] | 23INR0344 | XE Hermes Solar | Bell | 2025-08-25 | 2023-11-08 | Solar | PV | 100.36 | 2025 | Yes
[7 empty] | 23INR0349 | Tokio Solar | McLennan | 2025-08-25 | 2023-11-06 | Solar | PV | 175.72 | 2025 | Yes
[7 empty] | 23INR0056 | Caliche Mound Solar | Deaf Smith | 2025-08-28 | 2023-10-12 | Solar | PV | 408.21 | 2025 | Yes
[7 empty] | 24INR0139 | Midpoint Solar | Hill | 2025-08-30 | 2023-10-31 | Solar | PV | 99.8 | 2025 | Yes
[7 empty] | 24INR0303 | Erika Solar | Kaufman | 2025-08-31 | 2023-10-12 | Solar | PV | 204.08 | 2025 | No
[7 empty] | 23INR0061 | Noria Solar DCC | Nueces | 2025-09-01 | 2022-10-12 | Solar | PV | 145 | 2025 | Yes
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator | 23INR0367 | Fewell Solar | Limestone | 2025-09-09 | 2023-08-18 | Solar | PV | 203.5 | 2025 | Yes
2010 | 14.9 | 14.9 | 0 | 0 | 0 | 0 | 24INR0042 | Yaupon Solar SLF | Milam | 2025-09-17 | 2023-09-28 | Solar | PV | 204.08 | 2025 | Yes
2011 | 41.6 | 41.6 | 0 | 0 | 0 | 0 | 22INR0211 | Schoolhouse Solar | Lee | 2025-09-22 | 2021-07-11 | Solar | PV | 150.84 | 2025 | No
2012 | 72 | 72 | 0 | 0 | 0 | 0 | 20INR0236 | New Hickory Solar | Jackson | 2025-09-30 | 2020-06-30 | Solar | PV | 209.15 | 2025 | Yes
2013 | 121.18 | 121.18 | 0 | 0 | 0 | 0 | 23INR0235 | Hoyte Solar | Milam | 2025-09-30 | 2022-10-14 | Solar | PV | 206.75 | 2025 | Yes
2014 | 190.7 | 190.7 | 0 | 0 | 0 | 0 | 19INR0035 | Norton Solar | Runnels | 2025-10-01 | 2019-06-20 | Solar | PV | 125 | 2025 | Yes
2015 | 301.71 | 301.71 | 0 | 0 | 0 | 0 | 23INR0231 | Rocinante Solar | Gonzales | 2025-10-01 | 2022-04-25 | Solar | PV | 95 | 2025 | Yes
2016 | 698.22 | 698.22 | 0 | 0 | 0 | 0 | 21INR0421 | Armadillo Solar | Navarro | 2025-10-15 | 2021-02-02 | Solar | PV | 204 | 2025 | Yes
2017 | 1140.12 | 1140.12 | 0 | 0 | 0 | 0 | 24INR0010 | Pinnington Solar | Jack | 2025-10-15 | 2023-11-02 | Solar | PV | 666.1 | 2025 | Yes
2018 | 1909.16 | 1909.16 | 0 | 0 | 0 | 0 | 22INR0251 | Shaula I Solar | DeWitt | 2025-10-30 | 2022-02-16 | Solar | PV | 205.2 | 2025 | Yes
2019 | 2605.35 | 2605.35 | 0 | 0 | 0 | 0 | 24INR0206 | Glasgow Solar | Navarro | 2025-11-10 | 2023-11-08 | Solar | PV | 203.5 | 2025 | Yes
2020 | 6034.64 | 6034.64 | 0 | 0 | 0 | 0 | 20INR0203 | Pine Forest Solar | Hopkins | 2025-12-01 | 2020-07-29 | Solar | PV | 301.51 | 2025 | Yes
2021 | 10038.12 | 10038.12 | 0 | 0 | 0 | 0 | 20INR0242 | Anson Solar Center, Phase II | Jones | 2025-12-01 | 2024-05-15 | Solar | PV | 200.9 | 2025 | No
2022 | 14818.22 | 14818.22 | 0 | 0 | 0 | 0 | 21INR0391 | Grandslam Solar | Atascosa | 2025-12-01 | 2021-01-29 | Solar | PV | 121.89 | 2025 | No
2023 | 22153.33 | 22153.33 | 0 | 0 | 0 | 0 | 22INR0270 | Miller's Branch I | Haskell | 2025-12-01 | 2021-06-14 | Solar | PV | 200 | 2025 | Yes
2024 | 30069.06 | 25332.58 | 4531.28 | 205.2 | 0 | 0 | 22INR0559 | Honeycomb Solar | Bee | 2025-12-01 | 2023-05-01 | Solar | PV | 61.1 | 2025 | Yes
2025 | 45024.8 | 25332.58 | 15889.96 | 3802.26 | 0 | 0 | 22INR0454 | DR Solar | Culberson | 2025-12-15 | 2022-02-07 | Solar | PV | 36 | 2025 | Yes
2026 | 57130.37 | 25332.58 | 23946.87 | 7850.92 | 0 | 0 | 23INR0300 | Greater Bryant G Solar | Midland | 2025-12-15 | 2022-07-18 | Solar | PV | 17.7 | 2025 | No
2027 | 62675.7 | 25332.58 | 27025.77 | 10317.35 | 0 | 0 | 20INR0255 | Renegade Project | Deaf Smith | 2025-12-18 | 2021-01-04 | Solar | PV | 515.66 | 2025 | Yes
2028 | 63832.73 | 25332.58 | 27778.9 | 10721.25 | 0 | 0 | 22INR0342 | Matagorda Solar | Matagorda | 2025-12-27 | 2022-06-08 | Solar | PV | 101 | 2025 | No
[7 empty] | 16INR0049 | Nazareth Solar | Castro | 2025-12-31 | 2023-06-07 | Solar | PV | 204 | 2025 | Yes
[7 empty] | 19INR0042 | Long Point Solar | Brazoria | 2025-12-31 | 2019-10-24 | Solar | PV | 120 | 2025 | Yes
[7 empty] | 20INR0241 | Crowded Star Solar | Jones | 2025-12-31 | 2019-12-17 | Solar | PV | 218.79 | 2025 | Yes
[7 empty] | 21INR0274 | Carol Solar | Potter | 2025-12-31 | 2020-09-11 | Solar | PV | 223.2 | 2025 | No
[7 empty] | 22INR0261 | Dorado Solar | Callahan | 2025-12-31 | 2023-06-19 | Solar | PV | 401.35 | 2025 | Yes
[7 empty] | 23INR0249 | Limewood Solar | Bell | 2025-12-31 | 2023-02-22 | Solar | PV | 204.6 | 2025 | Yes
[7 empty] | 23INR0286 | Dry Creek Solar I | Rusk | 2026-01-01 | 2023-11-02 | Solar | PV | 202.54 | 2026 | Yes
[7 empty] | 24INR0477 | Barrett Solar | Rains | 2026-01-13 | 2023-10-05 | Solar | PV | 127.5 | 2026 | No
[7 empty] | 23INR0091 | Cascade Solar | Brazoria | 2026-01-16 | 2023-04-17 | Solar | PV | 254.2 | 2026 | Yes
[7 empty] | 22INR0274 | Crowded Star Solar II | Jones | 2026-01-26 | 2019-12-17 | Solar | PV | 190.18 | 2026 | No
[7 empty] | 21INR0428 | Nabatoto Solar North | Leon | 2026-02-01 | 2021-02-26 | Solar | PV | 450.7 | 2026 | Yes
[7 empty] | 21INR0253 | Ulysses Solar | Coke | 2026-02-23 | 2022-10-03 | Solar | PV | 150 | 2026 | Yes
[7 empty] | 22INR0262 | Deville Solar | Callahan | 2026-02-28 | 2023-08-29 | Solar | PV | 425.02 | 2026 | No
[7 empty] | 23INR0296 | Trojan Solar SLF | Cooke | 2026-02-28 | 2022-10-10 | Solar | PV | 0 | 2026 | Yes
[7 empty] | 21INR0207 | Quantum Solar | Haskell | 2026-03-31 | 2023-10-26 | Solar | PV | 374.4 | 2026 | Yes
[7 empty] | 23INR0031 | Solace Solar | Haskell | 2026-03-31 | 2024-01-30 | Solar | PV | 374.4 | 2026 | Yes
[7 empty] | 25INR0232 | Isaac Solar | Matagorda | 2026-03-31 | 2023-10-18 | Solar | PV | 51.6 | 2026 | Yes
[7 empty] | 20INR0035 | Angus Solar | Bosque | 2026-04-01 | 2021-12-06 | Solar | PV | 112 | 2026 | Yes
[7 empty] | 24INR0124 | High Noon Solar | Hill | 2026-04-01 | 2024-05-03 | Solar | PV | 182 | 2026 | Yes
[7 empty] | 21INR0362 | Oystercatcher Solar | Ellis | 2026-04-15 | 2021-08-20 | Solar | PV | 220.33 | 2026 | No
[7 empty] | 23INR0155 | Umbra (Stockyard) Solar | Franklin | 2026-04-16 | 2022-10-11 | Solar | PV | 207.84 | 2026 | No
[7 empty] | 19INR0103 | Rodeo Solar | Andrews | 2026-05-01 | 2019-08-20 | Solar | PV | 200 | 2026 | Yes
[7 empty] | 24INR0059 | Cuchillas Solar | Webb | 2026-05-01 | 2023-06-20 | Solar | PV | 305.6 | 2026 | Yes
[7 empty] | 23INR0093 | Alila Solar | San Patricio | 2026-05-15 | 2023-01-03 | Solar | PV | 256.5 | 2026 | Yes
[7 empty] | 24INR0106 | Payne Battlecreek | Hill | 2026-05-15 | 2024-02-23 | Solar | PV | 84.99 | 2026 | No
[7 empty] | 21INR0021 | Green Holly Solar | Dawson | 2026-05-30 | 2020-05-19 | Solar | PV | 413.6 | 2026 | No
[7 empty] | 21INR0022 | Red Holly Solar | Dawson | 2026-05-30 | 2020-10-19 | Solar | PV | 260 | 2026 | No
[7 empty] | 22INR0267 | Shaula II Solar | DeWitt | 2026-05-30 | 2022-04-27 | Solar | PV | 205.2 | 2026 | Yes
[7 empty] | 26INR0042 | Valhalla Solar | Brazoria | 2026-05-31 | 2023-12-06 | Solar | PV | 306.8 | 2026 | Yes
[7 empty] | 21INR0341 | Space City Solar | Wharton | 2026-06-01 | 2021-01-06 | Solar | PV | 609.74 | 2026 | Yes
[7 empty] | 24INR0038 | SP Jaguar Solar | McLennan | 2026-06-01 | 2022-09-12 | Solar | PV | 300 | 2026 | Yes
[7 empty] | 25INR0055 | Three W Solar | Hill | 2026-06-01 | 2023-03-28 | Solar | PV | 110.56 | 2026 | Yes
[7 empty] | 21INR0334 | Nightfall Solar SLF | Uvalde | 2026-06-30 | 2023-10-26 | Solar | PV | 181.16 | 2026 | Yes
[7 empty] | 24INR0337 | Eldora Solar | Matagorda | 2026-06-30 | 2023-11-15 | Solar | PV | 200.94 | 2026 | Yes
[7 empty] | 24INR0399 | Buzios Solar | Motley | 2026-06-30 | 2023-11-06 | Solar | PV | 253.46 | 2026 | Yes
[7 empty] | 25INR0105 | Diver Solar SLF | Limestone | 2026-06-30 | 2023-10-27 | Solar | PV | 225.59 | 2026 | Yes
[7 empty] | 25INR0060 | Argenta Solar | Bee | 2026-07-01 | 2024-04-05 | Solar | PV | 325 | 2026 | Yes
[7 empty] | 26INR0023 | Leon Solar Park | Leon | 2026-07-01 | 2024-05-21 | Solar | PV | 210.1 | 2026 | Yes
[7 empty] | 21INR0326 | Dove Run Solar | Duval | 2026-07-31 | 2023-10-31 | Solar | PV | 120.86 | 2026 | Yes
[7 empty] | 21INR0031 | Indigo Solar | Fisher | 2026-08-17 | 2022-09-15 | Solar | PV | 150 | 2026 | No
[7 empty] | 23INR0202 | Erath County Solar | Erath | 2026-08-27 | 2023-06-01 | Solar | PV | 207.4 | 2026 | Yes
[7 empty] | 25INR0109 | Sun Cactus Solar | Duval | 2026-08-31 | 2023-11-06 | Solar | PV | 120.63 | 2026 | Yes
[7 empty] | 23INR0289 | Skull Creek Solar | Anderson | 2026-09-16 | 2024-05-20 | Solar | PV | 137.26 | 2026 | No
[7 empty] | 23INR0207 | El Patrimonio Solar | Bexar | 2026-09-23 | 2023-12-11 | Solar | PV | 152.32 | 2026 | No
[7 empty] | 20INR0050 | Castro Solar | Castro | 2026-09-30 | 2020-11-30 | Solar | PV | 222.95 | 2026 | No
[7 empty] | 21INR0210 | Adamstown Solar | Wichita | 2026-09-30 | 2022-08-08 | Solar | PV | 251.28 | 2026 | No
[7 empty] | 22INR0279 | Clutch City Solar Phase I | Brazoria | 2026-10-01 | 2022-09-30 | Solar | PV | 200.75 | 2026 | No
[7 empty] | 24INR0298 | Leighton Solar SLF | Limestone | 2026-10-17 | 2024-05-28 | Solar | PV | 183 | 2026 | Yes
[7 empty] | 23INR0057 | Duffy Solar | Matagorda | 2026-11-01 | 2023-04-12 | Solar | PV | 545.21 | 2026 | Yes
[7 empty] | 21INR0520 | Viking Solar | Somervell | 2026-11-07 | 2022-10-25 | Solar | PV | 288.99 | 2026 | No
[7 empty] | 23INR0082 | Bottom Grass Solar | Colorado | 2026-12-01 | 2023-06-29 | Solar | PV | 508.61 | 2026 | No
[7 empty] | 23INR0385 | Camp Creek Solar SLF | Robertson | 2026-12-16 | 2023-07-15 | Solar | PV | 165.6 | 2026 | No
[7 empty] | 22INR0307 | Desert Vine Solar | Zapata | 2026-12-30 | 2022-12-16 | Solar | PV | 121.29 | 2026 | Yes
[7 empty] | 23INR0162 | Redonda Solar | Zapata | 2026-12-30 | 2021-12-28 | Solar | PV | 253.21 | 2026 | Yes
[7 empty] | 23INR0223 | Garcitas Creek Solar | Jackson | 2026-12-30 | 2022-06-30 | Solar | PV | 201.94 | 2026 | Yes
[7 empty] | 21INR0499 | Neptune Solar | Jackson | 2026-12-31 | 2000-05-30 | Solar | PV | 204.65 | 2026 | Yes
[7 empty] | 24INR0401 | Portside Energy Center (Solar) SLF | Victoria | 2026-12-31 | 2024-04-05 | Solar | PV | 41.44 | 2026 | No
[7 empty] | 25INR0052 | SanPat Solar 1 | San Patricio | 2026-12-31 | 2023-10-18 | Solar | PV | 256.23 | 2026 | Yes
[7 empty] | 23INR0030 | Langer Solar | Bosque | 2027-03-01 | 2023-08-31 | Solar | PV | 249.8 | 2027 | Yes
[7 empty] | 23INR0089 | Donegal Solar | Dickens | 2027-03-01 | 2022-07-25 | Solar | PV | 204.2 | 2027 | No
[7 empty] | 22INR0437 | TORMES SOLAR | Navarro | 2027-03-31 | 2024-04-10 | Solar | PV | 382.12 | 2027 | No
[7 empty] | 23INR0086 | Hanson Solar | Coleman | 2027-04-17 | 2023-09-20 | Solar | PV | 400.58 | 2027 | Yes
[7 empty] | 23INR0027 | Cachena Solar SLF | Wilson | 2027-04-29 | 2021-11-23 | Solar | PV | 600 | 2027 | Yes
[7 empty] | 22INR0281 | Pink Solar | Hunt | 2027-04-30 | 2022-08-30 | Solar | PV | 151.9 | 2027 | No
[7 empty] | 25INR0081 | SanPat Solar 2 | San Patricio | 2027-05-31 | 2023-10-18 | Solar | PV | 308.88 | 2027 | Yes
[7 empty] | 25INR0102 | Austin Bayou Solar | Brazoria | 2027-06-01 | 2023-11-15 | Solar | PV | 753.4 | 2027 | Yes
[7 empty] | 22INR0374 | Inertia Solar | Haskell | 2027-07-01 | 2021-05-04 | Solar | PV | 202.39 | 2027 | Yes
[7 empty] | 25INR0400 | Maldives Solar (Alternate POI) | Scurry | 2027-07-01 | 2023-12-01 | Solar | PV | 210 | 2027 | Yes
[7 empty] | 26INR0155 | Ross Solar | Refugio | 2027-07-31 | 2024-06-27 | Solar | PV | 1025.57 | 2027 | No
[7 empty] | 25INR0068 | High Chap Solar | Brazoria | 2027-08-04 | 2023-11-21 | Solar | PV | 152.25 | 2027 | Yes
[7 empty] | 25INR0080 | Meitner Solar | Gray | 2027-12-20 | 2024-01-31 | Solar | PV | 702.64 | 2027 | No
[7 empty] | 20INR0162 | Diamondback solar | Starr | 2027-12-31 | 2024-06-14 | Solar | PV | 201.6 | 2027 | Yes
[7 empty] | 22INR0257 | Corazon Solar Phase II | Webb | 2028-06-01 | 2020-08-04 | Solar | PV | 203.9 | 2028 | No
[7 empty] | 23INR0116 | Cantaloupe Solar | Reeves | 2028-07-01 | 2024-04-23 | Solar | PV | 303.13 | 2028 | Yes
[7 empty] | 24INR0258 | Zeissel Solar | Knox | 2028-07-01 | 2024-02-24 | Solar | PV | 450 | 2028 | Yes
[7 empty] | 21INR0226 | Equinox Solar 1 | Starr | 2028-12-30 | 2021-01-28 | Solar | PV | 200 | 2028 | No

## Battery Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 22INR0322 | Paleo BESS | Hale | 2024-08-09 | 2021-02-05 | Battery | BA | 200.8 | 2024 | Yes
[7 empty] | 25INR0328 | Longbow BESS | Brazoria | 2024-08-09 | 2023-07-18 | Battery | BA | 180.8 | 2024 | Yes
[7 empty] | 23INR0460 | PHOTON STORAGE | Wharton | 2024-08-13 | 2023-03-23 | Battery | BA | 305.48 | 2024 | Yes
[7 empty] | 23INR0403 | Connolly Storage | Wise | 2024-08-21 | 2023-02-27 | Battery | BA | 125.36 | 2024 | Yes
[7 empty] | 24INR0312 | Wigeon Whistle BESS | Collin | 2024-08-23 | 2022-12-08 | Battery | BA | 122.9 | 2024 | Yes
[7 empty] | 23INR0166 | Great Kiskadee Storage | Hidalgo | 2024-09-06 | 2022-06-30 | Battery | BA | 103.05 | 2024 | Yes
[7 empty] | 22INR0260 | Eliza Storage | Kaufman | 2024-09-27 | 2022-08-04 | Battery | BA | 100.4 | 2024 | Yes
[7 empty] | 24INR0147 | Holy ESS | Harris | 2024-09-28 | 2022-07-29 | Battery | BA | 209.32 | 2024 | Yes
[7 empty] | 24INR0629 | Jade Storage SLF | Scurry | 2024-09-30 | 2024-03-28 | Battery | BA | 0 | 2024 | Yes
[7 empty] | 24INR0630 | Andromeda Storage SLF | Scurry | 2024-09-30 | 2024-04-18 | Battery | BA | 0 | 2024 | Yes
[7 empty] | 20INR0246 | Ryan Energy Storage | Coryell | 2024-10-21 | 2021-02-18 | Battery | BA | 50 | 2024 | Yes
[7 empty] | 24INR0100 | Sheep Creek Storage | Callahan | 2024-10-31 | 2023-12-21 | Battery | BA | 142.1 | 2024 | Yes
[7 empty] | 22INR0353 | Carina BESS | Nueces | 2024-12-01 | 2021-08-03 | Battery | BA | 154.11 | 2024 | Yes
[7 empty] | 22INR0368 | Padua Grid BESS | Bexar | 2024-12-01 | 2021-11-16 | Battery | BA | 51.1 | 2024 | Yes
[7 empty] | 24INR0405 | Crowned Heron BESS | Fort Bend | 2024-12-15 | 2023-06-26 | Battery | BA | 154.2 | 2024 | Yes
[7 empty] | 24INR0265 | Jarvis BESS | Brazoria | 2024-12-23 | 2022-12-15 | Battery | BA | 308.4 | 2024 | Yes
[7 empty] | 22INR0349 | Antlia BESS | Val Verde | 2024-12-31 | 2021-06-05 | Battery | BA | 72.38 | 2024 | Yes
[7 empty] | 22INR0549 | Tanzanite Storage | Henderson | 2024-12-31 | 2022-07-15 | Battery | BA | 265.8 | 2024 | Yes
[7 empty] | 24INR0631 | Radian Storage SLF | Brown | 2024-12-31 | 2024-06-20 | Battery | BA | 0 | 2024 | Yes
[7 empty] | 23INR0419 | SOHO BESS | Brazoria | 2025-01-01 | 2022-12-01 | Battery | BA | 206.32 | 2025 | Yes
[7 empty] | 25INR0162 | SOHO II BESS | Brazoria | 2025-01-01 | 2023-04-15 | Battery | BA | 206.32 | 2025 | Yes
[7 empty] | 22INR0468 | Lower Rio BESS | Hidalgo | 2025-01-15 | 2023-07-10 | Battery | BA | 60.45 | 2025 | Yes
[7 empty] | 23INR0103 | Burksol BESS | Dickens | 2025-01-24 | 2022-11-17 | Battery | BA | 103.27 | 2025 | Yes
[7 empty] | 23INR0195 | Desert Willow BESS | Ellis | 2025-02-03 | 2023-05-15 | Battery | BA | 154.4 | 2025 | Yes
[7 empty] | 23INR0299 | Anole BESS | Dallas | 2025-02-09 | 2023-04-26 | Battery | BA | 247.1 | 2025 | Yes
[7 empty] | 22INR0417 | Amsterdam Storage | Brazoria | 2025-03-01 | 2022-04-14 | Battery | BA | 201.13 | 2025 | No
[7 empty] | 24INR0329 | XE Murat Storage | Harris | 2025-03-01 | 2023-11-01 | Battery | BA | 60.14 | 2025 | No
[7 empty] | 22INR0554 | Platinum Storage | Fannin | 2025-03-03 | 2022-11-17 | Battery | BA | 309.53 | 2025 | Yes
[7 empty] | 23INR0381 | Bexar ESS | Bexar | 2025-03-15 | 2023-07-31 | Battery | BA | 102.6 | 2025 | Yes
[7 empty] | 22INR0388 | Cachi BESS | Guadalupe | 2025-03-31 | 2021-06-11 | Battery | BA | 205.46 | 2025 | No
[7 empty] | 23INR0219 | Dogfish BESS | Pecos | 2025-04-16 | 2023-06-01 | Battery | BA | 77.4 | 2025 | Yes
[7 empty] | 23INR0287 | Avila BESS | Pecos | 2025-05-01 | 2023-02-06 | Battery | BA | 164.28 | 2025 | Yes
[7 empty] | 25INR0300 | Wizard BESS | Galveston | 2025-05-01 | 2023-08-21 | Battery | BA | 150.82 | 2025 | Yes
[7 empty] | 23INR0079 | Chillingham Storage | Bell | 2025-05-02 | 2022-02-04 | Battery | BA | 153.93 | 2025 | Yes
[7 empty] | 22INR0540 | Walstrom BESS | Austin | 2025-05-05 | 2023-06-30 | Battery | BA | 200 | 2025 | Yes
[7 empty] | 24INR0460 | Evelyn Battery Energy Storage System | Galveston | 2025-05-06 | 2023-09-14 | Battery | BA | 221.3 | 2025 | Yes
[7 empty] | 23INR0354 | Bordertown BESS | Starr | 2025-05-10 | 2022-10-12 | Battery | BA | 106.15 | 2025 | Yes
[7 empty] | 23INR0290 | Zeya BESS | Galveston | 2025-06-01 | 2023-01-20 | Battery | BA | 255.33 | 2025 | Yes
[7 empty] | 23INR0350 | Fort Duncan BESS | Maverick | 2025-06-01 | 2022-12-12 | Battery | BA | 106.15 | 2025 | Yes
[7 empty] | 23INR0358 | Castor BESS | Brazoria | 2025-06-01 | 2023-09-15 | Battery | BA | 205.39 | 2025 | Yes
[7 empty] | 24INR0128 | Desna BESS | Brazoria | 2025-06-01 | 2023-09-15 | Battery | BA | 205.46 | 2025 | Yes
[7 empty] | 25INR0467 | Bocanova BESS | Brazoria | 2025-06-01 | 2024-02-26 | Battery | BA | 300.92 | 2025 | Yes
[7 empty] | 23INR0401 | Headcamp BESS | Pecos | 2025-06-16 | 2024-02-16 | Battery | BA | 152.88 | 2025 | Yes
[7 empty] | 23INR0501 | Soda Lake BESS 1 | Crane | 2025-06-17 | 2018-08-20 | Battery | BA | 203.87 | 2025 | No
[7 empty] | 21INR0492 | Stockyard Grid Batt | Tarrant | 2025-06-30 | 2022-10-26 | Battery | BA | 150.6 | 2025 | Yes
[7 empty] | 24INR0039 | SP Jaguar BESS | McLennan | 2025-06-30 | 2022-09-12 | Battery | BA | 300 | 2025 | Yes
[7 empty] | 23INR0119 | Blevins Storage | Falls | 2025-07-01 | 2023-06-17 | Battery | BA | 181.3 | 2025 | Yes
[7 empty] | 24INR0568 | Shamrock Energy Storage (SLF) | Crockett | 2025-07-01 | 2022-05-11 | Battery | BA | 0 | 2025 | Yes
[7 empty] | 24INR0196 | Dori BQ BESS | Harris | 2025-07-04 | 2023-05-31 | Battery | BA | 154 | 2025 | No
[7 empty] | 21INR0443 | Cottonwood Bayou Storage | Brazoria | 2025-07-07 | 2022-03-18 | Battery | BA | 153.03 | 2025 | Yes
[7 empty] | 24INR0305 | MRG Goody Storage | Lamar | 2025-07-07 | 2023-11-07 | Battery | BA | 50.4 | 2025 | No
[7 empty] | 21INR0517 | Tidwell Prairie Storage 1 | Robertson | 2025-07-15 | 2022-11-03 | Battery | BA | 200 | 2025 | Yes
[7 empty] | 22INR0555 | TE Smith Storage | Rockwall | 2025-07-15 | 2023-11-08 | Battery | BA | 125.36 | 2025 | Yes
[7 empty] | 24INR0294 | Citrus Flatts BESS | Cameron | 2025-07-15 | 2023-09-08 | Battery | BA | 100.8 | 2025 | Yes
[7 empty] | 25INR0421 | Aldrin 138 BESS | Brazoria | 2025-07-15 | 2024-02-26 | Battery | BA | 207 | 2025 | Yes
[7 empty] | 23INR0343 | Guajillo Energy Storage | Webb | 2025-07-30 | 2021-12-21 | Battery | BA | 204.8 | 2025 | Yes
[7 empty] | 23INR0494 | Cartwheel BESS 1 | Hopkins | 2025-07-31 | 2023-11-10 | Battery | BA | 156.91 | 2025 | Yes
[7 empty] | 24INR0140 | Gaia Storage | Navarro | 2025-07-31 | 2023-11-08 | Battery | BA | 76.83 | 2025 | Yes
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator | 24INR0281 | Red Egret BESS | Galveston | 2025-08-01 | 2023-06-07 | Battery | BA | 310.58 | 2025 | Yes
2012 | 36 | 36 | 0 | 0 | 0 | 0 | 24INR0365 | XE Hermes Storage | Bell | 2025-08-25 | 2023-11-08 | Battery | BA | 100.42 | 2025 | Yes
2013 | 36 | 36 | 0 | 0 | 0 | 0 | 24INR0302 | Pintail Pass BESS | San Patricio | 2025-08-27 | 2023-05-16 | Battery | BA | 207.25 | 2025 | Yes
2014 | 36 | 36 | 0 | 0 | 0 | 0 | 24INR0138 | Midpoint Storage | Hill | 2025-08-30 | 2023-10-31 | Battery | BA | 51.26 | 2025 | Yes
2015 | 38 | 38 | 0 | 0 | 0 | 0 | 23INR0062 | Noria Storage | Nueces | 2025-09-01 | 2022-10-12 | Battery | BA | 75 | 2025 | Yes
2016 | 39 | 39 | 0 | 0 | 0 | 0 | 25INR0208 | Iron Belt Energy Storage | Borden | 2025-09-01 | 2023-01-16 | Battery | BA | 401.9 | 2025 | Yes
2017 | 92.3 | 92.3 | 0 | 0 | 0 | 0 | 25INR0389 | Stoneridge BESS | Milam | 2025-09-01 | 2024-04-19 | Battery | BA | 101.9 | 2025 | Yes
2018 | 103.7 | 103.7 | 0 | 0 | 0 | 0 | 24INR0169 | Yaupon Storage SLF | Milam | 2025-09-17 | 2023-09-28 | Battery | BA | 0 | 2025 | No
2019 | 153.3 | 153.3 | 0 | 0 | 0 | 0 | 25INR0262 | Shepard Energy Storage | Galveston | 2025-09-22 | 2024-01-17 | Battery | BA | 263.2 | 2025 | Yes
2020 | 275.4 | 275.4 | 0 | 0 | 0 | 0 | 23INR0232 | Rocinante BESS | Gonzales | 2025-10-01 | 2022-04-25 | Battery | BA | 33 | 2025 | Yes
2021 | 1306.53 | 1306.53 | 0 | 0 | 0 | 0 | 23INR0364 | Tierra Seca BESS | Val Verde | 2025-10-01 | 2023-05-18 | Battery | BA | 102.7 | 2025 | No
2022 | 2776.96 | 2776.96 | 0 | 0 | 0 | 0 | 24INR0295 | Lucky Bluff BESS SLF | Erath | 2025-10-15 | 2023-11-08 | Battery | BA | 100.8 | 2025 | Yes
2023 | 5100.07 | 5090.12 | 0 | 0 | 0 | 9.95 | 24INR0315 | Black Springs BESS SLF | Palo Pinto | 2025-10-15 | 2023-10-18 | Battery | BA | 120.96 | 2025 | Yes
2024 | 10441.38 | 7702.03 | 2546.2 | 0 | 0 | 193.15 | 24INR0057 | Hanson Storage | Coleman | 2025-10-21 | 2023-09-20 | Battery | BA | 101.39 | 2025 | No
2025 | 21728.01 | 7702.03 | 12324.35 | 1429.24 | 0 | 272.39 | 22INR0526 | Pine Forest BESS | Hopkins | 2025-10-29 | 2024-04-10 | Battery | BA | 210.05 | 2025 | Yes
2026 | 25095.9 | 7702.03 | 14160.95 | 2960.53 | 0 | 272.39 | 23INR0469 | Big Elm Storage | Bell | 2025-11-10 | 2024-05-10 | Battery | BA | 100.8 | 2025 | Yes
2027 | 26867.33 | 7702.03 | 15112.39 | 3780.52 | 0 | 272.39 | 24INR0207 | Glasgow Storage | Navarro | 2025-11-10 | 2023-11-08 | Battery | BA | 101 | 2025 | Yes
2028 | 27168.38 | 7702.03 | 15413.44 | 3780.52 | 0 | 272.39 | 21INR0444 | Long Point Storage | Brazoria | 2025-12-01 | 2023-08-28 | Battery | BA | 100.62 | 2025 | No
2029 | 27168.38 | 7702.03 | 15413.44 | 3780.52 | 0 | 272.39 | 22INR0552 | Sowers Storage | Kaufman | 2025-12-01 | 2022-04-22 | Battery | BA | 206.1 | 2025 | Yes
[7 empty] | 23INR0351 | Seven Flags BESS | Webb | 2025-12-01 | 2023-05-19 | Battery | BA | 102.7 | 2025 | Yes
[7 empty] | 23INR0392 | Honeycomb Storage SLF | Bee | 2025-12-01 | 2023-05-01 | Battery | BA | 0 | 2025 | Yes
[7 empty] | 24INR0491 | Gunnar BESS | Hidalgo | 2025-12-01 | 2023-09-22 | Battery | BA | 203 | 2025 | Yes
[7 empty] | 22INR0558 | Callisto II Energy Center | Harris | 2025-12-10 | 2023-12-11 | Battery | BA | 406.06 | 2025 | Yes
[7 empty] | 22INR0467 | Bird Dog BESS | Live Oak | 2025-12-11 | 2024-02-16 | Battery | BA | 60.4 | 2025 | Yes
[7 empty] | 23INR0336 | Bypass Battery Storage | Fort Bend | 2025-12-15 | 2023-12-04 | Battery | BA | 206.9 | 2025 | Yes
[7 empty] | 23INR0361 | Third Coast BESS | Jackson | 2025-12-15 | 2023-05-17 | Battery | BA | 102.84 | 2025 | Yes
[7 empty] | 21INR0505 | Ramsey Storage | Wharton | 2025-12-31 | 2022-08-11 | Battery | BA | 510.4 | 2025 | Yes
[7 empty] | 22INR0401 | Eval Storage | Cameron | 2025-12-31 | 2022-02-03 | Battery | BA | 255 | 2025 | Yes
[7 empty] | 24INR0472 | Amador Storage | Van Zandt | 2025-12-31 | 2023-11-02 | Battery | BA | 100.92 | 2025 | No
[7 empty] | 24INR0514 | Rogers Draw BESS | Gillespie | 2025-12-31 | 2024-02-28 | Battery | BA | 148.61 | 2025 | No
[7 empty] | 24INR0397 | Destiny Storage | Harris | 2026-01-31 | 2023-09-20 | Battery | BA | 201.11 | 2026 | Yes
[7 empty] | 24INR0275 | Picadillo BESS | Martin | 2026-02-15 | 2024-01-23 | Battery | BA | 100.83 | 2026 | No
[7 empty] | 25INR0329 | Project Lynx BESS | Nueces | 2026-03-14 | 2024-04-09 | Battery | BA | 262.09 | 2026 | Yes
[7 empty] | 25INR0131 | SOSA Storage | Madison | 2026-03-31 | 2023-12-05 | Battery | BA | 157.36 | 2026 | Yes
[7 empty] | 23INR0156 | Umbra (Stockyard) BESS | Franklin | 2026-04-16 | 2022-10-11 | Battery | BA | 72.98 | 2026 | No
[7 empty] | 23INR0340 | Larkspur Energy Storage | Upton | 2026-05-05 | 2022-02-28 | Battery | BA | 307.46 | 2026 | No
[7 empty] | 21INR0029 | Green Holly Storage | Dawson | 2026-05-30 | 2020-10-19 | Battery | BA | 50 | 2026 | No
[7 empty] | 21INR0033 | Red Holly Storage | Dawson | 2026-05-30 | 2020-10-19 | Battery | BA | 50 | 2026 | No
[7 empty] | 22INR0422 | Ferdinand Grid BESS | Bexar | 2026-05-31 | 2022-11-28 | Battery | BA | 201.2 | 2026 | Yes
[7 empty] | 24INR0436 | Carambola BESS | Hidalgo | 2026-05-31 | 2023-07-31 | Battery | BA | 97.43 | 2026 | Yes
[7 empty] | 26INR0034 | Bracero Pecan Storage | Reeves | 2026-06-01 | 2024-06-27 | Battery | BA | 232 | 2026 | No
[7 empty] | 24INR0109 | Oriana BESS | Victoria | 2026-06-15 | 2023-02-27 | Battery | BA | 60.3 | 2026 | Yes
[7 empty] | 24INR0338 | Eldora BESS | Matagorda | 2026-06-30 | 2023-11-15 | Battery | BA | 201.31 | 2026 | Yes
[7 empty] | 23INR0324 | Lumberjack Storage | Cherokee | 2026-07-01 | 2024-03-20 | Battery | BA | 51.3 | 2026 | No
[7 empty] | 25INR0061 | Argenta Storage | Bee | 2026-07-01 | 2024-04-05 | Battery | BA | 162 | 2026 | Yes
[7 empty] | 24INR0274 | Bufflehead BESS | Collin | 2026-07-06 | 2024-04-10 | Battery | BA | 100.8 | 2026 | No
[7 empty] | 25INR0100 | Goldeneye BESS | Bell | 2026-07-06 | 2024-02-26 | Battery | BA | 201.6 | 2026 | No
[7 empty] | 25INR0271 | City Breeze BESS | Matagorda | 2026-07-15 | 2024-05-15 | Battery | BA | 140.6 | 2026 | Yes
[7 empty] | 25INR0231 | Apache Hill BESS | Hood | 2026-11-15 | 2024-06-27 | Battery | BA | 201.2 | 2026 | Yes
[7 empty] | 23INR0083 | Bottom Grass BESS | Colorado | 2026-12-01 | 2023-06-29 | Battery | BA | 202.21 | 2026 | No
[7 empty] | 24INR0425 | Two Brothers Battery Energy Storage System | Victoria | 2026-12-01 | 2024-04-22 | Battery | BA | 152 | 2026 | Yes
[7 empty] | 23INR0423 | Camp Creek Storage SLF | Robertson | 2026-12-16 | 2023-07-15 | Battery | BA | 0 | 2026 | No
[7 empty] | 24INR0313 | Backbone Creek BESS | Burnet | 2026-12-26 | 2023-12-22 | Battery | BA | 120.69 | 2026 | No
[7 empty] | 24INR0403 | Portside Energy Center (BESS) SLF | Victoria | 2026-12-31 | 2024-04-05 | Battery | BA | 41.42 | 2026 | No
[7 empty] | 23INR0425 | Coneflower Storage Project | Chambers | 2027-02-03 | 2024-03-25 | Battery | BA | 178.92 | 2027 | Yes
[7 empty] | 23INR0331 | Orange Grove BESS | Jim Wells | 2027-04-30 | 2022-11-30 | Battery | BA | 61.39 | 2027 | Yes
[7 empty] | 24INR0395 | Berkman Storage | Galveston | 2027-04-30 | 2024-01-09 | Battery | BA | 150.86 | 2027 | Yes
[7 empty] | 25INR0160 | Canvasback BESS | Calhoun | 2027-06-15 | 2024-05-08 | Battery | BA | 150.5 | 2027 | Yes
[7 empty] | 22INR0375 | Inertia BESS 2 | Haskell | 2027-07-01 | 2021-05-04 | Battery | BA | 100.77 | 2027 | Yes
[7 empty] | 24INR0198 | Two Forks BESS | Cooke | 2027-07-01 | 2024-05-03 | Battery | BA | 309 | 2027 | Yes
[7 empty] | 26INR0156 | Ross Storage | Refugio | 2027-07-31 | 2024-06-27 | Battery | BA | 510.99 | 2027 | No
[7 empty] | 25INR0046 | Blue Skies BESS | Hill | 2027-12-31 | 2022-08-11 | Battery | BA | 309 | 2027 | No
[7 empty] | 23INR0117 | Cantaloupe Storage | Reeves | 2028-07-01 | 2024-04-23 | Battery | BA | 251.05 | 2028 | Yes
[7 empty] | 23INR0248 | Limewood Storage | Bell | 2028-12-29 | 2023-02-22 | Battery | BA | 50 | 2028 | Yes
[7 empty] | 24INR0259 | Zeissel Storage SLF | Knox | 2028-12-31 | 2024-02-24 | Battery | BA | 0 | 2028 | Yes
[7 empty] | Small Generators | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 22INR0590 | Muenster BESS | Cooke | 2024-12-31 | 2023-07-12 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 22INR0596 | Grizzly Ridge BESS | Hamilton | 2023-05-31 | 2021-10-18 | Battery | BA | 9.95 | 2023 | Yes
[7 empty] | 22INR0602 | Regis Palacios BESS | Matagorda | 2024-11-18 | 2022-10-07 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 23INR0499 | Laureles BESS | Cameron | 2024-11-05 | 2023-02-16 | Battery | BA | 9.8 | 2024 | Yes
[7 empty] | 23INR0500 | Fort Mason BESS | Mason | 2024-09-30 | 2023-01-10 | Battery | BA | 9.8 | 2024 | Yes
[7 empty] | 23INR0523 | Damon BESS | Brazoria | 2024-09-02 | 2022-10-18 | Battery | BA | 4.98 | 2024 | Yes
[7 empty] | 23INR0529 | Torrecillas BESS | Webb | 2024-12-31 | 2015-01-30 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 23INR0539 | Gregory BESS | San Patricio | 2024-11-11 | 2022-10-07 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 23INR0541 | Telview BESS | Fort Bend | 2024-05-31 | 2023-07-10 | Battery | BA | 9.96 | 2024 | Yes
[7 empty] | 23INR0556 | IEP Orchard BESS | Fort Bend | 2024-10-11 | 2023-08-09 | Battery | BA | 9.99 | 2024 | Yes
[7 empty] | 23INR0603 | Damon BESS 2 | Brazoria | 2025-03-12 | 2023-10-06 | Battery | BA | 9.99 | 2025 | Yes
[7 empty] | 23INR0617 | Hidden Lakes BESS | Galveston | 2025-01-22 | 2024-02-07 | Battery | BA | 9.9 | 2025 | Yes
[7 empty] | 23INR0618 | Farmersville West BESS 2 | Collin | 2025-01-22 | 2024-04-05 | Battery | BA | 9.9 | 2025 | Yes
[7 empty] | 23INR0619 | Junction North BESS | Kimble | 2025-01-22 | 2023-09-05 | Battery | BA | 9.9 | 2025 | Yes
[7 empty] | 23INR0807 | Mayberry II BESS | Hidalgo | 2024-12-07 | 2023-05-17 | Battery | BA | 9.95 | 2024 | Yes
[7 empty] | 24INR0499 | Medina Lake BESS | Bandera | 2024-08-31 | 2023-01-18 | Battery | BA | 9.8 | 2024 | Yes
[7 empty] | 24INR0545 | Spencer BESS | Harris | 2024-11-13 | 2023-10-31 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 24INR0546 | Crosby BESS | Harris | 2024-10-28 | 2023-10-31 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 24INR0547 | Angleton BESS | Brazoria | 2024-12-09 | 2023-10-31 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 24INR0591 | Citrus City BESS | Hidalgo | 2025-01-22 | 2024-02-02 | Battery | BA | 9.9 | 2025 | Yes
[7 empty] | 24INR0592 | Rio Grande City BESS 2 | Starr | 2025-01-22 | 2024-02-02 | Battery | BA | 9.9 | 2025 | Yes
[7 empty] | 24INR0593 | Falfur BESS | Brooks | 2025-02-15 | 2024-06-21 | Battery | BA | 9.8 | 2025 | Yes
[7 empty] | 24INR0610 | Century BESS | Tarrant | 2024-10-31 | 2023-04-14 | Battery | BA | 9.88 | 2024 | Yes
[7 empty] | 24INR0614 | Russek Street BESS | Reagan | 2024-08-09 | 2023-08-03 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 24INR0660 | Liggett Switch BESS | Dallas | 2024-11-30 | 2023-09-13 | Battery | BA | 9.95 | 2024 | Yes
[7 empty] | 24INR0688 | SANDLAKE BESS | Reeves | 2024-12-06 | 2024-03-26 | Battery | BA | 9.99 | 2024 | Yes
[7 empty] | 24INR0759 | Tynan BESS1 | Bee | 2024-11-27 | 2024-03-09 | Battery | BA | 9.9 | 2024 | Yes
[7 empty] | 25INR0642 | Crockett BESS1 | Harris | 2025-02-22 | 2023-10-10 | Battery | BA | 9.95 | 2025 | Yes

## Gas-Combined Cycle Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 22INR0533 | Temple Generation I Repower | Bell | 2022-06-09 | 2012-06-21 | Gas | CC | 67 | 2022 | Yes
[7 empty] | 23INR0524 | Temple II Repower | Bell | 2023-10-15 | 2012-06-21 | Gas | CC | 0 | 2023 | Yes
[7 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2024-06-30 | 2001-03-19 | Gas | CC | 21 | 2024 | Yes
[7 empty] | 23INR0029 | Cedar Bayou5 | Chambers | 2027-12-15 | 2022-01-10 | Gas | CC | 697 | 2027 | No
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
1999 | 6496.189 | 6496.189 | 0 | 0 | 0 | 0
2000 | 11480.519 | 11480.519 | 0 | 0 | 0 | 0
2001 | 18293.659 | 18293.659 | 0 | 0 | 0 | 0
2002 | 24571.899 | 24571.899 | 0 | 0 | 0 | 0
2003 | 30354.999 | 30354.999 | 0 | 0 | 0 | 0
2004 | 32385.519 | 32385.519 | 0 | 0 | 0 | 0
2005 | 32364.619 | 32364.619 | 0 | 0 | 0 | 0
2006 | 33068.819 | 33068.819 | 0 | 0 | 0 | 0
2007 | 33626.119 | 33626.119 | 0 | 0 | 0 | 0
2008 | 34187.219 | 34187.219 | 0 | 0 | 0 | 0
2009 | 35370.599 | 35370.599 | 0 | 0 | 0 | 0
2010 | 36830.799 | 36830.799 | 0 | 0 | 0 | 0
2011 | 37549.199 | 37549.199 | 0 | 0 | 0 | 0
2012 | 37549.199 | 37549.199 | 0 | 0 | 0 | 0
2013 | 37599.199 | 37599.199 | 0 | 0 | 0 | 0
2014 | 40330.999 | 40330.999 | 0 | 0 | 0 | 0
2015 | 41148.099 | 41148.099 | 0 | 0 | 0 | 0
2016 | 40749.109 | 40749.109 | 0 | 0 | 0 | 0
2017 | 42901.609 | 42901.609 | 0 | 0 | 0 | 0
2018 | 42901.609 | 42901.609 | 0 | 0 | 0 | 0
2019 | 43142.009 | 43142.009 | 0 | 0 | 0 | 0
2020 | 43142.009 | 43142.009 | 0 | 0 | 0 | 0
2021 | 43240.909 | 43240.909 | 0 | 0 | 0 | 0
2022 | 43240.909 | 43240.909 | 0 | 0 | 0 | 0
2023 | 43709.709 | 43709.709 | 0 | 0 | 0 | 0
2024 | 43797.709 | 43709.709 | 88 | 0 | 0 | 0
2025 | 43797.709 | 43709.709 | 88 | 0 | 0 | 0
2026 | 43797.709 | 43709.709 | 88 | 0 | 0 | 0
2027 | 44494.709 | 43709.709 | 88 | 697 | 0 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 24INR0605 | TEXAS GULF SULPHUR REPOWER | Wharton | 2024-06-25 | 2022-03-01 | Gas | GT | 16.1 | 2024 | Yes
[7 empty] | 23INR0506 | Beachwood II Power Station | Brazoria | 2024-08-25 | 2022-08-01 | Gas | GT | 102 | 2024 | Yes
[7 empty] | 24INR0736 | Remy Jade II Unit 7 Unit 8 Power Station | Harris | 2024-09-03 | 2022-08-01 | Gas | GT | 102 | 2024 | Yes
[7 empty] | 24INR0382 | Remy Jade II Power Station | Harris | 2025-07-30 | 2022-08-01 | Gas | GT | 102 | 2025 | No
[7 empty] | 26INR0049 | Calpine Freestone Peaker 1 | Freestone | 2026-05-01 | 2024-05-30 | Gas | GT | 228 | 2026 | Yes
[7 empty] | 26INR0109 | Calpine Freestone Peaker 2 | Freestone | 2026-05-01 | 2024-05-30 | Gas | GT | 228 | 2026 | Yes
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
1999 | 35219.87 | 35219.87 | 0 | 0 | 0 | 0
2000 | 35377.48 | 35377.48 | 0 | 0 | 0 | 0
2001 | 36091.14 | 36091.14 | 0 | 0 | 0 | 0
2002 | 36091.14 | 36091.14 | 0 | 0 | 0 | 0
2003 | 36039.14 | 36039.14 | 0 | 0 | 0 | 0
2004 | 34701.24 | 34701.24 | 0 | 0 | 0 | 0
2005 | 32803.04 | 32803.04 | 0 | 0 | 0 | 0
2006 | 32385.14 | 32385.14 | 0 | 0 | 0 | 0
2007 | 30659.14 | 30659.14 | 0 | 0 | 0 | 0
2008 | 30291.94 | 30291.94 | 0 | 0 | 0 | 0
2009 | 25769.37 | 25769.37 | 0 | 0 | 0 | 0
2010 | 23102.25 | 23102.25 | 0 | 0 | 0 | 0
2011 | 22745.55 | 22745.55 | 0 | 0 | 0 | 0
2012 | 23007.75 | 23007.75 | 0 | 0 | 0 | 0
2013 | 22564.91 | 22564.91 | 0 | 0 | 0 | 0
2014 | 22455.91 | 22455.91 | 0 | 0 | 0 | 0
2015 | 21077.11 | 21077.11 | 0 | 0 | 0 | 0
2016 | 22117.49 | 22117.49 | 0 | 0 | 0 | 0
2017 | 21812.63 | 21812.63 | 0 | 0 | 0 | 0
2018 | 22241.79 | 22241.79 | 0 | 0 | 0 | 0
2019 | 22136.49 | 22136.49 | 0 | 0 | 0 | 0
2020 | 22123.49 | 22123.49 | 0 | 0 | 0 | 0
2021 | 23065.69 | 23065.69 | 0 | 0 | 0 | 0
2022 | 23775.84 | 23775.84 | 0 | 0 | 0 | 0
2023 | 24331.04 | 24331.04 | 0 | 0 | 0 | 0
2024 | 25027.19 | 24795.49 | 220.1 | 0 | 11.6 | 0
2025 | 25129.19 | 24795.49 | 220.1 | 102 | 11.6 | 0
2026 | 25585.19 | 24795.49 | 676.1 | 102 | 11.6 | 0