## Sheet1
Market Coordination Meeting (MCT) and Texas SET Meeting Notes / Action Items
2024-03-04
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes March , 2024--MCT / TX SET
| No changes were made to the notes. | The Vice Chair will have these posted to the February meeting page.
ERCOT Updates
Market Test Flight 0224 | • ERCOT presented the flight update. • The current flight is running a little behind but should be wrapped up within the contingency period. • ERCOT shared that REPs can now sign up for registration of the Texas SET 5.0 flight, and encouraged any REP that has not signed up for Flightrak access to reach out to ERCOT so they can assist with having that completed.
Texas Set 5.0 MCT Updates | • Reviewed quick edits for Texas SET Business Requirements (version 2.8 now). • 867 Change Control to further define the different meter roles, ‘I” for the ignore meter role reports distributed generation, while “m” for the mobile meter role reports mobile generation. • Inserted IGL RMG Language • Added Functional Requirement for TDSPs to update an accounts Critical Care status after IAG is resolved via new transaction process. • Added new requirements around CR Communications, now indicating at least one communication type is required. • Added new requirements around state values now required to be capitalized “TX” not “Tx.”
Reviewed the DRAFT implementation plan for Texas SET 5.0. | • Discussed having CR’s update their systems so Saturday 11/09/24 during the SET 5.0 Conversion weekend will need to be blacked out as a holiday to ensure no registration orders get scheduled for that date. • There was discussion on handling orders submitted for conversion weekend, if a TDSP receives an order during the blackout period, the order will be moved to the following Monday 11/11/24. • CR’s will need to utilize the Safety Net process during the blackout period for MVI and RNP orders. • The group discussed the need for CR’s to stop sending DNP orders prior to conversion weekend to allow extra time for RNP orders to be processed. • The group discussed the amount of time ERCOT will need to perform system updates for SET 5.0, ERCOT is still reviewing. • A brief discussion around the contingency planning, which is the following weekend 11/15/24—11/17/24. If issues arise during conversion weekend the market will revert to SET 4.0A and plan to implement SET 5.0 the following weekend. • Market communications were lightly discussed and ERCOT advised they would send market notices once the conversion weekend had completed and CR’s could resume sending transactions.
Discussed the handling of IGL MarkeTrak issues that are in the middle of the process when we come to conversion weekend. | • ERCOT explained their review of this is still being tested to determine how best to handle and a further discussion will be held during the March TDTMS meeting. • MarkeTrak system will be down during the same window of time that ERCOT is down to update for SET 5.0. • Additional topics came up that will need to be further vetted, such as if the market should set a cutoff date for submitting new IGL issues? • If the number of pending MT issues should be discussed during ERCOT market calls on conversion weekend.
ERCOT WSDL API Update | • Still TBD, ERCOT is currently testing and would hope to have the updated WSDL available by Mid-September. TDSPs voiced needing it even earlier if possible as they will need to run tests for their system changes prior to conversion weekend.
ERCOT Documentation updates | • ERCOT is currently working on updating the MarkeTrak User Guides • Updated SET 5.0 transaction examples, Implementation Guide Redlines, and updated SEF Files can be found on the MCT page of ERCOT.
• Brief review of the process for updating the County Names in mass. • TDSPs will open a MarkeTrak issue with ERCOT and provide a test file to run in the RMTE around May 2024.
RMS Request: Texas SET 5.0 Production Go-Live Discussion
Texas SET Flight Test Certification Duration Discussion | ERCOT Legal is still reviewing possible language updates.
Next Meeting-- WebEx | 2024-04-09
Attendees F-T-F
Attendees Webex
Kyle Patrick - Reliant | Jordan Troublefield ERCOT | Tammy Stewart - ERCOT
Paula Shadle - NEC | Kathryn Thurman ERCOT | Vrushal Bonde - TNMP
Bill Snyder AEP | Kathy Scott Centerpoint Energy
Jeff Chen Centerpoint Energy | Angela Gromley - Calpine Corporation
Dee Lowerre Reliant | Mark Pepdjonovic ESG
Deb Belin Earth Etch | Angela Gromley - Calpine Corporation
Diana Rehfeldt TNMP | Frank Nunes - VertexOne
David Michelsen ERCOT | Tyler Krueger - BDE
Eric Lotter - Grid Monitor | Paul Yockey ERCOT
Gary Walcott - TNMP | Sam Pak ONCOR
Jesse Macias AEP | Sheri Wiegand Vistra
Joe Lindsay Systrends | Stephen Wilson TXU