## Sheet1
Market Coordination Meeting (MCT) and Texas SET Meeting Notes / Action Items
2024-04-09
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes April , 2024--MCT / TX SET
| No changes were made to the notes. | The Vice Chair will have the March Meeting Notes posted to the March meeting page.
ERCOT Updates
Market Test Flight 0224 | • ERCOT presented the flight update • ERCOT is nearly complete with Flight 0224, noting that only 1 CR is completing a bank transfer testing with 1 TDSP • ERCOT reviewed the upcoming schedule for Flight 0624 & Flight 0924 • Kathy Scott with CNP proposed that REPs should also blackout 11/08/24 in addition to 11/09/24 in preparation for Texas SET 5.0 Go-Live • Kathy with CNP brought up the need to take a final review of the Texas SET 5.0 test scripts to ensure the document is clear on what test scripts new CR’s will need to complete versus existing CR’s. Texas SET will add the topic to the May Agenda for review.
ERCOT WSDL API Update | • ERCOT and CNP met offline to discuss the timing for the updated WSDL to be provided • CNP indicated needing 6 weeks to test the updated WSDL on their side, so ERCOT would need it completed by the June/July timeframe • Dave Michelson with ERCOT shared he believed ERCOT should have a 90% complete WSDL to share by July • Dave also shared that any CR can set up a call to discuss the topic with ERCOT. Interested parties should email Dave Michelson or Tammy Stewart with ERCOT to set up a call
Texas SET Change Control Call
TXSETCC848: Update to ensure the State code is always Uppercase | Reviewed the final Approved Change Control document, appended with each applicable transaction's Implementation guide that has been updated
TXSETCC850: Update to the 824 Implementation Guide to align with current market processes | Reviewed the drafted chagne control & TX SET agreed to recommend to RMS to approve the Change Control.
Texas Set 5.0 MCT Updates
Texas SET Q&A Document Updates | • Item No.10 was added to the document to provide clarification around reprocessing transactions after Texas SET 5.0 goes live.
Transaction Names Inventory Lists | •Reviewed the Transaction Names Inventory Lists for Texas SET 5.0 updates.
Texas SET 5.0 Disucssion Items | • The working group discussed the operations and timing for using Safety Nets during the Go-Live weekend for Texas SET 5.0 implementation • NEC brought up the Veteran’s Day holiday around the SET 5.0 go-live date. No other TDSP has that holiday listed so should not be an issue • The working group also discussed TDSP CRIP availability for Safety Net operations during the Go-Live weekend. TDSPs to confirm their CRIP availability during the May Texas SET meeting • This aligned with the request for CR’s to black out 11/08, by starting the blackout period from the start of 11/08, in lieu of starting at 12pm Noon on 11/09, should allow more time for normal market operations • This would help with mitigating the risk of having a market participant send a transaction under the 4.0A SET format, then receiving a response transaction under the 5.0 SET format
RMS Request: Texas SET 5.0 Production Go-Live Discussion
Texas SET Flight Test Certification Duration Discussion | ERCOT Legal is still reviewing possible language updates.
Next Meeting-- WebEx | 2024-05-14
Attendees F-T-F
Attendees Webex
Kyle Patrick - Reliant | Jordan Troublefield ERCOT
Paula Shadle - NEC | Kathryn Thurman ERCOT
Bill Snyder AEP | Kathy Scott Centerpoint Energy
Jeff Chen Centerpoint Energy | Tammy Stewart - ERCOT
Kim Wall - Hansen Technologies | Darrell Miller - ESG
Deb Belin Earth Etch | Hhaas - IGS Energy
Diana Rehfeldt TNMP | Paul Yockey ERCOT
David Michelsen ERCOT | Sam Pak ONCOR
Eric Lotter - Grid Monitor | Sheri Wiegand Vistra
Rob Bevill - TNMP | Stephen Wilson TXU
Jesse Macias AEP