## Sheet1
Market Coordination Meeting (MCT) and Texas SET Meeting Notes / Action Items
2024-06-11
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes April, 2024--MCT / TX SET
| No changes were made to the notes. | The Vice Chair will have these posted to the February meeting page.
ERCOT Updates
Market Test Flight 0624/0924 | • ERCOT presented the flight update. • The current flight is going smoothly. • Discussions were held around what market participants need to test. ERCOT will be reaching out to REPs to ensure its known what DUNS/DUNS+4 setups will be required to test.
Texas SET 5.0 Test Script Review | • The Chair walked through the group through the test scripts required for flight 0924, SET 5.0. • The changes made to the ERCOT test scripts can be found on the log tab of the script pack. • ERCOT noted if REPS want to keep the CSA functionality, they will need to complete the CSA test script.
Texas Set 5.0 MCT Updates - Swimlane Review | • ERCOT walked the group through the swim lane documents for the updated CSA Add & new CSA Change market processes. • TDTMS Chair shared updates for the updated IGL process and walked through the different IGL scenario swim lane documents. • The group discussed the process for rejecting incorrectly sent BDMVI transactions, and whether ERCOT or the TDSPs would be the entity to reject the transaction. • The group determined it could be either depending on the issue causing the rejection. • Specifically, around date validations it was determined that ERCOT has not added any new validations for dates on BDMVI transactions with a “CR” or “IA” indicator, and the TDSPs might need to develop additional validations. • The working group agreed that REPs should be sending BDMVI for the agreed upon regain date so there are no issues.
Texas Set 5.0 MCT Updates - DDL Review | • ERCOT reviewed updated examples of the TDSP ESIID Extract and the Siebel Service Oder Extracts. • This provided context for REPs to understand where the county code fields will be listed. • There was a brief discussion of TDSP testing efforts for the county code updates in ERCOT systems. • The group also discussed how to resolve discrepancies in county code values. The group agreed that MarkeTrak would be the best tool to address such discrepancies(Service Address subtype was suggested).
Texas Set 5.0 Orientation Discussion | • Texas SET/MCT will hold a formal market call to review Texas SET 5.0 Implementation on 06/25/24 @ 9:30am. • The meeting will be held in person as well as Webex. • ERCOT will be taking attendance of all market participants to ensure all REPs are engaged and prepared for the Texas SET 5.0 Implementation. • The working group completed a draft of the agenda for the orientation meeting that will be distributed through the Texas SET ListServ.
RMS Request: Texas SET 5.0 Production Go-Live Discussion
Texas SET Flight Test Certification Duration Discussion | ERCOT Legal is still reviewing possible language updates.
Next Meeting-- WebEx | 2024-07-16
Attendees F-T-F
Attendees Webex
Kyle Patrick - Reliant | Jordan Troublefield ERCOT | Carolyn Reed - Centerpoint Energy
Paula Shadle - NEC | Kathryn Thurman ERCOT | Mark Pepdjonovic ESG
Bill Snyder AEP | Kathy Scott Centerpoint Energy | Frank Nunes - VertexOne
Jeff Chen Centerpoint Energy | Tammy Stewart - ERCOT | Joe Lindsay Systrends
Kim Wall - Hansen Technologies | Shanette | Juan Alegria - Champion Energy
Deb Belin Earth Etch | Laura Aldis | Lee D - Centerpoint Energy
Gary Walcott TNMP | Paul Yockey ERCOT | Melinda Earnest - AEP
David Michelsen ERCOT | Cindy Juarez | Monica Jones - Centerpoint Energy
Eric Lotter - Grid Monitor | Sheri Wiegand Vistra | Randi Flowers
Chris Dominguez | Stephen Wilson TXU | Rick Kalinowski - NRG
Jesse Macias AEP | Amy Sue Stirland - LPL | Will Faucher - TXU
Carrie - BDE | Angela Gromley - Calpine Corporation | Cassandra Jenkins - Centerpoint Energy
Bruce Grey | Leo Castillo - ERCOT | Lauren Lawder - Centerpoint Energy
John Schatz - Vistra | Sam Pak ONCOR | Steve Pliler - Vistra
Call In User 3 | Andrea Armistead | Debra
Elizabeth Baiza - LPL | Janet Gorman | Jaime Jaramillo - LPL
Myranda M. - LPL | Toni Bean | Tushar Thakar - Oracle
Viviana Valdez - LPL | Vrushal Bonde - TNMP | Candace Cox - NRG