| MarkeTrak Transition Plan November 2024 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sunday | Monday | Tuesday | Wednesday |  | Thursday | Friday | Saturday |  |
|  |  |  |  |  |  | 1 | 2 |  |
|  |  |  |  |  |  | Last Day for TDSP “Ready to Receive” |  |  |
| 3 | 4 | 5 | 6 |  | 7 | 8 | 9 |  |
|  | REPs to submit BDMVIs |  |  |  |  | TDSP Non-Business Day 12:00PM PM | TDSP Non-Business Day |  |
| 10 | 11 | 12 | 13 |  | 14 | 15 | 16 |  |
| TX SET 5.0 Go LIVE | MTs “sent to TDSP” without BDMVI will be returned to REPs to follow new workflow |  |  |  |  |  |  |  |
| 21 | 22 | 23 | 24 |  | 25 | 26 | 27 |  |
| 28 | 29 | 30 | 31 |  |  |  |  |  |

| FINAL Transition Plan TX SET V5.0 November 2024 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Tuesday November 5th | Wednesday November 6th | Thursday November 7th | Friday November 8th | Saturday November 9th | Sunday November 10th | Monday November 11th |
| 2:00 PM: Market Conference Call Confirm all MPs are ready to proceed with TX SET V5.0 implementation Required MP participation | 12:00 PM: CRs suspend sending 650_01 DNPs – any pending DNPs will be worked per DNP procedures 5:00 PM: TDSPs to cancel all pending 650_01 DNPs – TDSPs will complete unexecutable | 4:00 PM: Market Conference Call Confirm all DNPs are suspended Required TDSP participation | **TDSP Non-Business Day** Requested date for MVIs, MVOs, SWIs must be > 11/11/24 12:00 PM: CRs suspend sending all 814 transactions to ERCOT (EDI and MIS) CRs begin using Safety Net process for MVIs with requested dates of 11/8 and 11/9 and Reconnects for non-pay **Safety Nets are for emergency lights out only ** CRs suspend 814PCs CRs suspend all 650_01s TDSPs suspend 650_04s TDSPs suspend 814_20s 1:00 PM: TDSPs suspend 814 responses CRs suspend 824s TDSPs suspend 814PDs TDSPs suspend 650_02s TDSPs submit MarkeTrak to ERCOT with initial County load file 6:00 PM: Market Conference Call ERCOT confirms migration status & readiness Required MP participation | **TDSP Non-Business Day** Requested date for MVIs, MVOs, SWIs must be > 11/11/24 5:00 AM: TDSPs suspend 867s TDSPs suspend 810_02s (810_03MCs) CRs suspend 820_02s (820_03MCs) 6:00 AM: 997s suspended for all CRs begin using Safety Net process for MVIs with requested dates of 11/8 and 11/9 and Reconnects for non-pay **Safety Nets are for emergency lights out only ** 8:00 AM: ERCOT shuts down inbound and outbound processing and MarkeTrak ERCOT sends System Shutdown email to market 9:00 AM: Market Conference Call ERCOT confirms transaction suspension, update on processing Required MP participation 6:00 PM: Market Conference Call MP migration status Required MP participation | 10:00 AM: Market Conference Call MP migration status Confirm market readiness Required MP participation 5:00 PM: Market Conference Call MP migration status Confirm market readiness Required MP participation | 10:00 AM: Market Conference Call MP migration status Required MP participation |