## Slide 1: Lubbock Retail Integration Task Force – LRITF September 10th, 2024
Chris Rowley Michael Winegeart Sheri Wiegand

## Slide 2: LRITF meeting 8/6/24 & weekly market call update
The Task Force reviewed the following:
Decimals – Decimals are planned for 867s and 810s and will commence with 9/2 billing – up to 6 decimals could be received with typically 3-4 values – 6 places would indicate an estimated read. Sample test data revealed 2 decimal places on an 810_02 with rounding to occur on each cost recovery line item. Further discussions will be held on the absence of decimal language in the TXSET guides for certain QTY and MEA segments.
LSE files – LP&L indicated gap retrieval is in place, however, automated process to send reversioned files is still being tested. To ensure ERCOT has the latest interval data LP&L will be resending all LSE files for the months of March and April in time for final settlement as they work to finalize automated process.
SMT Readiness – LP&L has requested assistance from the TDUs to understand the REP’s data expectations/values, daily sync files, and any other relevant onboarding processes.

## Slide 3: Daily Market Calls Stabilization issues
The weekly market calls will be held on Thursdays @ 10:00 AM to discuss any on-going issues:
https://us06web.zoom.us/j/89361889543?pwd=olviNzrBXvZJHnEHKgOUZprYTpSDDV.1
Meeting ID: 893 6188 9543
Passcode: 112233
DNP 650_01 RCNs processing – REPs receiving ‘date in past’ rejections when transaction was submitted prior. ROL requests were being pushed two days out thus causing RCN to be received prior to DNP being completed. Temporary fix in place so RCNs are not rejected. Permanent fix to not push DNPs two days with ROL notation is still undergoing testing. It was discovered premium DNP and RCN charges were erroneously being sent for AMSR meters. LP&L will be sending out cancel/rebills.
867 IDR– LP&L continues to work with ESG to ensure transactions are submitted. LP&L is working with Oracle to ensure no overlapping dates occur.
Siebel Changes for Out of Sync conditions– ERCOT working with LP&L to ensure RORs are aligned in systems. LP&L has submitted ~19 MarkeTraks to correct the appropriate ROR and close out open enrollment requests.
BDMVIs submitted from transition until mid to late May – LP&L is unable to cancel an 810 for a BDMVI thus they are working to “credit note” the account ensure the REP receives the appropriate refund/credit.

## Slide 4: Daily Market Calls Stabilization issues- continued
810s received, Missing 867s – start/end reads on 867s were missing for some unmetered and metered situations. LP&L is in final stages of testing metered examples and working with Oracle for a solution. Unmetered cases should have received cancel/rebills.
810s with weekend due dates – LP&L has continued to not assess late fees until stabilization is nearly complete.
LOA Historical Usage Requests – LP&L has completed reformatting LOA requests to align with RMG.
650_01 Clearance Requests – LP&L has asked REPs to send disconnect and reconnect orders at least 15 minutes apart to prevent both orders from being submitted in the same batch thus unexecuting the reconnect. LP&L reports some REPs are continuing to submit in same batch.
814_20 ESI Maintenance- LP&L systems are unable to send an 814_20 to update the following: a premise to be reclassified from res vs non-res, address change, and meter type changes. Thus, REPs will need to send an MVI on a newly created ESI and a MVO on “old” ESI.

## Slide 5: Lessons learned
Customers with Multiple ESIs and DREP Process
TXSET Guides need updating
Need Regulatory/Legal decisions at beginning of project
Impact of Cycle Dates locked down and true MVI situations
Find a way to compare before defaulting – possibly provide customers with ESIs on their bundle bill prior to competition; create ESIs earlier in the process
We need to take some time and ensure we’ve captured the areas that need to be changed – ‘combo’ 814_05 kH vs KMON; Decimals; generalized practices - perhaps a ‘utility orientation’
Full awareness of any impacting legislation
Early conversations
LP&L has paved the way for additional MOU/ECs
Impacts stacking logic at go-live
Clear determination so REPs may design systems accordingly

## Slide 6: Lessons learned - continued
Phone Number formats & Country Code issue
Clean data for ESI creation
Addresses without descriptions
Decimals in meter reads
Update TXSET Guide
Avoid creation of ‘bad’ ESIs only to have to retire
Eliminates downstream confusion – customers, REPs
Understanding for Munis, other utilities may be associated
Systems should be able to use secondary address fields to help avoid inadvertent gain situations
With AMI being the standard meter type, this is an opportunity to allow decimals in meter reads. We are already using them in IDR situations

## Slide 7: Lessons learned - continued
Priority Codes for MVIs &Reconnects
TDSP Matrices in one location
Online enrollments – what options for multiple ESIs?
Cancel/rebill timing and LSE files
Should be included in the RMG along with other priority codes (service orders)
One place for: AMS Data Practices, Emergency Operating Plans, Solar Practices, Transaction Timelines
Including list in ERCOT opt-in checklist
Better customer experience if more than one ESI is to be enrolled
Providing a postcard to each customer with ESI information prior to sales window
This information is not captured in any protocols or guides at ERCOT… it is more of an ERCOT business process that impacts utilities processes. How can we capture for the next entrant? Opportunity to include in operating guide for settlements

## Slide 8: Lessons learned - continued
Full testing
Awareness of all files and extracts on ERCOT MIS
Shopping Fairs
Market Participants
Robust end to end testing with ‘real’ data including billing
Understanding of extracts available and purpose of data
WIN! Having a media market in a condensed geographical area resulted in effective communications to the residents
Providing questions for consideration – shopping guide and partnership with PUCT
Knowing the audience and conducting business/enrollments how the community wants to conduct business
Market participants were disengaged until the last minute
Requiring participation in the task force meeting if REP wants to become active in the territory

## Slide 9: Lessons learned - continued
EPS Meters
Understanding market processes
Understanding if territory has EPS meters, Muni will need to accept 867s from ERCOT
DCN/RCN processes and billing
ESI Maintenance and updating attributes
Understanding of the settlement differences of BUSIDRRQ, significance of LSE files and reversions, and impacts of cancel/rebills
ERCOT Settlement Process
Smart Meter Texas Onboarding
Expectations and requirements for integration
Updating Distribution Loss Factors
Calculation methodology, expectations and revisions

## Slide 10: TIMELINE of Actions
Q1 2023
Q2 2023
Q3 2023
Q4 2023
LP&L Rates
Customer Enrollment Process – Detailed Timeline
PUCT Complaint Process / Application of PUCT Rules
Transaction Timelines / TXSET Timelines
CSA Process
Mass Customer Lists
Power to Choose website
Customer Forums/Town Halls
Flight Testing / Bank Testing
CBCI files
Default REP Selection Process
DNP Blackout Period
Market Operations Group Established
GO LIVE – Transition to Competition
Q4 2022
Pro Forma Tariff
Access Agreement
POLR Process
Safety Net Process
Tampering Information Process
Smart Meter Texas
ESI IDs in TDSP Extract
RMG Chapter 8 Revisions
Historical Usage Requests
TDSP AMS Data Practices
ERCOT Activities: SAC04s, Load Profiles
TSDP Activities: Critical Care, DLFs, Solar/DG, Switch Hold Files, BUSIDDRQ, Call Center, OGFLT, Weather Moratoriums, Proration
March 2024
Completed
Q3 2023
Q4 2023
Q1 2024
Q4 2024 Q1 2025

## Slide 11: Lritf meeting 9/10/2024 @ 1:00PM following RMS – ERCOT Met Center (and via Webex)
AGENDA ITEMS:
Decimals
AMS Data Practices – Gap Retrieval & Updated LSE files
Stabilization
  650_01 RCN Processing
  DNP Discretionary Service Charges on 810s
  867_03 IDRs
  Seibel Changes with ERCOT
  BDMVIs and 810s
  810s received, missing 867s
    Missing start/end Reads
LOA Historical Usage Request - Format
814_20 ESI ID Maintenance
Updating DLFs
Open MarkeTraks
LP&L Weekly Market Calls
Lessons Learned
Open Discussion
  Pending LP&L Rate Case