## Slide 1
RTC+B Task Force
Update
Matt Mereness
TWG
December 19, 2024

## Slide 2
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox
Telemetry set-up and modeling
NEW

## Slide 3: January 14th RTCBTF Meeting

## Slide 4: Market Trial Handbooks
Link to TAC Approved Market Trials Plan (RTCBTF home page posting)
Soliciting public comment on Draft Market Trial Handbooks (posted Dec 11 RTCBTF)
    QSE Market Submissions (Handbook #1)
    QSE Telemetry Check-Out (Handbook #2)
All handbooks will reflect same weekly market trials call:
QSEs participate in weekly WebEx meetings (May 5- June 30)
  Every Monday 10am-10:30 am CPT (ahead of first meeting ERCOT will send reminders and post meeting on ERCOT calendar)
  Meeting agenda:
    Expectations of QSEs for the week
    Communicate any known issues with on-going trial
    Provide snapshot of cumulative QSE scorecards
    Support any technical and/or business questions

## Slide 5: Market Trial Handbooks
QSE Market Submissions (Handbook #1) – BACKGROUND INFO IN GREEN

## Slide 6: Market Trial Handbooks
QSE Market Submissions (Handbook #1) – TRIALS REQUIREMENTS IN RED

## Slide 7: Market Trial Handbooks
QSE Telemetry Check-Out (Handbook #2)

## Slide 8: Reminder
Thanks for the support and Technical feedback
Questions should be going through the RTCBTF in 2025
Next meeting is January 14, 2025 and reviewing Handbooks is part of discussion
  https://www.ercot.com/calendar/01142025-RTCBTF-Meeting