## Slide 1
RTC+B Task Force
Update
Matt Mereness
TWG
January 30, 2025

## Slide 2: Outline
Program update: RTC+B Program Update from Board T&S
Reminder of Scope of RTC+B Program (no change)
Current Issues for RTCBTF Review

## Slide 3: RTC+B Program Update (excerpt from December Board T&S RTC Update)

## Slide 4
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added to network model.
NEW

## Slide 5: Reminder of Details Scope of RTC+B Program (Excel version posted with meeting)
No change from
October 2024

## Slide 6: Meeting discussions
1. Antitrust Admonition (Matt Mereness)
2. RTCBTF Updates and Issues (Matt Mereness) - ADDED January 23 and Feb 7 afternoon meeting
3. Discussion of NPRR for RTC+B Parameters (ERCOT staff)
- Ramp Rate sharing (NPRR language)
- AS Proxy Offer Floor (NPRR language with more ASDC discussion)
- ASDC for RUC discussion (NPRR sections impacted and presentation)
- AS Duration Requirements (initial discussion)
4. Proposed changes for AS Qualification (Nitika Mago)
- Follow-up on discussion of IRR AS qualification
5. Review any Market feedback on Market Trials Handbooks (Matt Mereness)
- QSE Market Submissions (Handbook #1) – No comments received
- QSE Telemetry Check-Out (Handbook #2) – No comments received
6. Discussion of AS Demand Curves (Jonas Kersulis- IMM)
- ASDC sensitivity analysis for different ASDC proposals and draft NPRR
7. Refreshed RTC Efficiency Cost Savings (Matthew Schmidt)
- ERCOT study of annual RTC cost savings in 2023-2024
8. Other Business
- WMS question about WSL in Load Forecast (NPRR1253)

## Slide 7: Additional Meetings added Jan 23 and Feb 7 prior to Feb 19 meeting