## Slide 1
RTC+B Task Force
Update
Matt Mereness
RTCBTF
Feb 7, 2025

## Slide 2: Outline
Focused discussion today:
  Work on 3 NPRRs (NPRR1268, 1269, 12970)
    Review comments and presentations
  Verbal update on State of Charge AS Duration Discussion
  Market Readiness
    ESR Model names posted
    DAM ESR “training”
    IT Updates to TWG

## Slide 3: RTCBTF Issues List
First red box is NPRR1269 for 3 policy issues
Second red box is IMM NPRR1268 for ASDC changes
Third red box is a clean-up NPRR1270 and remove automatic qualification
Still need evaluation of State of Charge and AS Duration
Market Trials

## Slide 4
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.

## Slide 5: Summary and Timeline of NPRRs that will be in flight
NPRR1268 for ASDC Modifications (IMM sponsor)
NPRR1269 for Parameter/Policy Changes (ERCOT sponsor)
  AS Proxy Offer Floors - ASDCs for Reliability Unit Commitment
  Ramp Rate Sharing - AS Duration Requirements (ie, State of Charge)
NPRR1270 for AS Qualification details (ERCOT sponsor)
State of Charge – TBD but target July Board
Timeline and vetting of RTC+B NPRRs
Jan 2025
Feb 2025
Mar 2025
Apr 2025
May 2025
June 2025
File NPRRs
(No impacts) Jan 28
PRS Urgency & Table NPRRs
Feb 12
PRS Approval March 12
TAC approval
March 26
Board Approval
April 8
PUCT Approval
May 15
RTCBTF: Jan 23, Feb 19, add 1-2 meetings
Stakeholder comments in Feb and March
ERCOT window for “re-factoring” development
ERCOT market trials deployed and begin on May 5, 2025

## Slide 6: RTCBTF Discussion today
Discussion of NPRR 1268- IMM Modifications to ASDCs / IMM staff
a. Hunt Energy Comments 1/30/25
b. IMM filed comments 2/5/25
c. ERCOT verbal discussion to remove 100 point requirement on ASDC
Discussion of NPRR 1269- ERCOT 3 Parameter Policy issues / ERCOT staff
a. AS Proxy Offer Floor
- IMM comments filed 2/6/25
b. RUC ASDC
- ERCOT to share analysis in presentation
c. Ramp sharing
Discussion of NPRR 1270 Clarification and AS Qualification / Nitika Mago
Verbal update on State of Charge and AS Duration next steps / Nitika Mago
Market Readiness / ERCOT Staff
a. ESR Model naming convention and post spreadsheet
b. DAM ESR Offers
c. IT updates from TWG 1/30/25 (RTC Digital Certs and ICCP requests)
Potential extra meeting- Friday March 7 (before March 12 PRS meeting)

## Slide 7: Discuss Feb 19th RTCBTF Meeting
Market Trials