## Slide 1
Project Update
February 27, 2025
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
    SCR820 Update
  2025 Release Targets
  Major Projects
  2022-2024 Impact Analysis Accuracy Results
  Priority/Rank Recommendations for Revision Requests with Impacts
    VCMRR042 – SO2 and NOx Emission Index Prices Used in Verifiable Cost Calculations
    Additional time needed to complete IAs
      SCR829 – API for the NDCRC Application
      SCR830 – Expose Limited API Endpoints Using Machine-to-Machine Authentication
  Technology Working Group (TWG)
    Next meeting is 2/27/2025
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2025 January Off-Cycle Release – 1/1/2025 Complete
  NPRR1219 – Methodology Revisions and New Definitions for the Report on Capacity, Demand and Reserves in the ERCOT Region (CDR)
2025 January Release – 1/30/2025 Complete
  NPRR945 – Net Metering Requirements
2025 March Release – 3/28/2025 In Flight
  NPRR1145 – Use of State Estimator-Calculated ERCOT-Wide TLFs in Lieu of Seasonal Base Case ERCOT-Wide TLFs for Settlement
  NPRR1253(a) – Incorporate ESR Charging Load Information into ICCP
    ICCP implementation in March 2025 release (Public API implementation to follow by 6/1/2025)
SCR820 – Operator Real-Time Messaging During Emergency
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.
Update from 1/30/2025 TWG Meeting

## Slide 4: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 |  | NPRR1145 NPRR1253(a) | RTC+B Market Trials begin on 5/5/2025 | NPRR1253(b) | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
 |  |  |  |  | RTC+B Stabilization begins
R7
R8
R10
R11
E
NS
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR965
NPRR1000
NPRR1014
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216
NPRR1236
NPRR1245
NPRR1246
NOGRR211
NOGRR268
OBDRR020
OBDRR052
PGRR118
E
NPRR963(a) – Portion of NPRR
NPRR1253(a) – ICCP
NPRR1253(b) – Public API
ü
ü
1/1
NS

## Slide 5: Major Projects
Other Project Highlights

## Slide 6: Variance from IA Cost Range – Revision Request Projects
10
Exceeds IA Range
12 Projects
Below IA Range
2 Projects
Within IA Range
15 Projects
If actual spend falls within the IA range the variance is 0
Actual $ Variance from IA Range
2022
11 Projects
23 Revision Requests
2023
7 Projects
12 Revision Requests
2024
11 Projects
18 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
4
5
6
7
8
9
11
12
13
14
15
16
17
18
20
27
22
23
24
25
26
3
2
28
29
21
19
Chart: 
| NPRR863 FFR Advancement | DGR DESR Implementation Strategy | NPRR939 Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During S | MarkeTrak Upgrade & Enhancements | Securitization - Subchapter N | SCR800 and SCR809 Implementation | NPRR1093 Load Resource Participation in Non-Spinning Reserve | NPRR1108 ERCOT Shall Approve or Deny All Resource Outage Requests | NPRR1120 Create Firm Fuel Supply Service | NPRR1097 Create Resource Forced Outage Report | SCR812 Create Intermittent Renewable Generation Integration Report | Creation of ERCOT Contingency Reserve Service (ECRS) | SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2 | NPRR1020 - EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | SCR807 and SCR816 implementation | Securitization Phase 2A- Maine Invoice and Credit Exposure | NPRR1154 Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | SCR822 Create Daily Energy Storage Integration Report and Dashboard | NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility | SCR819 Improving IRR Control to Manage GTC Stability Limits | NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | NERC FAC Standard Changes Alignment | NPRR1149, NPRR1121, NPRR1090, NPRR962 | Implement consideration of ESR SOC in ERCOT tools and studies | NPRR1026 BESTF-7 Self-Limiting Facilities | RIOO-IS_RS ESR-Single Model & Validation Rules Update | NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs | NPRR1131 Controllable Load Resource Participation in Non-Spin | NPRR1183 ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without
Cost Variance % | 0.20272 | 0 | 0 | 0 | 0 | 0 | 0 | -0.42237 | 0 | 0.34445 | 0 | 0.62013 | -0.23501 | 0.070893 | 1.23 | 0 | 0 | 0.033856 | 5.3047 | 0.14037 | 0.14493 | 0.27735 | 0.40609 | 0 | 0.19879 | 0 | 0 | 0 | 0
Source
Market
ERCOT

## Slide 7: Variance from IA Duration Range – Revision Request Projects
12
Exceeds IA Range
10 Projects
Below IA Range
8 Projects
Within IA Range
11 Projects
2022
11 Projects
23 Revision Requests
2023
7 Projects
12 Revision Requests
2024
11 Projects
18 Revision Requests
If actual duration falls within the IA range the variance is 0.
Note: Graph compares the posted IA duration range with the actual project duration
Number of Months from IA Range
1
2
3
4
5
6
8
9
10
11
13
14
15
16
17
18
19
20
21
22
23
24
27
7
25
26
28
29
Chart: 
| NPRR863 FFR Advancement | DGR DESR Implementation Strategy | NPRR939 Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During S | MarkeTrak Upgrade & Enhancements | Securitization - Subchapter N | SCR800 and SCR809 Implementation | NPRR1093 Load Resource Participation in Non-Spinning Reserve | NPRR1108 ERCOT Shall Approve or Deny All Resource Outage Requests | NPRR1120 Create Firm Fuel Supply Service | NPRR1097 Create Resource Forced Outage Report | SCR812 Create Intermittent Renewable Generation Integration Report | Creation of ERCOT Contingency Reserve Service (ECRS) | SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2 | NPRR1020 - EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | SCR807 and SCR816 implementation | Securitization Phase 2A- Maine Invoice and Credit Exposure | NPRR1154 Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | SCR822 Create Daily Energy Storage Integration Report and Dashboard | NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility | SCR819 Improving IRR Control to Manage GTC Stability Limits | NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | NERC FAC Standard Changes Alignment | NPRR1149, NPRR1121, NPRR1090, NPRR962 | Implement consideration of ESR SOC in ERCOT tools and studies | NPRR1026 BESTF-7 Self-Limiting Facilities | RIOO-IS_RS ESR-Single Model & Validation Rules Update | NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs | NPRR1131 Controllable Load Resource Participation in Non-Spin | NPRR1183 ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without
Duration Variance (%) | 0.3341 | -0.099642 | 0.00028177 | 0 | -0.064943 | 0 | -0.23734 | -0.017916 | -0.17452 | 0.045365 | -0.092702 | 0 | 0 | 0 | 0.17521 | 0 | 0 | 0 | 2.8856 | 0 | 0.29849 | 0.098901 | 0 | 0.15713 | 0.10536 | 0.068376 | -0.32062 | -0.21652 | 0.0081087
Source
Market
ERCOT

## Slide 8: Variance from IA Cost Range – Revision Request Projects
10
Exceeds IA Range
12 Projects
Below IA Range
2 Projects
Within IA Range
15 Projects
If actual spend falls within the IA range the variance is 0
Actual $ Variance from IA Range
2022
11 Projects
23 Revision Requests
2023
7 Projects
12 Revision Requests
2024
11 Projects
18 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
4
5
6
7
8
9
11
12
13
14
15
16
17
18
20
27
22
23
24
25
26
3
2
28
29
21
19
Chart: 
| DGR DESR Implementation Strategy | NPRR939 Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During S | MarkeTrak Upgrade & Enhancements | Securitization - Subchapter N | SCR800 and SCR809 Implementation | NPRR1093 Load Resource Participation in Non-Spinning Reserve | NPRR1108 ERCOT Shall Approve or Deny All Resource Outage Requests | NPRR1120 Create Firm Fuel Supply Service | NPRR1097 Create Resource Forced Outage Report | SCR812 Create Intermittent Renewable Generation Integration Report | SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2 | NPRR1020 - EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | SCR807 and SCR816 implementation | Securitization Phase 2A- Maine Invoice and Credit Exposure | NPRR1154 Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | SCR822 Create Daily Energy Storage Integration Report and Dashboard | NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility | SCR819 Improving IRR Control to Manage GTC Stability Limits | NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | NERC FAC Standard Changes Alignment | NPRR1149, NPRR1121, NPRR1090, NPRR962 | Implement consideration of ESR SOC in ERCOT tools and studies | NPRR1026 BESTF-7 Self-Limiting Facilities | RIOO-IS_RS ESR-Single Model & Validation Rules Update | NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs | NPRR1131 Controllable Load Resource Participation in Non-Spin | NPRR1183 ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without
Cost Variance ($) | 0 | 0 | 0 | 0 | 0 | 0 | -126711 | 0 | 13778 | 0 | -129253 | 15951 | 221405 | 0 | 0 | 3047 | 159142 | 8422 | 10870 | 41602 | 105584 | 0 | 39758 | 0 | 0 | 0 | 0
Source
Market
ERCOT

## Slide 9: Variance from IA Duration Range – Revision Request Projects
10
Exceeds IA Range
9 Projects
Below IA Range
8 Projects
Within IA Range
12 Projects
If actual spend falls within the IA range the variance is 0
2022
11 Projects
23 Revision Requests
2023
7 Projects
12 Revision Requests
2024
11 Projects
18 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
4
5
6
7
8
9
11
12
13
14
15
16
17
18
20
27
22
23
24
25
26
3
2
28
29
21
19
Number of Months from IA Range
Chart: 
| NPRR863 FFR Advancement | DGR DESR Implementation Strategy | NPRR939 Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During S | MarkeTrak Upgrade & Enhancements | Securitization - Subchapter N | SCR800 and SCR809 Implementation | NPRR1093 Load Resource Participation in Non-Spinning Reserve | NPRR1108 ERCOT Shall Approve or Deny All Resource Outage Requests | NPRR1120 Create Firm Fuel Supply Service | NPRR1097 Create Resource Forced Outage Report | SCR812 Create Intermittent Renewable Generation Integration Report | Creation of ERCOT Contingency Reserve Service (ECRS) | SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2 | NPRR1020 - EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | SCR807 and SCR816 implementation | Securitization Phase 2A- Maine Invoice and Credit Exposure | NPRR1154 Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | SCR822 Create Daily Energy Storage Integration Report and Dashboard | NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility | SCR819 Improving IRR Control to Manage GTC Stability Limits | NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | NERC FAC Standard Changes Alignment | NPRR1149, NPRR1121, NPRR1090, NPRR962 | Implement consideration of ESR SOC in ERCOT tools and studies | NPRR1026 BESTF-7 Self-Limiting Facilities | RIOO-IS_RS ESR-Single Model & Validation Rules Update | NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs | NPRR1131 Controllable Load Resource Participation in Non-Spin | NPRR1183 ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without
Duration Variance (Mo.) | 8.0184 | -1.7936 | 0.0019724 | 0 | -0.58448 | 0 | -2.3734 | -0.14333 | -1.5707 | 0.22682 | -0.46351 | 0 | 0 | 0 | 2.1026 | 0 | 0 | 0 | 14.428 | 0 | 1.7909 | 0.69231 | 0 | 1.5713 | 0.84287 | 0.82051 | -0.96187 | -1.2991 | 0.048652
Source
Market
ERCOT

## Slide 10: Revision Request Project Legend
NPRR863, NPRR1015, NPRR1079, NOGRR187, FFR Advancement
NPRR917, NPRR1016, NPRR1052, NPRR1065, NOGRR212, PGRR082, RRGRR026, DGR DESR Implementation Strategy
NPRR939, Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
SCR815, MarkeTrak Upgrade & Enhancements
NPRR1103, NPRR1114, Securitization Phase 2A - Maine Invoice and Credit Exposure
SCR800, SCR809, Addition of DC Tie Ramp to GTBD Calculation and Changes to External Telemetry Validations in Resource Limit Calculator
NPRR1093, NPRR1101, Load Resource Participation in Non-Spinning Reserve and Non-Spin Deployment Groups
NPRR1108, ERCOT Shall Approve or Deny All Resource Outage Requests
NPRR1120, Create Firm Fuel Supply Service
NPRR1097, Create Resource Forced Outage Report
SCR812, Create Intermittent Renewable Generation Integration Report
NPRR863, NPRR1085, NPRR1096, NPRR1148, Creation of ERCOT Contingency Reserve Service (ECRS)
SCR789, Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2
NPRR1020, EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads
SCR807, SCR816, Increase CRR Transaction Capability and CRR Auction Bid Credit Enhancement
NPRR1103, NPRR1114, Securitization Phase 2A - Maine Invoice and Credit Exposure
NPRR1154, Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service
SCR822 Create Daily Energy Storage Integration Report and Dashboard
NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility
SCR819, NPRR1111, Improving IRR Control to Manage GTC Stability Limits
NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision
NOGRR249, NERC FAC Standard Changes Alignment
NPRR1149, NPRR1121, NPRR1090, NPRR962, Implementation of Systematic Ancillary Service Failed Quantity Charges, Add Posting Requirement to the Exceptional Fuel Cost Submission Process, ERS Winter Storm Uri Lessons Learned, and Publish Approved DC Tie Schedules
NPRR1186, Implement Consideration of ESR SOC in ERCOT Tools and Studies
NPRR1026 BESTF-7 Self-Limiting Facilities
NPRR1002, NPRR1132, NPRR1153, RIOO-IS_RS ESR-Single Model & Validation Rules Update
NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs
NPRR1131, NPRR1058, Controllable Load Resource Participation in Non-Spin and Resource Offer Modernization
NPRR1183 ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without ECEII

## Slide 11: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
VCMRR042 | SO2 and NOx Emission Index Prices Used in Verifiable Cost Calculations | 2026 | 4720 | $90k-$140k, 6-8 months Impacted Systems: Settlements, Integration Post-RTC+B candidate – discussed at WMS
SCR829 | API for the NDCRC Application | TBD | TBD | Additional time needed to complete IA
SCR830 | Expose Limited API Endpoints Using Machine-to-Machine Authentication | TBD | TBD | Additional time needed to complete IA
Recommendations for…
PPL Rank Information
Next available 2025 Rank in Business Strategy = 4560
Next available 2026 Rank in Business Strategy = 4720
Next available Rank in Regulatory = 400

## Slide 12: Technology Working Group (TWG)
Agenda for TWG meeting held on 1/30/2025:
Next TWG scheduled for 2/27/2025