## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
February 27, 2025

## Slide 2: Outline
Upcoming implementation milestones
Current Issues and Schedule for RTCBTF
Disposition of three NPRRs for consideration at next TAC meeting

## Slide 3
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added to network model.
Connectivity testing begins in 2 weeks, QSE Trials in 10 weeks

## Slide 4: Reminder of Details Scope of RTC+B Program
No change from
October 2024
Note that NPRRs 1268, 1269,1270 will be added after approval but have no QSE system impacts.

## Slide 5: RTCBTF Issues List
First red box is NPRR1269 for 3 policy issues (target April Board)
Second red box is IMM NPRR1268 for ASDC changes (target April Board)
Third red box is a clean-up NPRR1270 and remove automatic qualification (target April Board)
Still need evaluation of State of Charge and AS Duration (target June Board)
Market Trials

## Slide 6: RTCBTF Key Discussions 1/23/2025, 2/7/2025, 2/19/2025
Market Readiness / ERCOT Staff
a. Completed review of Handbook #1- QSE Market Submission
b. Completed review of Handbook #2- QSE Telemetry Check-Out
c. Initial Review of Handbook #3 – Open Loop SCED
d. Initial Review of Handbook #4 – QSE Telemetry Tests
e. Draft Operator Training Seminar slides (work-in-progress)
f. Added RTC+B Telemetry Changes Training Video to training library
Discussion of NPRR 1268- IMM Modifications to ASDCs / IMM staff
Discussion of NPRR 1269- ERCOT 3 Parameter Policy issues / ERCOT staff
Discussion of NPRR 1270- Clarification and AS Qualification / Nitika Mago
State of Charge / AS Duration de-coupled for analysis and target June Board
Jan 2025
Feb 2025
Mar 2025
Apr 2025
May 2025
June 2025
File NPRRs
(No impacts) Jan 28
PRS Table NPRRs
Feb 12
PRS Urgency & Apprv 3/12
TAC approval
March 26
Board Approval
April 8
PUCT Approval
May 15
RTCBTF: Jan 14, 23, Feb 7,19, March 5, 25
Stakeholder comments in Feb and March
ERCOT window for “re-factoring” development
ERCOT market trials deployed and begin on May 5, 2025

## Slide 7: Disposition of NPRRs at RTCBTF needed at April Board
NPRR1268: IMM Modifications to ASDC
General RTCBTF consensus for:
  IMM-Modified-Blended ASDCs as reflected by:
    Original NPRR1268
    Plus IMM clarifying comments on Feb 5
    Plus ERCOT comments filed Feb 19 (on top of Feb 5 IMM) to cap DAM AS Prices (to match RTM) and remove 100-point curve requirement.
Non-consensus item:
  Hunt Energy comments were filed Jan 30th proposing realignment of AORDC. After two meetings, stakeholders leaning toward being a separate NPRR with broader scope for AODRC/ASDC issues.

## Slide 8: Disposition of NPRRs at RTCBTF needed at April Board
NPRR1269: ERCOT 3 Parameter Policy issues
Issue- AS Proxy Offers:
  Momentum in favor of ERCOT proposal to use of x% of ASDC as proxy offer floor (evolved compromise after months of discussion)
  Note that the IMM believes AS Proxy Offer floor should be cost based or $0 (comments filed Feb 6- no language changes)
  Other notes:
    Consensus that that AS proxy offers distort the market and should be rare exceptions and quickly corrected.
    Consensus on the decreasing risk of proxy impacts by passing NPRR1270 to remove automatic AS qualification.
    ERCOT expected to file comments codifying x = 95%.

## Slide 9: Disposition of NPRRs at RTCBTF needed at April Board
NPRR1269: ERCOT 3 Parameter Policy issues (continued)
Issue- RUC ASDC:
  No opposition to ERCOT proposal for RUC Floor on ASDC (in the range of $10-20/MW at tail of AS Plan) to ensure most of AS Plan secured by RUC. ERCOT still studying optimal price floor for RUC.
  Some momentum to the idea that same ASDC floor in RUC should apply to RTM and DAM ASDCs (relates to NPRR1268). Multiple stakeholders mentioned the potential for filing comments.
Issue- AS Ramp Rate sharing
  Consensus with no issues

## Slide 10: Disposition of NPRRs at RTCBTF needed at April Board
NPRR1270: Clarification and AS Qualification
Strong consensus in favor of NPRR to remove original protocol concept of expansion of qualification to automatically include all SCED-dispatched resources for ECRS and Non-Spin.
  Note that all AS qualifications are grandfathered into RTC+B.

## Slide 11: RTCBTF Next Steps
ERCOT/RTCBTF continuing to focus on Handbooks and training development for Market Trials in coming weeks.
Half-day RTCBTF meeting after WMS on March 5 to focus on the 3 NPRRs prior to March 12 PRS
Next TAC meeting should be prepared to vote on all 3 NPRRs for April 8 Board consideration
Questions?