## Slide 1
RTC+B Market Trials - Market Submissions
Sreenivas Badri
Sruthi Hariharan
Nathan Smith
October 23, 2025

## Slide 2: RTC+B Market Trials – Submissions Testing
RTC QSE
Submission Testing
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
Start
03/07/2025
Start
05/05/2025
Start
09/02/2025
Go-Live
12/5/25*
Apr 2025
Mar 2025
Feb 2025
RTC Vendor
Submission Testing
Start
07/07/2025
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
RTC QSE
Submission Testing
Open-loop
RTC SCED
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
Feb 2025
Optional: RTC QSE/Vendor Developer
Submission Testing
This presentation covers the plan for ERCOT RTC+B Market Trial system configurations and digital certificates to support the stages of market trials and go-live to achieve the following:
  Isolate initial testing path for QSE/Vendor Sandbox testing from current production
  Minimize risk of RTC+B market submissions impacting current production
Day-Ahead Market
Non-Binding DAM using QSE offers for at least 2 tests
Transition to Go-Live
30-day Market Notice
11/5/25

## Slide 3
RTC+B Market Submissions - Systems configurations
RTC QSE
Submission Testing
Open-loop
RTC SCED
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC & Day Ahead Market & Transition to Go-Live
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
Start
03/07/2025
Start
05/05/2025
Start
09/02/2025
Go-Live
12/5/25*
Apr 2025
Mar 2025
Feb 2025
Optional: RTC QSE/Vendor Developer
Submission Testing
Start
07/07/2025
Certificate: Current MOTE
Env: ERCOT RTC Market Trial
URL: RTC MIS MOTE URL
Certificate: Current Production
Env: ERCOT RTC Market Trial
URL: RTC MIS Market Trial
Cert: Production
Env: Prod
URL: MIS Prod
QSE/Vendor developer can use MOTE certificates & RTC MIS MOTE API URL to test the submissions until end of submission testing phase (end of June) as needed. At the start of the Open Loop testing, RTC MOTE MIS URLs will be disabled.
URL links: RTC MOTE and Market Trial URL links to be used for MMSUI, OSUI and API submissions. Actual links are provided in next slide.
For notifications/responses to MPs from RTC Market Trials environment, MP will need to provide the listener URL to ERCOT

## Slide 4: RTC+B Market Submissions - Systems configurations
Currently (pre-RTC),
 | Digital Certificate | MMSUI/OSUI | API
Current MOTE | Current MOTE | MOTE MIS URL: testmis.ercot.com/mmsui testmis.ercot.com/osui | MOTE MIS API URL: testmisapi.ercot.com /2007-08/Nodal/eEDS/EWS/ testmisapi.wan.ercot.com:9443/2007-08/Nodal/eEDS/EWS/
Current Prod | Current Production | PROD MIS URL: mis.ercot.com/mmsui mis.ercot.com/osui | PROD MIS API URL: misapi.ercot.com/2007-08/Nodal/eEDS/EWS/ api.wan.ercot.com:8443/2007-08/Nodal/eEDS/EWS/

## Slide 5: RTC+B Market Submissions - Systems configurations
RTC+B Market Trials and Go-live
RTC+B Phase | Digital Certificate | MMSUI / OSUI URL | Internet/ WAN API URLs
Vendor/QSE Submissions Testing | Current MOTE | RTC MOTE MIS URLs https://testmarkettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://testmarkettrials.ercot.com/osrui/osrui/Summary.action | RTC+B MOTE Internet/WAN URL https://testmarkettrialsapi.ercot.com/NodalAPI/EWS/ https://testmarkettrialsapi.wan.ercot.com/NodalAPI/EWS/
Open Loop and Closed Loop Testing | Current Production | RTC Market Trial URL https://markettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://markettrials.ercot.com/osrui/osrui/Summary.action | RTC+B Market Trials Production System Internet/WAN URLs https://markettrialsapi.ercot.com/NodalAPI/EWS/ https://markettrialsapi.wan.ercot.com/NodalAPI/EWS/
From RTC Go-live onwards | Current Production | Current Prod MIS URL mis.ercot.com/mmsui mis.ercot.com/osui | RTC+B Go Live Production System New Internet/WAN URLs: Internet API URL: https://misapi.ercot.com/NodalAPI/EWS/ WAN API URL: https://api.wan.ercot.com/NodalAPI/EWS/

## Slide 6: RTC+B Market Submissions - Systems configurations Public Key Update for Internet/WAN API submissions
For API submissions into Market Trials environments, need to download public keys and place into the keystore location in system being used for RTC+B submissions.
No change to digital user certificates – continue to use existing MOTE and Production Certificates
Market Trail API Public key location: https://www.ercot.com/services/mdt/webservices

## Slide 7: RTC+B Market Trial Systems – Site Failover Schedule
No | Site Failover Date | Active Data Center | Notes
1 | 09/05/2025 | Taylor | 
2 | 10/03/2025 | Bastrop | 
3 | 11/07/2025 | Taylor | 
Current Production and RTC+B Market Trials Systems December Site Failovers are cancelled considering RTC+B Go-Live activities.
ERCOT Taylor will be Active Data Center for RTC+B Go-Live.

## Slide 8: Optional - RTC+B QSE Go-Live Cutover Connectivity Testing - Nov 3rd – Nov 7th
Some QSEs are using current production to support dual real-time market submissions into ERCOT RTC+B Market Trial Production System in parallel to Current Production.
Some QSEs are using parallel RTC+B Production and/or QA/Dev systems to support dual Real-Time and Day-Ahead Market Submissions into ERCOT RTC+B Market Trial Production System in parallel to current production.
QSEs Cutover Connectivity Testing window will be Open on November 3rd – November 7th to provide QSEs an opportunity to test out go-live cutover configurations and connectivity against ERCOT RTC+B Market Trials Systems.
  This testing window allows QSEs who are currently using parallel RTC+B systems for market submissions into RTC+B to test out their cutover software configurations without impacting current production market submissions.
  This test helps QSEs minimize risks with Go-Live cutover steps of their market systems.
  No changes will be made to ERCOT RTC+B market trial systems.
  QSEs are expected to use ongoing RTC+B market trials URLs and Production Certs for this connectivity test and submit production quality market submission into ERCOT RTC+B system.

## Slide 9: Optional - RTC+B QSE Go-Live Cutover Connectivity Testing - Nov 3rd – Nov 7th
Current Production - Market Submissions System
QSE
ERCOT
RTC+B - Market Submissions System
QSE
ERCOT
Current Production
- Market Submissions System
(Deploy RTC+B Code + Update Configurations/URLs)
Current Production MIS
QSE
ERCOT
RTC+B - Market Submissions System
RTC+B Market Trials URL
QSE
ERCOT
Current Production MIS
RTC+B Market Trials URL
Ongoing Market Trials
Optional - Connectivity Testing (Nov 3rd – Nov 7th)
Connect to RTC+B Market Trials to test connectivity for an hour

## Slide 10: RTC+B Market Trials Systems Readiness for Market Submissions Testing
RTC+B Market Trials Systems are built and setup for market submissions testing from Market Manager UI and through API.
Market Trials Systems is released for QSE submission testing as well as telemetry verification from 05/05/2025 to 06/30/2025.
Valid current MOTE certificates are required to connect to RTC+B Market Trials Systems for this phase of testing.
Report issues to ERCOT at rtcb@ercot.com
Market Notice was sent on 2/26/2025 with details on QSE/Vendor sandbox testing.
https://www.ercot.com/services/comm/mkt_notices/M-B022625-01
Market Notice was sent on 4/16/2025 with details on QSE/Vendor submission testing and telemetry verification.
  https://www.ercot.com/services/comm/mkt_notices/M-A041625-01

## Slide 11: RTC+B Market Trials Systems Readiness for Open Loop and Closed Loop Testing Market Submissions
06/30/2025 5:00 PM - RTC+B Market Trials MOTE URLs (UIs/APIs) will be disabled permanently.
  RTC+B MOTE will be available only from Go Live for normal MOTE testing activities.
  QSEs can use non-monitoring days (Mon/Wed/Fri) to make test submissions into RTC+B Market Trials Production System to test software changes until Go-Live.
    Once testing is completed, cancel the test submission or update test submission with production quality market data.
07/01/2025 – 07/06/2025 – Configure RTC+B Market Trials System with Market Trials Production System URLs, deploy latest RTC+B code and perform site failover testing.
  During this time, Market Trials Market and Outage Submissions systems (APIs/UIs) will be unavailable for market submissions.
07/07/2025 08:00 AM – RTC+B Market Trials Production Systems will be up and running for Open Loop Testing.
Same Market Trials Production System configuration will be used for Day-Ahead Market Submissions (Sept – Oct) and for Closed Loop Testing as well.
QSE Activities
  Update RTC+B Market Trials – Market Submission Systems with ERCOT RTC+B Market Trials Production Systems Internet/Wan API URLs and certs to support Open Loop Testing from 07/07 and Closed Loop Testing.
  Set up the listeners in RTC+B environment to receive notifications from ERCOT during open loop and closed loop testing and provide listener URLs to ERCOT

## Slide 12: Dual Market Submissions
Market Submissions to Current Production should not be impacted until Go-Live.
Open Loop Testing (07/07 – 08/29)
  Dual Market Submissions – QSEs are expected to submit following RTC+B real-time Market Submissions into RTC+B Market Trial Production System with Production Quality in parallel to Current Production for the monitoring days (Tuesday/Thursday) 09:00 AM – 5:00 PM as indicated in Handbook#3.
    COPs
    TPOs
    AS Offers
    ESR Energy Bid/Offer Curves
    RTM Bids and Offers
    Output Schedules
  Market Submissions quality will be validated during monitoring days
  RTC+B SCED will be run on these monitoring days (Tuesday/Thursday) with above production quality market submissions and expect to produce production quality SCED results (Energy Base points, AS Awards, congestion management etc.).
Closed Loop Testing (Sept – November)
  1st Closed Loop Testing is planned on September 2nd week, 2nd Closed Loop Testing is planned in October. If needed 3rd Closed Loop Testing will be scheduled in November.
  These are 2 hours tests – RTC LFC/SCED will be controlling the grid.
  Dual Market Submissions – QSEs are expected to submit above RTC+B real-time Market Submissions into RTC+B Market Trial Production System with Production Quality in parallel to Current Production starting from 5:00PM of the day prior to the closed loop testing until the completion of the test.
    Real-time Market Submissions should be submitted for all 24 hours of the closed loop testing day

## Slide 13: Dual Market Submissions
Day Ahead Market Executions (Sept – Oct)
  At least 2 RTC+B Day Ahead Markets will be executed
  QSEs RTC+B systems should be setup to test their day-ahead market submissions for defined transactions (Energy Bid/Offer Curves, AS Self-Arrangement, DAM AS Only Offers, and normal DAM submissions).
    During day-market submissions into RTC+B, current production day-ahead market submissions should not be impacted.
  ERCOT will execute and publish at least two Day-Ahead Markets
  DAM participation is strongly encouraged, but will not be required in Readiness metrics
Go-Live
  Dual Market Submissions – QSEs are expected to submit RTC+B real-time Market Submissions into RTC+B Market Trial Production System with Production Quality in parallel to current production starting from few hours or days before Go-Live.
    Exact start time of dual market submissions for Go-Live will be provided during Go-Live Cutover discussions.
At any given time either current production or RTC+B system will be live, NOT both.

## Slide 14: RTC+B Go-Live Cutover – Dual Submissions prior to Go-Live
 | Submission Type | RTC Expectations for Submission Dual Entry | *Bulk and Dual submission Times
RESOURCE | COP | Submit for all Operating Hours 12/4/2025 HE1800 and beyond for RUC Capacity Short snapshot | Bulk submission - on or before 12/04 4:00 PM and from here dual submission until go-live
 | AS Offer | Submit by 12/4 for all ODs 12/5/2025 and beyond. For those using dual-entry, ensure expiration times reflect desired RTC participation. Note that submissions needed on 12/4/2025 for OD 12/5/2025 for RUC Capacity short snapshot. | Bulk submission - on or before 12/04 4:00 PM and from here dual submission until go-live
Trades | AS Trade | Submit from 12/4 for OD 12/5 for RUC Capacity Short Snapshot | Bulk submission (from both parties) - on or before 12/04 4:00 PM and from here dual submission until go-live
 | Energy Trade | Submit for OD 12/4/2025 and beyond, Energy trades for 12/4 can be updated/confirmed up to 12/5 14:30 | Bulk submission (from both parties) - on or before 12/03 4:00 PM and from here dual submission until go-live (HRUC looking at OD 12/04 from 12/3 4:00 PM run)
 | Capacity Trade | For OD 12/5 and beyond | Bulk submission (from both parties) - on or before 12/04 4:00 PM and from here dual submission until go-live
Please refer to RTC+B Go-Live Dual Submissions spreadsheet posted under RTCBTF site for more details:
https://www.ercot.com/files/docs/2025/10/23/Cutover-Strategy_Dual-Submissions_20251015.xlsx
Dual submissions start from 12/01/2025 for the OD 12/04 and onwards.
*Bulk submissions are optional for QSEs, it can be used if QSE has limitations to support constant dual submissions. For trades, both parties should coordinate submissions and confirmations at the same time.

## Slide 15: RTC+B Go-Live Cutover – Dual Submissions through APIs – QSE/ERCOT Systems Setup
If QSEs are using their current production Market System for RTC+B Real-Time Market dual Submissions and does not have ability to do Day-Ahead (DA) and Trades dual submissions, they can use their QA or lower environments to make DA and Trades dual submissions into ERCOT RTC+B Market Trials System in preparation for Go-live.
  In this case, QSE will not receive DA and Trades related notifications from ERCOT if QSE does not have listener setup in their lower environment.
Dual Submissions for Go-Live
Current Production - Market Submissions System
QSE 1
ERCOT
RTC+B - Market Submissions System (Prod/QA)
QSE 2
ERCOT
Current Production MIS
RTC+B Market Trials URL
RTC+B Real-Time Market Submissions
RTC+B Market Submissions - Real-Time, DA and Trades
RTC+B - Market Submissions System (QA)
(DA and Trades)
QSE 1
RTC+B – DA and Trades
*** Actual Go-Live systems detailed cutover plan will be shared during November Go-Live Cutover Workshops ***

## Slide 16: Outage Submissions
For the initial phases of market trial testing including Vendor sandbox testing and QSE submission testing (spanning Mar-Jun 2025):
  Request QSEs to send us an email request (to RTCB@ercot.com) with the details of the outage to be approved for ERCOT review/action.
  ERCOT will manually approve the outages.
  This will help QSEs, and their vendors test their Outage Scheduler software.
Open Loop Testing
  Outage Submissions testing is not mandatory during Open Loop Testing but strongly encouraged to continue to test the outage submissions utilizing the RTC+B Market Trials Production Systems UI/API URLs until end of October (10/31/2025).
  RTC+B Outage Scheduler will be transitioned to Read-Only Mode from November 1st until Go-Live (Dec 4th night) for ERCOT Outage Coordination studies. Market Participants (QSEs/TSPs) can only query outages i.e., they can not make any outage changes from November 1st until Go-Live.
Closed Loop Testing
  Outage Submissions into ERCOT RTC+B Market Trials Production System is not required during Closed Loop Testing.
Dual Outage Submissions for Go-live
  Dual submission of Outages is not required for Go-Live as well.
Above 2.3.6 and 4.3.8 sections updates modifies XSDs, rest are EIP Specifications Document updates Only.

## Slide 17: RTC+B Final Outage Submissions Testing Window
Latest RTC+B Outage Scheduler model is loaded into RTC+B and outages are synced from current production.
RTC+B Outage Scheduler will be available for QSEs/TSPs outage submissions testing (using API/OS UI) until end of October (10/31/2025) Only.
From November 1st, RTC+B Outage Scheduler will be made “Read-Only” until Go-Live. This means QSEs/TSPs can only query outages but can not make any changes from 11/01/2025.
Above change is required to allow ERCOT outage coordination team begin 60-day and 90-day ahead outages studies utilizing RTC+B Outage Scheduler and avoid dual outage submissions from QSEs/TSPs.
  Starting from November 1st until Go-Live on Dec 4th night, RTC+B outage scheduler system outages will be updated periodically from current production (including converting combo model ESR outages to Single Model) to keep RTC+B outage scheduler in sync with current production outages.
  Please refer to Market notice was sent out on 10/03/2025 for more details
    https://www.ercot.com/services/comm/mkt_notices/M-A092624-04

## Slide 18: RTC+B Market Trials Upcoming Activities
10/27/2025 Model Load and Release Deployment
  OCT_ML5 network model load to RTC Market Trials
  MMS and EMS release deployments to RTC Market Trials. Includes some fixes for issues that were previously identified in Closed Loop #1:
    Received Non-Spin awards for a unit that is offline and cannot provide offline non-spin
    Received RRS awards for unit on STARTUP
    BLR resource not getting awarded ECRSM
    Unexpected AS Awards based on MCPC - Defect identified due to incorrect AS proxy offers for MT SCED intervals 9/11 10:30 - 11:00 AM
10/30/2025 Closed Loop LFC test #2
    Market Notice Link https://www.ercot.com/services/comm/mkt_notices/M-A100925-01
11/2/2025 2025 Long DST Transition
  Encourage MPs to submit Market Submissions for Long DST OD 11/02
  ERCOT will monitor EMS and MMS applications
11/3/2025 to 11/7/2025 – Optional cutover connectivity testing window
  To provide QSEs an opportunity to test out go-live cutover configurations and connectivity against ERCOT RTC+B Market Trials Systems.

## Slide 19: IRR Forecast to QSEs
ERCOT is not planning to send Wind/Solar forecast to QSEs RTC+B environment through API from ERCOT Market Trials environment.
QSEs are expected to use Wind/Solar forecast from current production for RTC+B COP submissions.

## Slide 20: Market Submission Issues
ERCOT is reaching out to a subset of QSEs where ERCOT has observed potential real-time market submission issues on Aug 19 and/or Aug 21.
Summary of issues/observations:
  Off-line ECRS (OFFEC) offers are unable to be awarded in RTM for RTC+B. Please submit these as an online ECRS offer with resource status ‘OFFQS’ during the RTM.
  Resources providing AS in Production did not have respective AS Offers in RTC+B
    Examples:
      Missing online Non-Spin offers for ESRs carrying online Non-Spin in Production.
      Only submitting AS Offers for ECRS instead of all AS types carried in Production (RRSPF, Non-Spin, ECRS)
      ESRs – Only offering in RRSPF, AS Offers not submitted for AS types (REGDN, REGUP, ECRS) that these resources are carrying in Production.
  Submitting AS Offers for just a subset of types the Resource is qualified to provide.
  Submitting “test” MW amounts for all ESRs instead of resource capability for AS.
  Submitting MW amounts much less than resource capability.
ERCOT is requesting QSEs to resolve these issues as soon as possible, these issues are impacting SCED solution quality.
Closed Loop Testing Preparation – Resource RTC+B EOC should match with production EOC. Practice the submission now in preparation for Closed Loop Test on 09/11/2025.

## Slide 21: Market Submissions Handbooks Review
For each phase of Market Trials testing, a handbook will be posted to the RTBTF web page - https://www.ercot.com/committees/tac/rtcbtf
Handbook to cover the expectations for each phase of testing, including
  the key activities for that testing phase,
  required submissions and expectations of submissions data entry with regard to current Production submissions. For example, during closed loop testing we would expect RTC submissions to closely align with current Production submissions to ensure smooth transition into and out of closed loop testing,
  QSE performance evaluation criteria,
  and high-level timelines for each phase.
Screenshot from Market Trials Handbook 1 – RTC QSE Submission Testing
https://www.ercot.com/files/docs/2025/04/07/RTCB_Market_Trials_Handbook_1_MarketSubmissions.docx

## Slide 22: Market Submissions Handbooks Review
Screenshot from RTC Market Trials Handbook 3 - Open Loop Testing
https://www.ercot.com/files/docs/2025/04/07/RTCB_Market_Trials_Handbook_3_OpenLoop_RTC_SCED_04182025_FINAL_Revised_071125.docx

## Slide 23: Market Submissions Handbooks Review
Screenshot from RTC Market Trials Handbook 6 – Day Ahead Market
https://www.ercot.com/files/docs/2025/04/28/RTCB_Market_Trials_Handbook_6_DayAheadMarket_06132025_FINAL.docx

## Slide 24: FAQ - Market Trials Submission Testing
Q1. The following questions related to Market Trials submissions testing have been addressed in the RTC Market Trial handbooks. Details in the following two slides:
  What are the different submissions that QSE needs to submit for each phase of Market Trials?
  What is the duration for which QSE needs to submit for each phase of Market Trials?
  What actions/applications will ERCOT be running during each phase?
  What are performance evaluation criteria for the QSEs for each phase of Market Trial testing?

## Slide 25: FAQ - Market Trials Submission Testing
Q2. Request for IP/DNS information
A2. These are not changed for RTC. For any IP address or DNS names for Ercot API or Ercot Notification Source IP address, please contact the ERCOT client reps/account managers, or send a request email to RTCB mailbox.
Q3. Notifications from ERCOT
A4. To support testing notifications from ERCOT for API submissions, QSEs should submit API Listener URL set up information using the template available from the “Technical RTC+B Details” section of the RTCBTF page. QSEs are expected to complete this template and send it to RTCB@ercot.com.
The specific coded alerts/notifications from ERCOT can be found in the EIP External Specs document Section 5.3.1 - https://www.ercot.com/files/docs/2024/06/24/EIP_External_Interfaces_Specification_RTCB_v1.0.zip
For Market submission validations and corresponding error messages – the only changes are related to the submission changes for RTC. The updated RTC+B submission validation rules can be found here - https://www.ercot.com/mp/data-products/data-product-details?id=NP4-450-M. These messages do not include an error code, and the message text for these vary based on the submission error and are specific to the resource/values submitted.

## Slide 26: FAQ - Market Trials Submission Testing
Q4. When can MPs start testing DAM and SCED awards data along with reports in Market Trials?
A4. Currently the Market Trial environment is setup with limited functionality. For the first two phases of testing, the functionality is limited to vendor and QSE market submission testing and telemetry validations. Starting with Open Loop testing till go-live, the environment will be updated to allow for DAM/SCED runs.
DAM award reports will be available on MMSUI/via EWS on the days when DAM is run on RTC market trials
During open loop testing, ERCOT will publish the following four reports:
SCED Shadow Prices and Binding Transmission Constraints - NP6-86-CD
LMPs by Resource Nodes, Load Zones and Trading Hubs Market Trials - NP6-788-CD
Modify Real-Time ORDC and Reliability Deployment Price Adders and Reserves by SCED Interval - NP6-323-CD
Real-Time Clearing Prices for Capacity by SCED interval – NP6-332-CD

## Slide 27: FAQ - Market Trials Submission Testing
Q5. RTC+B Settlements Extracts in Market Trials?
A5. Market Trials are limited for Settlements and Billing:
ERCOT will not be providing QSE specific statement files, however, generalized sample DAM and RTM Statements posted to 5/21 RTCBTF meeting page
  https://www.ercot.com/calendar/05212025-RTCBTF-Meeting
These statements do not structurally change, but will include changes in the billing determinants for RTC
ERCOT has provided training on the RTC billing determinants and posted in a YouTube on this page:
  https://www.ercot.com/committees/tac/rtcbtf/training (Select RTC+B Settlement Overview)

## Slide 28: RTC+B Market Trials
Questions?
Provide feedback to ERCOT on any concerns/questions at rtcb@ercot.com