## Slide 1
RTC+B Market Trials Systems – Model Load and Release Deployment Schedule
Sruthi Hariharan
March 26, 2025

## Slide 2: CIM Model Load Schedule - Draft
Similar to the Production Load Schedule published on ercot.com (https://www.ercot.com/gridinfo/transmission/opsys-change-schedule/), ERCOT will publish a draft Network Operations Model (NOM) load schedule for the RTC Market Trials environment effective May to go-live in December.
The schedule will include the following key information:
  Deadline for ICCP submissions (3-4 weeks before the Market Trials load date) – to be managed based on the volume of requests.
  Market Trials Load date - Date market trials environment ready NOM is loaded and used.
Sample schedule below (to be finalized and published to the RTCBTF site in April 2025). The schedule will move to a weekly cadence as we get closer to closed loop testing and go-live.
Network Model | ICCP Request Deadline | Market Trial Load | Market Trial Phase
RTC_MAY_ML1 | 4/10/2025 | 5/2/2025 | QSE Submission Testing
RTC_JUN_ML2 | 5/22/2025 | 6/13/2025 | QSE Submission Testing
RTC_JUL_ML1 | 6/12/2025 | 7/3/2025 | Open Loop RTC SCED
DRAFT

## Slide 3: Release Deployment and Maintenance Patching Schedule
Functional changes and defect fixes will be deployed into the market trials environment monthly
  For example, a release was deployed into Market Trials on 3/18/2025 which addressed a few defects related to AS-only offer submission validation and ESR three-part offer submissions
For any critical fixes significantly impeding market trials testing, we will prioritize and take the fixes in as soon as possible.
Starting May 2025, ERCOT will communicate any environment downtime to be expected during regular business hours (Mon-Fri 8-5 PM) for release deployment or maintenance patching. This will be coordinated to not coincide with the monitored operating days mentioned in the market trials handbooks.

## Slide 4: RTC+B Market Trials Systems – Model Load and Release Deployment Schedule
Questions?
Provide feedback to ERCOT on any concerns/questions at rtcb@ercot.com