## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
April 23, 2025

## Slide 2: Outline
Update on RTCBTF Issues List
Update on RTC NPRRs
Market Readiness response scorecard
Market Notice on Market Trials Start 5/5/25
Summary of Discussions
Policy Parking-Deck for post go-live

## Slide 3: RTCBTF Issues List
Red boxes are NPRR1268, 1269, 1270 (April Board)
Blue Box is evaluation of State of Charge and AS Duration (target June Board)
Market Trials
Market Trials

## Slide 4: Summary and Timeline of NPRRs
NPRRs set for PUCT May 15 Open Meeting
  NPRR1268 for ASDC Modifications (IMM sponsor)
  NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  NPRR1270 for AS Qualification details (ERCOT sponsor)
State of Charge NPRR – Began discussion March 25 and targeting June Board
Final Clarifying NPRR – Begin discussion June 18 and target Sep Board
  Settlement changes (corrections)
  Retain current NFRC telemetry point (do not retire)
  Offer/Bid structure clean-up (inconsistent protocols)
-----------------------------------------------------------------------------------------------
Remaining Stakeholder path to Board Meetings before Go-Live:
  PRS May 14 > TAC May 28 > Board June 24
  PRS Aug 13 > TAC Aug 28 > Board Sep 23
  ---------------------------------------------------------------------------------------------------------

## Slide 5
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.

## Slide 6: Other Updates
Readiness engagement update:
  Developed new folders on RTCBTF home page (done and continue to add content)
    Market Trials folder: Handbooks and supporting materials
    Technical Support folder: Key TWG technical materials
  RTCB@ercot.com mailbox for support of stakeholder implementation questions (done)
  Target to add more training videos in next 60 days (in process)
    Operations
    Load Resources
    Day-Ahead Market
    Battery
    RTC Worksheet Solver Walkthrough
  Following guidance from RTCBTF to engage DSWG separately (done 4/17/25)
  Outreach to Operator Training Seminar and Spring GCPA (complete next Wednesday)
  Next TWG meeting is April 24
    ERCOT will continue to support detailed technical conversations such as adding telemetry points to network model, digital certificates, accessing ERCOT systems in March/April timeframe
Formal Market Trials begin in 2 weeks (May 5, 2025)
  Weekly WebEx every Monday 10am-10:30am (starting May 5 – December 8, 2025)

## Slide 7: Market Notice on QSE Readiness (response due by March 31)
Market Notice for QSE Awareness with Monday March 31 due date:

## Slide 8: QSE Scores
Scores for responding to March RTC+B Awareness Readiness Survey: 100%

## Slide 9: Market Notice on RTC+B Market Trials
Market Notice sent April 16 to announce start date/time and explain market trials:

## Slide 10: Focus for remainder of RTCBTF today:
State of Charge / AS Duration Discussion (Nitika Mago)
Presentation and Draft NPRR and NOGRR
Market Readiness
Review Handbook #3- Open Loop SCED (Round 3-final) - Nathan Smith
Review Handbook #4- QSE Telemetry Tests (Round 3-final) - Abhi Masanna Gari
Review Handbook #5- Close-Loop LFC Tests (Round 1-initial) - Matt Mereness
Review Handbook #6- Day-Ahead Market Tests (Round 1-initial) - Alfredo Moreno
Review 3 New training modules
Day-Ahead Market Training- Alfredo Moreno
Battery Training- Kenneth Ragsdale
RTC Spreadsheet tool and examples- Ryan King
TWG Updates/Questions
Reports update- (Matt for Jamie Lavas)
Other Business
Next steps on HEN proposal related to underlying AORDC calculations (Shams)

## Slide 11: What is coming to TAC in May:
FUTURE TAC VOTE: State of Charge / AS Duration (Nitika Mago)
NPRR and NOGRR to be filed in coming days
    Non-Spin duration should remain at least at four hours
    ECRS duration should be changed to one hour
    Regulation Service and RRS duration should be changed to 30 minutes
    RUC studies should use a one-hour duration for all Ancillary Service types, excluding Fast Frequency Response (FFR) which should continue to require a 15-minute duration.
If needed, can consider additional RTCBTF WebEx meeting
Start Considering Parking Lot Items
Some market design issues keep coming up and need a future forum, e.g. HEN proposal related to underlying AORDC calculations (Shams).
Whether items come to TAC with a brief explanation of issue and then TAC could consider re-assignment.
Questions?
Thanks for the support of RTCBTF and Market Trials on May 5th