## Slide 1
Weekly
RTC+B Market Trials Update
ERCOT Staff
May 12, 2025

## Slide 2: Outline
Antitrust Admonition
Reminder of Key Document Postings
Expectations of QSEs for the Week
Communicate any known Issues within On-going Trial
Provide Snapshot of Cumulative QSE Scorecards
Support any Technical and/or Business Questions

## Slide 3
WebEx Meeting reminders (same as other ERCOT forums):
Please keep line muted
If you have a question, please use the chat feature to either:
  Type in your question, or
  Type in “Question” and wait to be recognized to state question

## Slide 4
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 5: Market Trials
TAC Approved the Market Trials Plan in October 2024
Discussions with RTC+B Task Force have shaped the Handbooks
Handbook #1- QSE Submission Testing
Handbook #2- QSE Telemetry Tests
Handbook #3- Open Loop SCED
Handbook #4- QSE Telemetry Tests
Handbook #5- Close-Loop LFC Tests (draft)
Handbook #6- Day-Ahead Market Tests (draft)
All are posted on the
RTCBTF Homepage
under Market Trials banner

## Slide 6: Market Trials
Detailed discussions with TWG have provided technical content details
Digital Certificate details
Connectivity/URL details to User Interfaces and APIs
Reminder of how to submit new ICCP requests
RTC and Production Telemetry connectivity
Network Model Load Schedule
All are posted on the
RTCBTF Homepage
under Technical Details banner

## Slide 7: Initial RTC+B FAQ has been posted
Worksheets for categories
Posted on RTCBTF Home Page under KeyDocs
Common questions/responses in Excel Workbook (target weekly updates)
Search workbook for Key Words

## Slide 8: Resources for May-June Market Trials
Everything needed for current market trials is on RTCBTF home page

## Slide 9: Summary of Market Trial activities for this week and following weeks
QSE connectivity and market submissions
  Submit to Market Management System and Outage Scheduler
  Goal to submit at least one successful transaction for each requested transaction type per QSE once during the 8-week period
QSE telemetry set-up and check-out
  Submit all ICCP requests to ERCOT to add telemetry points
  Check-out will be for a sampling of resources within the QSE portfolio to ensure data flowing between ERCOT/QSE
Scoring will not start until Week of May 19

## Slide 10: Scorecard example:
Scores for responding to March RTC+B Awareness Readiness Survey for QSE with Resources ~ 107 QSEs
Scoring does not start until week of May 19

## Slide 11: Scorecards for this Market Trials
Handbook Book 1: ERCOT will publish 3 scorecards, one for each type of Resource: Generation, Load Resources, ESR
    Green: all submissions types completed at least once during the trial
    Yellow: some submissions types completed at least once during the trial
    Red: no submissions received
Handbook 2: ERCOT will publish 2 scorecards:
  Complete all telemetry additions
    Green: all new telemetry added (100%)
    Yellow: some telemetry added
    Red: no new telemetry added
  Check-out complete
    Green: Check-out successfully completed (for sample of Resources)
    Yellow: Check-out scheduled, but not yet complete
    Red: No check-out activity

## Slide 12: Current ERCOT Issues Impacting Trial sequence
Environment:
  Some user access issues reported (data set-up issue in environment). QSE can request assistance for ERCOT to resolve RTCB@ercot.com
Defects:
  Load Resources submitting ECRS in COP
  AS Only Offer Submission response is missing
  Next release planned May 28

## Slide 13: Wrap-Up and Questions
Remainder of meeting time to take questions each week-
First round of questions specifically about this Market Trial period
Second round of questions for more general RTC+B as time allows
Can always email the RTC+B Program mailbox: RTCB@ercot.com
FAQ is also a resource for questions that other have asked.
Thanks for your support!