## Slide 1
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
FTPS and API Security Upgrade Project
Announcement
Esther Kent and Andrea OFlaherty
RMS Meeting May 13, 2025

## Slide 2
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Agenda
Project Purpose and Benefits
Scope and Market Participant Action Required
Timeline
Transition Support for REPs and CSPs
Reference Material
  REP and CSP Tasks Required for FTP
  REP and CSP Tasks Required for API

## Slide 3
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Project Purpose and Benefits
Purpose
Upgrade the following security protocols for the data delivery integration points at SMT:
Move from File Transfer Protocol Secure (“FTPS”) to SSH File Transfer Protocol “SFTP” for Retail Electric Provider (REP) and Competitive Service Provider (CSP) LSE file downloads, enrollment reporting downloads, and subscription reporting downloads.
Add JSON Web Tokens (“JWT”) tokens to the APIs for ad hoc reporting data retrieval.
Benefits
Enhanced security.
Modernizes the SMT solution technology for longer term technical currency.
Simplifies the File Transfer Protocol (“FTP”) integration for Market Participants by no longer requiring SSL Certificates and therefore, eliminating Certificate renewals.

## Slide 4
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Scope and Market Participant Action Required
Scope
The scope of the upgrade will impact FTP and API functionality only – affecting the REP’s and CSP’s integration points to access and download data from their FTP folders and ad hoc data retrieval via APIs.
The upgrade does not affect any SMT Website portal access for any user types (residential, business, REPs, CSPs etc.).
Market Participant Action Required
REPs and CSPs will be required to upgrade their FTP and API integration points to continue downloading and requesting ad hoc data via API from SMT.

## Slide 5: SMT FTPS and API Upgrade
Timeline
May 2025
6th May- Help Desk Communication and Enablement
13th May - RMS Meeting Presentation
14th May – Initial Market Notice (90 Day)
19th May - Commence Development Efforts
20th May – First Market Technical Q and A Web Conference
June 2025
3rd June – Second Market Technical Q and A Web Conference
22nd June – Second Market Notice (60 Day)
27th June - Complete Development
30th June - Commence System Integration Testing
July 2025
1st July - Third Market Technical Q and A Web Conference
18th July - Complete System Testing
21st July - Commence UAT
22nd July – Third Market Notice (30 Day)
30th July – Fourth Market Technical Q and A Web Conference
August 2025
8th August - Complete UAT
13th August - Help Desk Enablement
14th Aug – Fifth Market Technical Q and A Web Conference
19th August - Fourth Market Notice (3 Day)
22nd Aug - Final Market Technical Q and A Web Conference
23rd August - Go Live
September 2025
22nd August thru 11th September - Market Transition Support – REPs, IT vendors and CSPs to upgrade to the new Services. New and replaced services running in parallel
12th September - Decommission replaced FTPS and API services
Help desk tickets can be opened by Market Participants at any time for one-on-one support

## Slide 6
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Transition Support for REPs and CSPs
Market Technical Q and A Web Conferences
20th May
3rd June
1st July
30th July
14th August
22nd August
One on One Assistance Via Help Desk Ticket
Request a one-on-one assistance session via a help desk ticket by either calling 844-217-8595 or emailing Support@SmartMeterTexas.com
SMT Transition Support August 22nd through September 11th
SMT has planned support personnel dedicated for REP and CSP transition assistance starting today throughout the duration of the project including an additional three weeks after go live from August 22nd through September 11th.

## Slide 7
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Reference Materials

## Slide 8
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Overview of REP and CSP Tasks Required for FTP
(Reference Only - This Will be Covered in SMT Upcoming Technical Conferences and/or One on One Sessions as Needed)
Tasks required for FTP upgrade and re-integration:
Generate an SSH key pair and provide the public key to SMT for configuration.
Update network firewall settings to allow outbound traffic from the client system to the new SMT SFTP service, while blocking outbound FTP traffic if a firewall is in place.
Update any existing scripts, batch jobs, or automation tools to utilize the SFTP protocol instead of FTPS, if custom code is in use. Various tools such as WinSCP and FileZilla can facilitate SFTP connections.
Test file downloads.
No changes are required to the existing file decryption process using PGP keys.

## Slide 9
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Overview of REP and CSP Tasks Required for API
(Reference Only - This Will be Covered in Upcoming Technical Conferences and/or One on One Sessions as Needed)
Tasks required for API upgrade and re-integration:
Obtain JWT Tokens: API clients must request a JSON Web Token (JWT) from the new token API endpoint provided by SMT. The token will be valid for a defined period of time(1 hour).
Update API Request Headers: Replace Basic Auth credentials (Authorization: Basic bas64(<username>:<password>)) with the JWT token in the request headers ( Authorization: Bearer <jwt-token>).
Secure Token Storage: Store tokens securely in the client environment and reuse this token for subsequent API calls until expiry.
Handle Token Expiry: Implement logic to detect token expiration i.e., implement error handling for expired or invalid tokens (HTTP 401 Unauthorized responses) and request a new token using the new token API endpoint provided by SMT.
Test API Requests with JWT: Validate API requests using the JWT to ensure proper authorization.
No changes to the existing process for generation of the API user credentials.
No changes to the network are required.