## Slide 1
RTC+B Task Force
Update
Matt Mereness
RTCBTF
May 21, 2025

## Slide 2: Outline
Discussion today:
  Update on RTCBTF Issues List
  Update on NPRRs
  Market Trials Update
  Rest of Today’s Agenda

## Slide 3: RTCBTF Issues List
Red boxes are NPRR1268, 1269, 1270 (April Board)
Blue Box is evaluation of State of Charge and AS Duration (target June Board)
Market Trials
Market Trials

## Slide 4: Summary and Timeline of NPRRs
NPRRs set for PUCT May 15 Open Meeting (PUCT approved)
  NPRR1268 for ASDC Modifications (IMM sponsor)
  NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  NPRR1270 for AS Qualification details (ERCOT sponsor)
AS Duration / State of Charge (NPRR1282 / NOGRR277)
  Began discussion March 25 and targeting June Board
  NPRR1282 PRS Approved
  NOGRR277 ROS email vote in flight
Final Clarifying NPRR – Begin discussion June 18 today and target Sep Board
  Review today for any issues
  ERCOT to submit NPRR by end of week for extended review at subsequent RTCBTF meetings
Remaining Stakeholder path to Board Meetings before Go-Live:
  PRS May 14 > TAC May 28 > Board June 24
  PRS Aug 13 > TAC Aug 28 > Board Sep 23

## Slide 5
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.

## Slide 6: Other Updates
Readiness engagement update:
  Developed new folders on RTCBTF home page (done)
    Market Trials folder: Handbooks and supporting materials
    Technical Support folder: Key TWG technical materials
  RTCB@ercot.com mailbox for support of stakeholder implementation questions
  Established FAQ document and posted on RTCBTF home page
  Target to add more training videos in next 30 days (in process)
    Operations / Load Resources / RTC Worksheet Solver Walkthrough
    Day-Ahead Market / Battery
  Following guidance from RTCBTF to engage DSWG separately (done 4/17/25)
  Outreach to Operator Training Seminar and Spring GCPA (complete next Wednesday)
  Next TWG meeting is May 29
    ERCOT will continue to support detailed technical conversations such as adding telemetry points to network model, digital certificates, accessing ERCOT systems in March/April timeframe
Closed-Loop LFC planning (critical for market feedback)- later today
Looking to start internal work on Transition/Cutover Plan
Formal Market Trials began May 5, 2025 (more on next slide)

## Slide 7: Weekly Market Trials update
Trials meeting every Monday 10-10:30am until December
  Standalone calendar page each week with WebEx
    RTCBTF Home Page houses all market trials documentation
  Averaging 150-175 participants
  Weekly presentation walk-through with Q&A
    Weeks 1&2 were educational
    Week 3 scoring was initiated
    Heavy use of RTCB@ercot.com email -> FAQ
Quick walkthrough of this week’s meeting

## Slide 8: Focus for remainder of RTCBTF today:
Draft Clarification NPRR needed before Go-Live (Dave Maggio)
Discussion of impacts of capping System Lambda and alternatives (Shams)
State of Charge / AS Duration Discussion (Nitika Mago)
Discussion as needed for NPRR1282/NOGRR277
Re-education on AS Deployment Factors (Sai whitepaper prior to NPRR1204)
Market Readiness
Review Handbook #5- Closed-Loop LFC Tests (Round 2) - Matt Mereness
Review Handbook #6- Day-Ahead Market Tests (Round 2) - Alfredo Moreno
Review of Settlement Statements and Extracts - Magie Shanks
Other Business