## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
May 28, 2025

## Slide 2: Outline
Update on RTCBTF Issues List
Update on RTC NPRRs
Market Trials Update (began 5/5/25)
Request for pause of work competing with RTC+B resources (Keith Collins)

## Slide 3: RTCBTF Issues List
NPRR1268, 1269, 1270 approved at PUCT (thank you!)
State of Charge and AS Duration (NPRR1282/NOGRR277 target June Board)
Market Trials
Market Trials

## Slide 4: Summary and Timeline of NPRRs
NPRRs approved at PUCT May 15 Open Meeting
  NPRR1268 for ASDC Modifications (IMM sponsor)
  NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  NPRR1270 for AS Qualification details (ERCOT sponsor)
AS Duration / State of Charge (NPRR1282 / NOGRR277)
  Began discussion March 25 and targeting June Board
  NPRR1282 PRS approved / NOGRR277 ROS email approval
Final Clarifying NPRR – Began discussion June 18 May 21 (Sept Board)
  Will be filed and can be tabled at PRS while more discussion at RTCBTF
  10 areas of clarification with minimal to no system changes such as:
    Settlement changes (corrections)
    Retain current NFRC telemetry point (do not retire)
    Offer/Bid structure clean-up (inconsistent protocols)
Remaining Stakeholder path to Board Meetings before Go-Live:
  PRS May 14 > TAC May 28 > Board June 24
  PRS Aug 13 > TAC Aug 28 > Board Sep 23

## Slide 5: Other RTCBTF Updates
Readiness engagement update:
  Developed new folders on RTCBTF home page (done)
    Market Trials folder: Handbooks and supporting materials
    Technical Support folder: Key TWG technical materials
  RTCB@ercot.com mailbox for support of stakeholder implementation questions
  Established FAQ document and posted on RTCBTF home page
  Target to add more training videos in next 30 days (in process)
    Operations / Load Resources / RTC Worksheet Solver Walkthrough
    Day-Ahead Market / Battery
  Following guidance from RTCBTF to engage DSWG separately (done 4/17/25)
  Outreach to Operator Training Seminar and Spring GCPA (complete)
  ERCOT posted sample Settlement Statements/Extracts at May 21 RTCBTF
  Next TWG meeting is May 29
    ERCOT will continue to support detailed technical conversations such as adding telemetry points to network model, digital certificates, accessing ERCOT systems in March/April timeframe
Formal Market Trials began May 5, 2025 (more on next slide)
Closed-Loop LFC Handbook review (critical for market feedback)
Starting internal work on Transition/Cutover Plan (moving earlier in review)
Shams proposal of removing system lambda capping logic deferred until an NPRR is potentially filed (out of scope for RTCBTF)

## Slide 6
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 7: Weekly Market Trials update
Trials meeting every Monday 10-10:30am until December
  Standalone calendar page each week with WebEx
    RTCBTF Home Page houses all market trials documentation
  Averaging 150-175 participants
  Weekly presentation walk-through with Q&A
    Weeks 1&2 were educational
    Week 3 scoring was initiated
    Heavy use of RTCB@ercot.com email -> FAQ
Highlights of weekly Market Trials slides on next 5 slides

## Slide 8: RTC+B FAQ updated weekly
Worksheets for categories
Posted on RTCBTF Home Page under Key Documents
Common questions/responses in Excel Workbook (target weekly updates)
Search workbook for Key Words

## Slide 9: Detailed Scorecard for Handbook 1 Market submissions:
5/27 Scores for QSEs with Resources – successful submissions for resource types specified in Handbook 1
Scoring:

## Slide 10: Scorecard 2A for Handbook 2- 100% of ICCP Telemetry points added by QSE
5/27 Scores for QSE with Resources - ICCP Telemetry points added in current model.
Scoring:

## Slide 11: Scorecard 2B for Handbook 2- Telemetry checkout meetings completed with ERCOT staff for sample of live data transfer capability
5/27 Scores for QSEs with Resources – Scheduling Check-out and Check-out complete
Scoring:

## Slide 12: What is coming to TAC in July:
At July TAC we will be:
Halfway through market trials
  Assess and cross-check on any show-stopping issue or missing Market Participants
  Plans for Closed Loop LFC Testing (Sept/Oct)
  Plans for Transition/Cutover (eg, dual entry)
Wrapping up changes to Clarification NPRR
Any Questions on RTCBTF activities?
Question here or later can always be directed to RTCB@ERCOT.com
Next few slides on prioritization and protecting the RTC+B resources (Keith Collins)

## Slide 13: ERCOT requests support in prioritizing initiatives during RTC implementation
ERCOT staff is currently being pulled in many directions, including the development of initiatives that could be better prioritized after RTC+B go-live in December 2025
  These efforts are starting to impact the ability of Market Operations and Settlements SMEs to focus on RTC+B implementation efforts
ERCOT requests to pause work on non-priority revision requests and impact analyses that involve market design and settlements matters
  Market Operations plans to pause work on ERCOT-sponsored non-priority items and requests stakeholder support in pausing work on non-priority market sponsored revision requests
  Market Operations will continue to work on priority items including outstanding RTC+B go-live items as well as legislatively mandated items such as Dispatchable Reliability Reserve Service (DRRS) and ERCOT Board approved initiatives such as Demand Response development
  ERCOT has more bandwidth to focus on Transmission Planning and some System Operations related items and these efforts will continue without pause at this time
ERCOT requests that TAC consider directing PRS (or other group) to work with ERCOT staff to develop a roadmap/parking deck process to help manage workflow after RTC+B go live

## Slide 14: Current ERCOT priority initiatives

## Slide 15: Initiatives ERCOT recommends prioritizing after RTC+B go-live
NPRR 1214 – Pricing mechanism enhancements
NPRR 1255 – ESR mitigation
NPRR 1264 – Energy Attributes Certificate
NPRR 1279 – Contracted fuel costs in mitigation
Other pre-NPRR initiatives