## Slide 1
RTC+B Market Trials – QSE Market Submissions and Telemetry Checkout
Testing status
Sruthi Hariharan/Kevin McGarrahan
May 29, 2025

## Slide 2: RTC Market Trials Testing Status
In progress, QSE submission and telemetry verification period – 05/05/2025 – 06/30/2025
QSE Connectivity and Market Submissions
  Submit to Market Management System and Outage Scheduler
  Goal to submit at least one successful transaction for each requested transaction type per QSE once during the 8-week period
QSE Telemetry Setup and Checkout
  QSEs submitted RTC+B Telemetry points, modelling in ERCOT Production ICCP is “In Progress”.
  Reminder: If you have not submitted all RTC+B telemetry points, last date to submit is 05/29/2025 to make it to JUN ML3 production model load so ERCOT can model, plan and complete the telemetry check out by end of June.
    Lead time to get modeled after requests submitted: ~ 3 weeks
  Checkout will be for a sampling of resources within the QSE portfolio to ensure data flowing between ERCOT and QSE
Testing progress being tracked via scorecards posted to the weekly Market Trials Webex meeting pages

## Slide 3: Current issues impacting RTC Market Trials
RTC Market Trials release deployment with fixes for submission related issues:
  User access roles sync between MOTE and RTC market trials (data set-up issue in environment)
    QSE can request assistance for ERCOT to resolve RTCB@ercot.com
  Load Resources on ONL status submitting ECRS in COP getting rejected
  AS Only Offer Submission response notification is missing
  ESR Energy Bid/Offer Curve rejected if last quantity below 1MW
  COP MaxSOC value with 2 decimal places rejected (current Production accepts 2 decimal places)
Release deployment to RTC Market Trials – Wed, 5/28/2025 4 PM

## Slide 4: Next Phase of Market Trials testing – Open Loop testing
Open Loop testing period – 7/7/2025 – 8/29/2025
During monitored Operating Days (Tuesday and Thursday 9am-5pm)
MP activities
    Parallel entry of market submissions for SCED for all resources into RTC Market Trials environment – COP, TPO, AS offers, RTM energy bids, single model ESR submissions. Note – expecting market interface tools and processes are setup to make continuous production quality submissions.
    Parallel entry of telemetry for all the RTC+B points – RTC resource status, AS capability, frequency responsive capacity and min/max limits, power augmentation capacity, and single model ESR telemetry for all points incorporating current resource operations status and capability.
    Note – expecting EMS/AGC/SCADA/other backend calcs are setup and running to continuously feed these values with production quality data.
During non-monitored Operating Days: QSEs can submit market submissions and updated telemetry at their own discretion and continue testing their systems.

## Slide 5: Next Phase of Market Trials testing – Open Loop testing
During monitored Operating Days (Tuesday and Thursday 9am-5pm)
ERCOT activities
  Run RTC+B SCED with regular sync of enforced transmission constraints between current Production and RTC market trials
  Publish the following four Reports:
    SCED Shadow Prices and Binding Transmission Constraints - NP6-86-CD
    LMPs by Resource Nodes, Load Zones and Trading Hubs Market Trials - NP6-788-CD
    Modify Real-Time ORDC and Reliability Deployment Price Adders and Reserves by SCED Interval - NP6-323-CD
    Real-Time Clearing Prices for Capacity by SCED interval – NP6-332-CD

## Slide 6: Market Trials Testing Status
Questions?
Provide feedback to ERCOT on any concerns/questions at rtcb@ercot.com