## Slide 1
Project Update
May 14, 2025
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2025 Release Targets
  Major Projects
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1214 – Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk
    NPRR1226 – Estimated Demand Response Data
    NPRR1238 – Registration of Loads with Curtailable Load Capabilities
    NPRR1267 – Large Load Interconnection Status Report
  Technology Working Group (TWG)
    Next meeting is 5/29/2025
  Aging Projects Related to Revision Requests
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2025 May Release – R5 – 5/29/2025 In Flight
  NPRR1253 – Incorporate ESR Charging Load Information into ICCP
    ICCP and Public API implementation
    Implementation Update
      Background:
        Recall that ERCOT was challenged to support this NPRR’s reporting requirements without disrupting RTC development and took an action item to consider alternative ways to develop the API reporting
        At TAC, ERCOT stated there was an alternative technical reporting solutions, however, it was recently discovered this will not fully meet the protocol requirements (published every 5 minutes, rather than every SCED run)
      ERCOT will proceed as planned with delivery of the new telemetry points and API reporting for ESR charging data
        ERCOT will issue a Market Notice in next 1-2 weeks with more details on how to access the ESR charging (as discussed at TWG meeting)
        ERCOT’s delivery of NPRR1253 will provide the data requested by the market (real-time telemetry and API values for ESR charging)
    The technical delivery for summer 2025 will not strictly meet the protocol language as related to reporting requirements for “each SCED process” so NPRR1253 will remain gray-boxed
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.
Reminder from last month’s report

## Slide 4: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 | NPRR1254 RTC+B Market Trials Sandbox Deployed | NPRR1145 | RTC+B Market Trials begin on 5/5/2025 | NPRR1253 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
 |  |  |  |  | RTC+B Stabilization begins
R7
R8
R10
R11
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR965
NPRR1000
NPRR1014
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216
NPRR1236
NPRR1245
NPRR1246
NOGRR211
NOGRR268
OBDRR020
OBDRR052
PGRR118
E
NPRR963(a) – Portion of NPRR
NPRR1253(a) – ICCP
NPRR1253(b) – Public API
ü
ü
1/1
E
3/1
ü
3/7
ü
ü

## Slide 5: Major Projects
Other Project Highlights

## Slide 6: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1214 | Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | TBD | TBD | $800k-$1.2M, 12-18 months Impacted Systems: MMS, Settlements, Reporting
NPRR1226 | Estimated Demand Response Data | 2026 | 4770 | $100k-$150k, 5-7 months Impacted Systems: EMS, Reporting
NPRR1238 | Registration of Loads with Curtailable Load Capabilities | 2026 | 4535 | $700k-$1M, 10-14 months Impacted Systems: MMS, EMS, NMMS ERCOT continues to discuss the approach to a manual data collection process
NPRR1267 | Large Load Interconnection Status Report | 2026 | 4760 | $100k-$150k, 5-8 months Impacted Systems: RIOO, Public API ERCOT will deliver a monthly manual report until the project to automate it using data sourced from RIOO can be completed
Recommendations for…
PPL Rank Information
Next 2025 Rank in Business Strategy = 4570 Next 2028 Rank in Business Strategy = 5110
Next 2026 Rank in Business Strategy = 4760 Next 2029 Rank in Business Strategy = 5300
Next 2027 Rank in Business Strategy = 4900 Next Rank in Regulatory = 400

## Slide 7: Technology Working Group (TWG)
Agenda for TWG meeting held on 4/24/2025:
Next TWG scheduled for 5/29/2025

## Slide 8: Aging Revision Request Project Review
After the RTC+B project goes live, it will be valuable to have a reprioritized list of pending Revision Request projects
The “Aging Projects Relating to Revision Requests” list used in 2024 has been updated for recent activity
Multi-month review at PRS
  May: Review the contents of the posted aging list
  June: PRS members are asked to be prepared for a priority discussion
  July/August: Follow-up discussion after ERCOT assesses resources on the highest priority items
Legislative priorities will be an important consideration

## Slide 9: Aging Revision Request Review at PRS – Stats
Category | 2024 Process | May 2025
1 – Proceed as Planned | 19 | 10
3 – No Action | 14 | 10
4 – Candidate for Revision / Removal | 2 | 2
5 – Post-RTC+B | 23 | 26
6 – Market Input Needed | 0 | 13
Total | 58 | 61
“2024 Process” is where PRS concluded in August 2024
“May 2025” includes updates since last year’s review
  RR’s started and completed
  Newly approved items
  New items in the queue for PUCT or Board approval
See posted Excel file for details