## Slide 1
RTC+B Task Force
& Market Trials Update
Matt Mereness
TWG
May 29, 2025

## Slide 2: Outline
Update on RTCBTF Issues
Market Trials Update (began 5/5/25)

## Slide 3: RTCBTF Issues List
NPRR1268, 1269, 1270 approved at PUCT (thank you!)
State of Charge and AS Duration (NPRR1282/NOGRR277 target June Board)
Market Trials
Market Trials

## Slide 4: Summary and Timeline of NPRRs
NPRRs approved at PUCT May 15 Open Meeting
  NPRR1268 for ASDC Modifications (IMM sponsor)
  NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  NPRR1270 for AS Qualification details (ERCOT sponsor)
AS Duration / State of Charge (NPRR1282 / NOGRR277)
  Began discussion March 25 and targeting June Board
  NPRR1282 PRS approved / NOGRR277 ROS email approval
Final Clarifying NPRR – Began discussion June 18 May 21 (Sept Board)
  Will be filed and can be tabled at PRS while more discussion at RTCBTF
  10 areas of clarification with minimal to no system changes such as:
    Settlement changes (corrections)
    Retain current NFRC telemetry point (do not retire)
    Offer/Bid structure clean-up (inconsistent protocols)
Remaining Stakeholder path to Board Meetings before Go-Live:
  PRS May 14 > TAC May 28 > Board June 24
  PRS Aug 13 > TAC Aug 28 > Board Sep 23

## Slide 5: Other RTCBTF Updates
Readiness engagement update:
  Developed new folders on RTCBTF home page (done)
    Market Trials folder: Handbooks and supporting materials
    Technical Support folder: Key TWG technical materials
  RTCB@ercot.com mailbox for support of stakeholder implementation questions
  Established FAQ document and posted on RTCBTF home page
  Target to add more training videos in next 30 days (in process)
    Operations / Load Resources / RTC Worksheet Solver Walkthrough
    Day-Ahead Market / Battery
  Following guidance from RTCBTF to engage DSWG separately (done 4/17/25)
  Outreach to Operator Training Seminar and Spring GCPA (complete)
  ERCOT posted sample Settlement Statements/Extracts at May 21 RTCBTF
  Next TWG meeting is May 29
    ERCOT will continue to support detailed technical conversations such as adding telemetry points to network model, digital certificates, accessing ERCOT systems in March/April timeframe
Formal Market Trials began May 5, 2025 (more on next slide)
Closed-Loop LFC Handbook review (critical for market feedback)
Starting internal work on Transition/Cutover Plan (moving earlier in review)
Shams proposal of removing system lambda capping logic deferred until an NPRR is potentially filed (out of scope for RTCBTF)

## Slide 6
Weekly
RTC+B Market Trials Update
ERCOT Staff
May 27, 2025

## Slide 7: Outline
Antitrust Admonition
Reminder of Key Document Postings
Expectations of QSEs for the Week
Provide Update of Cumulative QSE Scorecards
Communicate any known Issues within On-going Trial
Support any Technical and/or Business Questions

## Slide 8
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 9: Market Trials
TAC Approved the Market Trials Plan in October 2024
Discussions with RTC+B Task Force have shaped the Handbooks
Handbook #1- QSE Submission Testing
Handbook #2- QSE Telemetry Tests
Handbook #3- Open Loop SCED
Handbook #4- QSE Telemetry Tests
Handbook #5- Close-Loop LFC Tests (draft)
Handbook #6- Day-Ahead Market Tests (draft)
All are posted on the
RTCBTF Homepage
under Market Trials banner

## Slide 10: Market Trials
Detailed discussions with TWG have provided technical content details
Digital Certificate details
Connectivity/URL details to User Interfaces and APIs
Reminder of how to submit new ICCP requests
RTC and Production Telemetry connectivity
Network Model Load Schedule
All are posted on the
RTCBTF Homepage
under Technical Details banner

## Slide 11: RTC+B FAQ has been updated to 5/22
Worksheets for categories
Posted on RTCBTF Home Page under Key Documents
Common questions/responses in Excel Workbook (target weekly updates)
Search workbook for Key Words

## Slide 12: Resources for May-June Market Trials
Everything needed for current market trials is on RTCBTF home page

## Slide 13: Summary of Market Trial activities for this week and following weeks
QSE connectivity and market submissions
  Submit to Market Management System and Outage Scheduler
  Goal to submit at least one successful transaction for each requested transaction type per QSE once during the 8-week period
QSE telemetry set-up and check-out
  Submit all ICCP requests to ERCOT to add telemetry points
    Lead time to get modeled after requests submitted: ~ 3 weeks
  Check-out will be for a sampling of resources within the QSE portfolio to ensure data flowing between ERCOT/QSE
Scoring continues

## Slide 14: Scorecards for this Market Trials
Handbook Book 1: ERCOT will publish 3 scores, one for each type of Resource: Generation, Load Resources, ESR
    Green: all submissions types completed at least once during the trial
    Yellow: some submissions types completed at least once during the trial
    Red: no submissions received
Handbook 2: ERCOT will publish 2 scorecards:
  Complete all telemetry additions
    Green: all new telemetry added (100%)
    Yellow: some telemetry added
    Red: no new telemetry added
  Check-out complete
    Green: Check-out successfully completed (for sample of Resources)
    Yellow: Check-out scheduled, but not yet complete
    Red: No check-out activity

## Slide 15: Detailed Scorecard for Handbook 1 Market submissions:
5/27 Scores for QSEs with Resources – successful submissions for resource types specified in Handbook 1
Scoring:

## Slide 16: Scorecard 2A for Handbook 2- 100% of ICCP Telemetry points added by QSE
5/27 Scores for QSE with Resources - ICCP Telemetry points added in current model.
Scoring:

## Slide 17: Scorecard 2B for Handbook 2- Telemetry checkout meetings completed with ERCOT staff for sample of live data transfer capability
5/27 Scores for QSEs with Resources – Scheduling Check-out and Check-out complete
Scoring:

## Slide 18: Current ERCOT Issues Impacting Trial sequence
Defects to be resolved in next release (May 28):
  Some user access issues reported (data set-up issue in environment)
    QSE can request assistance for ERCOT to resolve RTCB@ercot.com
  Load Resources submitting ECRS in COP
    Submit COP with 0 MW for ECRS
  AS Only Offer Submission response is missing
    No workaround needed
  ESR Energy Bid/Offer Curve rejected if last quantity below 1MW
    Submit EB/OC with last quantity value at or above 1MW
May 28 - Short outage around 4PM CDT to fix the above issues
Ongoing issue:
  COP MaxSOC value with 2 decimal places rejected
    Submit COP MaxSOC with only 1 decimal place until fix implemented

## Slide 19: Wrap-Up and Questions
Remainder of meeting time to take questions each week-
First round of questions specifically about this Market Trial period
Second round of questions for more general RTC+B as time allows
Can always email the RTC+B Program mailbox: RTCB@ercot.com
FAQ is also a resource for questions that other have asked.
Thanks for your support!