## Recent Revision Requests
|  | REVISION REQUEST PRIORITIZATION | [7 empty] | Total Count = 155 |  | Start here: Filter on "Not Started" and "On Hold"
Group | Target Start | Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Tier | 2025 Notes | 2024 Recommendation | 2024 Notes | Major Impacted System | Major Impacted System % | % Vendor Required | Sponsor | Impacted Systems (Listed on IA)
Grid | 2020-01-01 | Revision Requests | 2020 | 2880 |  |  | SCR804 | PPL | 2019-10-08 | ERCOT GridGeo Access for Transmission Operators | Complete | $400k - $600k | 6 - 12 months | N/A | 0 - Complete | 0 - Complete | Complete | Grid Ops Systems | 94% | 28% | Oncor, AEP
Markets | 2020-03-01 | Revision Requests | 2020 | 2630 |  |  | NPRR905 | PPL | 2019-02-12 | CRR Balancing Account Resettlement | Complete | $60k - $80k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | Complete | S&B | 72% | 0% | Market Settlements Working Group
Other | 2020-03-01 | Revision Requests | 2020 | 2930 |  |  | NPRR902 | PPL | 2019-12-10 | ERCOT Critical Energy Infrastructure Information | Complete | $150k - $225k | 6 - 9 months | N/A | 0 - Complete | 0 - Complete | Complete | Reporting | 55% | 0% | ERCOT
Grid | 2020-05-01 | Revision Requests | 2019 | 230 |  |  | PGRR070 | PPL | 2019-06-11 | Revised Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability Assessments | Complete | $100k - $150k | 12 - 18 months | N/A | 0 - Complete | 0 - Complete | Complete | Reporting | 100% | 0% | ERCOT
Markets | 2020-05-01 | Revision Requests | 2020 | 2990 |  |  | NPRR998 | PPL | 2020-04-14 | ERS Deployment and Recall Messages | Complete | $15k - $25k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 77% | 0% | ERCOT
Other | 2020-07-01 | Regulatory | 2020 | 240 | 1 - Regulatory | 1 - High | NPRR978 | PPL | 2020-02-11 | Alignment with Amendments to PUCT Substantive Rule 25.505 | Complete | $65k-$95k | 6 - 8 months | N/A | 0 - Complete | 0 - Complete | Complete | Reporting | 53% | 0% | ERCOT
Other | 2020-07-01 | Regulatory | 2020 | 250 | 1 - Regulatory | 1 - High | SCR806 | PPL | 2020-02-11 | Adding QSE and DME Information to Disclosure Reports | Complete | $65k-$95k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | Complete | Reporting | 100% | 0% | ERCOT
Grid | 2020-07-01 | Revision Requests | 2020 | 2980 | 2 - High Priority | 1 - High | NPRR974 | PPL | 2020-02-01 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | Complete | $50k-$80k | 5-7 months | N/A | 0 - Complete | 0 - Complete | Previously flagged as "High Priority" | Reporting | 62% | 0% | Texas Competitive Power Associates | DAIP, MMS, External Public
Grid | 2020-11-01 | Regulatory | 2020 | 300 | 1 - Regulatory | 1 - High | NOGRR195 | PPL | 2020-08-01 | Generator Voltage Control Tolerance Band | Complete | $30k-$50k | 4-6 months | N/A | 0 - Complete | 0 - Complete | Complete | EMS | 67% | 0% | ERCOT | EMS, BI & Data Analytics
Grid | 2020-12-01 | Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 1 | Complete | $300k-$450k | 9-12 months | N/A | 0 - Complete | 0 - Complete | Complete | NMMS | 100% | 76% | ERCOT | NMMS
Grid | 2020-12-01 | Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 2 | Complete | $300k-$450k | 9-12 months | N/A | 0 - Complete | 0 - Complete | Complete | NMMS | 100% | 76% | ERCOT | NMMS
Grid | 2021-01-13 | Revision Requests | 2020 | 3080 |  |  | SCR811 | PPL | 2020-10-13 | Integrate Solar (PVGR) Forecasts and Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation | Complete | $60k-$90k | 5-7 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 76% | 35% | ERCOT | MMS, EMS
Markets | 2021-04-13 | Revision Requests | 2021 | 2705 |  |  | NPRR1051 | PPL | 2021-02-09 | Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k-$20k | 3-5 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 100% | 0% | ERCOT | Market Operation Systems
Markets | 2021-07-26 | Revision Requests | 2021 | 3340 |  |  | NPRR1081 | PPL | 2021-06-28 | Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 45% | 0% | IMM, ERCOT | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Retail | 2021-09-01 | Revision Requests | 2021 | 1440 |  |  | SCR815 | PPL | 2021-08-19 | MarkeTrak Administrative Enhancements | Complete | $350k - $550k | 15 - 20 months | N/A | 0 - Complete | 0 - Complete | Complete | Retail | 98% | 0% | TDTMS
Grid | 2021-10-01 | Revision Requests | 2020 | 2910 | 5 - Consider When Efficiencies Exist With Another Effort | 1 - High | SCR800 | PPL | 2019-12-01 | Addition of DC Tie Ramp to GTBD Calculation | Complete | $30k-$50k | 3-5 months | N/A | 0 - Complete | 0 - Complete | Complete | EMS | 38% | 0% | ERCOT | EMS, Data Management, MMS, BI & Data Analytics
Grid | 2021-10-01 | Revision Requests | 2020 | 3040 | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | SCR809 | PPL | 2020-06-01 | Changes to External Telemetry Validations in Resource Limit Calculator | Complete | $40k-$60k | 4-6 months | N/A | 0 - Complete | 0 - Complete | Complete | EMS | 83% | 0% | ERCOT | EMS, BI & Data Analytics
Markets | 2021-10-01 | Revision Requests | 2021 | 3320 |  |  | LPGRR068 | PPL | 2021-06-08 | Add BUSLRG and BUSLRGDG Profile Types | Complete | $20k - $40k | 3 - 6 months | N/A | 0 - Complete | 0 - Complete | Complete | BI & Data Analytics | 53% | 0% | ERCOT
Grid | 2021-11-02 | Revision Requests | 2019 | 2770 | 2 - High Priority | 1 - High | NPRR939 | PPL | 2019-10-01 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k-$100k | 5-7 months | N/A | 0 - Complete | 0 - Complete | Previously flagged as "High Priority" | MMS | 70% | 0% | ERCOT | MMS, DAIP, Integration
Grid | 2021-12-01 | Regulatory | 2022 | 320 | 1 - Regulatory | 1 - High | NPRR1108 | PPL | 2022-04-28 | ERCOT Shall Approve or Deny All Resource Outage Requests | Complete | $275k-$375k | 7-10 months | N/A | 0 - Complete | 0 - Complete | Complete | OS | 58% | 27% | ERCOT | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems
Markets | 2022-01-01 | Revision Requests | 2021 | 3350 |  |  | SCR814 | PPL | 2021-10-28 | Point-to-Point (PTP) Obligation Bid Interval Limit | Complete | $10k-$25k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 100% | 0% | ERCOT | Market Operation Systems
Markets | 2022-03-10 | Regulatory | 2022 | 330 | 1 - Regulatory | 1 - High | NPRR1120 | PPL | 2022-03-31 | Create Firm Fuel Supply Service | Complete | $250k-$400k | 9-12 months | N/A | 0 - Complete | 0 - Complete | Complete | S&B | 70% | 0% | ERCOT | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems
Markets | 2022-03-21 | Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 2 - Medium | NPRR1020a | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - EPS Metering | Complete | $175k-$225k | 8-12 months | N/A | 0 - Complete | 0 - Complete | Complete | EPS Meter | 86% | 0% | Tesla | EPS Meter
Grid | 2022-07-01 | Revision Requests | 2021 | 3250 | 3 - Consider When Resources are Available | 1 - High | SCR812 | PPL | 2020-12-08 | Create Intermittent Renewable Generation Integration Report | Complete | $30k-$60k | 5-7 months | N/A | 0 - Complete | 0 - Complete | Complete | Reporting | 68% | 0% | ERCOT | DAIP, Reporting
Grid | 2022-07-01 | Regulatory | 2022 | 325 | 1 - Regulatory | 1 - High | NPRR1097 | PPL | 2022-03-31 | Create Resource Forced Outage Report | Complete | $20k-$40k | 3-5 months | N/A | 0 - Complete | 0 - Complete | Complete | Reporting | 90% | 0% | ERCOT | Data Management & Analytic Systems, ERCOT Website and MIS Systems
Retail | 2022-07-19 | Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | NPRR1095 | PPL | 2022-03-31 | Texas SET V5.0 Changes | Complete | $1.0M - $1.5M | 16 - 20 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | Registration | 80% | 0% | TX SET Working Group | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems
Retail | 2022-07-19 | Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | SCR817 | PPL | 2022-03-31 | Related to NPRR1095 MarkeTrak Validation Revisions Aligning with Texas SET V5_0 | Complete | $400k - $600k | 10 - 15 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | Retail | 65% | 0% | TDTMS | CRM & Registration Systems, Integration Systems, Retail Systems
Retail | 2022-07-19 | Revision Requests | 2023 | 3700 |  |  | SCR823 | PPL | 2022-11-03 | ERCOT Mass System “County Name” File Updates for Texas SET V5.0 Implementation | Complete | $30k - $40k | N/A | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | Retail | 100% | 0% | TX SET Working Group
Grid | 2022-08-01 | Revision Requests | 2021 | 3330 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1063 | PPL | 2021-08-19 | Dynamic Rating Transparency | Complete | $15k - $25k | 3 - 4 months | N/A | 0 - Complete | 0 - Complete | Complete | MIS | 100% | 0% | DC Energy | ERCOT Website and MIS Systems
Grid | 2022-09-01 | Revision Requests | 2021 | 3290 | 3 - Consider When Resources are Available | 1 - High | NPRR1040 | PPL | 2021-02-09 | Compliance Metrics for Ancillary Service Supply Responsibility | Complete | $20k-$30k | 3-5 months | N/A | 0 - Complete | 0 - Complete | In Flight | BI & Data Analytics | 90% | 0% | LCRA, STEC, Reliant | Data Management & Analytic Systems
Grid | 2022-10-01 | Revision Requests | 2020 | 2855 | 2 - High Priority | 1 - High | SCR807 | PPL | 2020-06-01 | Increase CRR Transaction Capability | Complete | $50k-$100k | 5-7 months | N/A | 0 - Complete | 0 - Complete | Previously flagged as "High Priority" | CRR | 95% | 60% | DC Energy | CRR, Integration
Markets | 2022-10-01 | Revision Requests | 2022 | 2855 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | SCR816 | PPL | 2022-03-31 | CRR Auction Bid Credit Enhancement | Complete | $50k - $80k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | Roadmap - CRR | CRR | 100% | 52% | DC Energy | Congestion Revenue Rights (CRR)
Grid | 2023-04-03 | Revision Requests | 2023 | 3730 |  |  | SCR820 | PPL | 2022-11-03 | Operator Real-Time Messaging During Emergency | Planning | $750k - $1.25M | 18 - 24 months | N/A | 0 - In-Flight - Proceed | 0 - In-Flight - Proceed | In Flight | Grid Ops Systems | 98% | 0% | AEP, CenterPoint
Markets | 2023-04-03 | Revision Requests | 2023 | 3770 |  |  | NPRR1154 | PPL | 2023-01-26 | Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | Complete | $40k - $70k | 5 - 7 months | N/A | 0 - Complete | 0 - Complete | Complete | S&B | 89% | 0% | LCRA | S&B, Data Management & Analytic Systems
Markets | 2023-05-01 | Revision Requests | 2022 | 3630 |  |  | NPRR1112 | PPL | 2022-09-15 | Elimination of Unsecured Credit Limits | Complete | $10k - $20k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Complete | CMM | 100% | 0% | ERCOT | CMM
Grid | 2023-06-01 | Revision Requests | 2020 | 2870 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR962 | PPL | 2019-10-01 | Publish Approved DC Tie Schedules | Complete | $15k-$30k | 3-4 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | Reporting | 86% | 0% | ERCOT | DAIP, BI & Data Analytics
Markets | 2023-06-01 | Revision Requests | 2021 | 3360 | 2 - High Priority | 1 - High | NPRR1090 | PPL | 2021-10-28 | ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Complete | $15k - $25k | 3 - 5 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | Previously flagged as "High Priority" | MMS | 71% | 0% | ERCOT | Data Management & Analytic Systems, Market Operation Systems
Markets | 2023-06-01 | Revision Requests | 2022 | 3590 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1121 | PPL | 2022-07-14 | Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Complete | $25k - $45k | 3 - 5 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | Reporting | 85% | 0% | ERCOT | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems
Grid | 2023-06-01 | Revision Requests | 2023 | 3720 |  |  | NPRR1136 | PPL | 2022-09-15 | Updates to Language Regarding a QSE Moving Ancillary Service Responsibility Between Resources | Complete | $15k - $25k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 100% | 0% | ERCOT | MMS
Markets | 2023-07-01 | Regulatory | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1007 | PPL | 2020-12-08 | Real-Time Co-Optimization (RTC) | Execution | $50M-$55M | 3.5-4.5 years | N/A | 0 - In-Flight - Proceed | 0 - In-Flight - Proceed | Part of RTC+B | MMS | 53% | 24% | ERCOT | MMS, EMS, Integration, DAIP, S&B, NMMS, CMM, OTS, Registration
Markets | 2023-07-01 | Revision Requests | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1204 | PPL | 2024-02-01 | Considerations of State of Charge with Real-Time Co-Optimization Implementation | Execution | $750k - $1.0M | N/A | N/A | 0 - In-Flight - Proceed | 0 - In-Flight - Proceed | Part of RTC+B | MMS | 96% | 77% | ERCOT | MMS, EMS
Grid | 2023-07-01 | Revision Requests | 2020 | 3015 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1014 | PPL | 2020-12-08 | BESTF-4 Energy Storage Resource Single Model | Execution | $3.5M-$4.5M | 2-3 years | N/A | 0 - In-Flight - Proceed | 0 - In-Flight - Proceed | Part of RTC+B | EMS | 60% | 49% | ERCOT | EMS, MMS, DAIP, S&B, OS, Integration, NMMS, RIOO, Registration
Grid | 2023-07-01 | Revision Requests | 2020 | 3060 | 3 - Consider When Resources are Available | 1 - High | NPRR1002 | PPL | 2020-08-01 | BESTF-5 Energy Storage Resource Single Model Registration and Charging Restrictions in Emergency Conditions | Complete | $100k-$200k | 7-10 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | Roadmap - RIOO | RIOO | 83% | 0% | ERCOT | Resource Integration and Ongoing Operations, Integration, DAIP
Markets | 2023-07-01 | Revision Requests | 2022 | 3005 | 2 - High Priority | 1 - High | NPRR1092 | PPL | 2022-04-28 | Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Complete | $50k - $100k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | Previously flagged as "High Priority" | MMS | 100% | 0% | IMM | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems
Grid | 2023-07-01 | Revision Requests | 2023 | 3595 |  |  | NPRR1186 | PPL | TBD | Implement consideration of ESR SOC in ERCOT tools and studies | Complete | $500k - $700k | 7 - 10months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | MMS | 64% | 25% | ERCOT
Markets | 2023-07-01 | Revision Requests | 2023 | 3780 |  |  | NPRR1149 | PPL | 2023-03-23 | Implementation of Systematic Ancillary Service Failed Quantity Charges | Complete | $120k - $160k | 6 - 8 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | S&B | 71% | 0% | ERCOT
Grid | 2023-07-03 | Revision Requests | 2020 | 3010 |  |  | NPRR1026 | PPL | 2020-12-08 | BESTF-7 Self-Limiting Facilities | Complete | $200k-$250k | 7-10 months | N/A | 0 - Complete | 0 - Complete | In Flight | RIOO | 58% | 0% | ERCOT | RIOO-RS, EMS, OTS, DAIP, External Public
Grid | 2023-07-03 | Revision Requests | 2023 | 360 | 1 - Regulatory | 1 - High | NOGRR249 | PPL | 2023-10-12 | Communication of System Operating Limit Exceedances | Complete | $100k - $150k | 5 - 7 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | N/A | N/A | 0% | ERCOT
Other | 2023-07-03 | Revision Requests | 2023 | 3790 |  |  | NPRR1153 | PPL | 2023-03-23 | ERCOT Fee Schedule Changes | Complete | $20k - $30k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Complete | RIOO | 98% | 0% | ERCOT | RIOO, ERCOT.com
Grid | 2023-08-01 | Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | SCR813b | PPL | 2021-10-28 | NMMS Jointly-Rated Equipment Coordination Confirmation | Execution | $100k - $150k | 5 - 7 months | N/A | 0 - In-Flight - Proceed | 0 - In-Flight - Proceed | In Flight | NMMS | 100% | 40% | ERCOT | Network Management Systems
Other | 2023-08-01 | Revision Requests | 2023 | 3620 |  |  | SCR822 | PPL | 2022-09-15 | Create Daily Energy Storage Integration Report and Dashboard | Complete | $60k - $90k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | In Flight | BI & Data Analytics | 44% | 0% | Reliant
Grid | 2023-09-01 | Regulatory | 2023 | 340 | 1 - Regulatory | 1 - High | NPRR1132 | PPL | 2023-01-26 | Communicate Operating Limitations during Cold and Hot Weather Conditions | Complete | $65k - $95k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | Complete | RIOO | 49% | 0% | ERCOT
Grid | 2023-12-01 | Revision Requests | 2022 | 3570 | 2 - High Priority | 2 - Medium | SCR819 | PPL | 2022-03-31 | Improving IRR Control to Manage GTC Stability Limits | Complete | $40k - $60k | 4 - 6 months | N/A | 0 - Complete | 0 - Complete | Previously flagged as "High Priority" | EMS | 70% | 0% | ERCOT | EMS, Market Operation Systems
Markets | 2024-01-01 | Revision Requests | 2022 | 3500 | 3 - Consider When Resources are Available | 1 - High | NPRR1023 | PPL | 2021-04-13 | Change to CRR Repossession Process | On Hold | $250k - $350k | 10 - 14 months | TBD |  | 0 - In-Flight - Proceed | Roadmap - CRR | CRR | 100% | 65% | ERCOT | Congestion Revenue Rights (CRR)
Markets | 2024-04-01 | Revision Requests | 2023 | 3720 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1131 | PPL | 2022-09-15 | Controllable Load Resource Participation in Non-Spin | Complete | $100k - $150k | 6 - 9 months | N/A | 0 - Complete | 1 - Proceed as planned | Resources confirmed for Target Start | MMS | 40% | 0% | ERCOT | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems
Markets | 2024-04-01 | Revision Requests | 2023 | 3740 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1139 | PPL | 2022-11-03 | Adjustments to Capacity Shortfall Ratio Share for IRRs | Complete | $15k - $30k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Resources confirmed for Target Start | S&B | 100% | 0% | ERCOT | S&B
Markets | 2024-06-01 | Revision Requests | 2021 | 3270 | 3 - Consider When Resources are Available | 2 - Medium | NPRR945 | PPL | 2020-12-08 | Net Metering Requirements | Complete | $10k-$20k | 3-4 months | N/A | 0 - Complete | 3 - No action | O&M - working through some issues | RIOO | 64% | 0% | TIEC | RIOO-RS, External Public
Retail | 2024-06-01 | Revision Requests | 2024 | 3600 | 3 - Consider When Resources are Available | 2 - Medium | RMGRR168 | PPL | 2022-09-15 | Modify ERCOT Responsibilities During the Mass Transition | Complete | $50k - $75k | 5 - 8 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | Resources confirmed for Target Start | Registration | 100% | 0% | TX SET Working Group | Registration
Other | 2024-06-01 | Revision Requests | 2024 | 4040 |  |  | NPRR1183 | PPL | 2023-10-12 | ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without ECEII | Complete | $50k - $75k | 4 - 6 months | N/A | 0 - Complete | 1 - Proceed as planned | Scheduled to start in June 2024 | ERCOT.com | 52% | 0% | ERCOT | External Public, DAIP
Grid | 2024-07-01 | Revision Requests | 2019 | 2710 | 3 - Consider When Resources are Available | 1 - High | SCR799 | PPL | 2019-06-01 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Complete | $150k-$250k | 5-7 months | N/A | 0 - Complete | 1 - Proceed as planned | Scheduled to start in June 2024 | SOTE | 100% | 0% | Oncor | SOTE
Markets | 2024-08-01 | Revision Requests | 2021 | 3210 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1004 | PPL | 2020-08-01 | Load Distribution Factor Process Update | Not Started | $45k-$65k | 5-7 months | TBD | 5 - Post-RTC+B | 1 - Proceed as planned |  | MMS | 41% | 0% | ERCOT | MMS, Integration, DAIP, External Public
Markets | 2024-09-01 | Revision Requests | 2022 | 3195 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1091 | PPL | 2021-12-16 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | March PRS: assess for near-term One of multiple SCED pricing run changes. Either bundle or prioritize against other changes to the same process. | MMS | 73% | 40% | Shell Energy | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Markets | 2024-09-01 | Revision Requests | 2024 | 4010 |  |  | NPRR1145 | PPL | 2023-05-11 | Use of State Estimator-Calculated ERCOT-Wide TLFs in Lieu of Seasonal Base Case ERCOT-Wide TLFs for Settlement | Complete | $50k - $80k | 3 - 6 months | N/A | 0 - Complete | 1 - Proceed as planned | Q3 2024 start target (September) | S&B | 54% | 0% | ERCOT | S&B, EMS, Data Mgmt
Grid | 2024-10-01 | Revision Requests | 2019 | 2580 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | PGRR066 | PPL | 2018-12-01 | Interconnection Request Cancellation and Creation of Inactive Status | Complete | $100k-$150k | 4-6 months | N/A | 0 - Complete | 0 - Complete | Roadmap - RIOO | RIOO | 100% | 0% | ERCOT | Resource Integration and Ongoing Operations
Other | 2024-10-01 | Revision Requests | 2020 | 2920 | 3 - Consider When Resources are Available | 2 - Medium | SCR805 | PPL | 2019-12-01 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k-$60k | 4-6 months | TBD | 5 - Post-RTC+B | 1 - Proceed as planned | Candidate for a reporting bundle starting in late 2024 | Reporting | 97% | 0% | ERCOT | DAIP, Data Access & Transparency
Grid | 2024-10-01 | Revision Requests | 2021 | 3200 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | PGRR076 | PPL | 2020-08-01 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Execution | $50k-$75k | 6-9 months | N/A | 0 - In-Flight - Proceed | 1 - Proceed as planned | Roadmap - RIOO | RIOO | 57% | 0% | ERCOT | Resource Integration and Ongoing Operations, Integration, Data Access & Transparency
Other | 2024-10-01 | Revision Requests | 2021 | 3230 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR1035 | PPL | 2020-10-13 | DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k-$40k | 3-5 months | TBD | 5 - Post-RTC+B | 1 - Proceed as planned | Candidate for a reporting bundle starting in late 2024 | Reporting | 83% | 0% | ERCOT | DAIP, External Public
Other | 2024-10-01 | Revision Requests | 2024 | 4090 |  |  | NPRR1208 | PPL | 2024-04-11 | Creation of Invoice Report | Not Started | $40k - $60k | 4 - 6 months | TBD | 5 - Post-RTC+B | 1 - Proceed as planned | Candidate for a reporting bundle starting in late 2024 | Reporting | 91% | 0% | Reliant | DAIP, External Public
Markets | 2025-03-01 | Revision Requests | 2020 | 2850 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR936 | PPL | 2019-10-01 | CRR Account Holder Limits | Not Started | $150k-$250k | 8-10 months | TBD |  | 1 - Proceed as planned | Roadmap - CRR | CRR | 90% | 51% | Engie | CRR, DAIP
Markets | 2025-03-01 | Revision Requests | 2024 | 4060 |  |  | NPRR1184 | PPL | 2023-11-30 | Update to Procedures for Managing Interest on Cash Collateral | Complete | $100k - $150k | 6 - 9 months | N/A | 0 - Complete | 1 - Proceed as planned | Phase 1 completed Phase 2 pending | CMM | 85% | 0% | Tenaska | CMM, Data Management & Analytic Systems, Channel Management Systems, ERCOT Website and MIS Systems
Grid | 2025-07-01 | Revision Requests | 2024 | 3900 |  |  | NOGRR226 | PPL | 2023-01-26 | Addition of Supplemental UFLS Stages | Not Started | $40k - $60k | 3 - 5 months | TBD |  | 1 - Proceed as planned | Work with NOGRR247 | EMS | 95% | 0% | LCRA | EMS, Grid Decision Support Systems
Grid | 2025-07-01 | Revision Requests | N/A | N/A |  |  | NOGRR247 | PPL | 2023-10-12 | Change UFLS Stages and Load Relief Amounts | Not Started | <$10k | 1 - 2 months | TBD |  | 1 - Proceed as planned | Work with NOGRR226 | EMS | 83% | 0% | ERCOT | EMS, Grid Decision Support Systems
Grid | 2025-12-01 | Revision Requests | 2023 | 3710 | 3 - Consider When Resources are Available | 1 - High | SCR818b | PPL | 2022-04-28 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started | $300k - $500k | 9 - 12 months | TBD |  | 1 - Proceed as planned | No impact to other systems | NMMS | 100% | 64% | CenterPoint | Grid Modeling Systems
Grid | 2028-07-01 | Revision Requests | 2019 | 2530 | 5 - Dependent on Other Project | 2 - Medium | NPRR857 | PPL | 2018-10-01 | Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k-$700k | 12-18 months | TBD | 3 - No action | 3 - No action | Southern Spirit | OS | 53% | 25% | ERCOT | OS, EMS, OTS, WAN, NMMS, External Public, Integration, BI & Data Analytics, REG, Data Access & Transparency, DAIP
Grid | 2028-07-01 | Revision Requests | 2021 | 3280 | 9 - No Action Needed | 2 - Medium | NPRR1034 | PPL | 2021-02-09 | Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k-$70k | 5-7 months | TBD | 3 - No action | 3 - No action | Southern Spirit | BI & Data Analytics | 52% | 0% | Southern Cross Transmission | Pi, EIS, NoticeBuilder, MIS
Grid | 2028-07-01 | Revision Requests | 2022 | 2530 | 9 - No Action Needed | 2 - Medium | NPRR1098 | PPL | 2022-03-31 | DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | TBD | 3 - No action | 3 - No action | Southern Spirit | BI & Data Analytics | 100% | 0% | ERCOT | Grid Decision Support Systems
Grid | 2026-10-01 | Revision Requests | 2026 | 4700 |  |  | NOGRR215 | PPL | 2023-10-12 | Limit Use of Remedial Action Schemes | Not Started | $1.0M - $1.5M | 12 - 18 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Note 2026 Priority | MMS | 67% | 65% | ERCOT | MMS, EMS, Reporting
Other | 2025-04-01 | Revision Requests | 2025 | 4510 |  |  | SCR825 | PPL | 2024-04-11 | ERCOT Voice Communications Aggregation | Not Started | $150k-$250k | 7 - 10 months | TBD | 5 - Post-RTC+B | 1 - Proceed as planned | Only undertake when the need arises | Registration | 38% | 0% | Tenaska | CRM & Registration Systems, EMS, Market Operation Systems, Integration, Telecom Systems
Markets | 2027-03-01 | Revision Requests | 2023 | 3750 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR1140 | PPL | 2022-11-03 | Recovering Fuel Costs for Generation Above LSL During RUC-Committed Hours | Not Started | $20k - $30k | 3 - 4 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Currently handling this change with a manual workaround. This is a low priority/low risk as it is dispute based and not common. We do not recommend starting until after RTC+B. | S&B | 100% | 0% | ERCOT | S&B
Markets | 2027-04-01 | Revision Requests | 2019 | 2720 | 2 - High Priority | 1 - High | NPRR904 | PPL | 2019-08-01 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $200k-$300k | 6-9 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | DC Tie curtailment is a rare event. One of multiple SCED pricing run changes. Either bundle or prioritize against other changes to the same process. Previously flagged as "High Priority". | MMS | 85% | 41% | Rainbow | MMS, EMS, BI & Data Analytics, DAIP
Markets | 2027-04-01 | Revision Requests | 2019 | 2720 | 2 - High Priority | 1 - High | OBDRR009 | PPL | 2019-08-01 | ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | On Hold | $30k-$50k | 4-6 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | DC Tie curtailment is a rare event. One of multiple SCED pricing run changes. Either bundle or prioritize against other changes to the same process. Previously flagged as "High Priority". | MMS | 40% | 0% | Rainbow | MMS, DAIP, BI & Data Analytics
Markets | 2027-04-01 | Revision Requests | 2020 | 2840 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR918 | PPL | 2019-10-01 | Validation for PTP Obligations with Links to an Option | Not Started | $30k-$50k | 4-6 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Could be manually verified | MMS | 57% | 0% | ERCOT | MMS, DAIP, Integration
Markets | 2027-04-01 | Revision Requests | 2020 | 2860 | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR941 | PPL | 2019-12-01 | Create a Lower Rio Grande Valley Hub | Not Started | $250k-$350k | 6-8 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Enhancement | MMS | 91% | 75% | DC Energy | MMS, DAIP, EMS, External Public
Markets | 2027-04-01 | Revision Requests | 2020 | 2970 | 3 - Consider When Resources are Available | 2 - Medium | NPRR826 | PPL | 2020-02-01 | Mitigated Offer Caps for RMR Resources | Not Started | $100k-$200k | 6-8 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Limited frequency | MMS | 70% | 68% | Citigroup | MMS, DAIP, External Public, Data Access & Transparency
Markets | 2027-04-01 | Revision Requests | 2024 | 4030 |  |  | NPRR1182 | PPL | 2023-10-12 | Inclusion of Controllable Load Resources and Energy Storage Resources in the Constraint Competitiveness Test Process | Not Started | $60k - $90k | 5 - 7 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B |  | MMS | 100% | 0% | ERCOT | MMS
Grid | 2027-07-01 | Revision Requests | 2018 | 2090 | 5 - Dependent on Other Project | 2 - Medium | NPRR825 | PPL | 2017-12-01 | Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k-$300k | 8-12 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | DC Tie curtailment is a rare event | MMS | 82% | 0% | Rainbow | MMS, Data Access & Transparency, DAIP, Integration
Grid | 2027-07-01 | Revision Requests | 2024 | 4050 |  |  | NPRR1171 | PPL | 2023-10-12 | Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Not Started | $350k - $550k | 9 - 12 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | March PRS: assess for near-term Work with NPRR1213 | MMS | 93% | 50% | ERCOT | MMS, EMS, Data Mgmt, RIOO
Grid | 2027-07-01 | Revision Requests | 2024 | 4050 |  |  | NPRR1213 | PPL | 2024-04-11 | Allow DGRs and DESRs on Circuits Subject to Load Shed to Provide ECRS | Not Started | $350k-$450k | 8 - 12 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | March PRS: assess for near-term Work with NPRR1171 | MMS | 87% | 43% | Enchanted Rock | MMS, Data Mgmt, EMS
Grid | Q2 2024 | Revision Requests | 2024 | 4000 |  |  | SCR821 | PPL | 2023-01-26 | Voltage Set Point Target Information for Distribution Generation Resource (DGR) or Distribution Energy Storage Resource (DESR) | Complete | $25k - $50k | 3 - 5 months | N/A | 0 - Complete | 1 - Proceed as planned | O&M | EMS | 100% | 0% | American Electric Power | EMS
Markets |  | Regulatory | 2019 | 220 |  |  | NPRR885 | PPL | 2019-06-11 | Must-Run Alternative (MRA) Details and Revisions Resulting from PUCT Project No_ 46369, Rulemaking Relating to Reliability Must-Run Service | On Hold | $500k - $700k | 8 - 12 months | TBD | 3 - No action | 3 - No action | Keep On Hold - next steps to be determined | S&B | 29% | 3% | ERCOT | S&B, BI & Data Analytics, MMS, Integration, EMS, Data and Information Products, Registration System, Data Access & Transparency, External Public
Markets |  | Revision Requests | 2019 | 2510 | 3 - Consider When Resources are Available | 1 - High | NPRR829 | PPL | 2017-10-01 | Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k-$300k | 5-10 months | TBD | 3 - No action | 3 - No action | Keep On Hold - next steps to be determined | CMM | 26% | 0% | Enchanted Rock | CMM, NMMS, EMS, REG, Integration, DAIP, Data Access & Transparency
Markets |  | Revision Requests | 2019 | 2520 | 9 - No Action Needed | 3 - Low | NPRR841 | PPL | 2018-02-01 | Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Execution | $60k-$80k | 4-6 months | N/A | 0 - In-Flight - Proceed | 3 - No action | Functionality (and gray box) is removed with RTC+B. If we did it this would be a “throw away”. | S&B | 88% | 0% | ERCOT | S&B, Integration, Data Access & Transparency, CRM & Registration System
Markets |  | Revision Requests | 2019 | 2650 |  |  | NPRR863 | PPL | 2019-02-12 | Creation of ERCOT Contingency Reserve Service (ECRS) | Complete | $2.5M - $3.5M | 20 - 30 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 81% | 60% | STEC
Markets |  | Revision Requests | 2019 | 2700 | 4 - Consider When Resources are Available | 1 - High | NPRR917 | PPL | 2019-08-01 | Nodal Pricing for Settlement Only Distribution Generators (SODGs) and Settlement Only Transmission Generators (SOTGs) | Complete | $300k-$400k | 9-12 months | N/A | 0 - Complete | 0 - Complete | Complete | S&B | 30% | 0% | ERCOT | S&B, Integration, MMS, DAIP, NMMS, CMM, REG, Data Access & Transparency, External Public, BI & Data Analytics
Markets |  | Revision Requests | 2020 | 2515 | 3 - Consider When Resources are Available | 1 - High | NPRR1030 | PPL | 2020-08-01 | Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k-$225k | 8-12 months | TBD | 3 - No action | 3 - No action | No action - expecting replacement NPRR | S&B | 74% | 0% | ERCOT | S&B, DAIP, CMM, Integration
Grid |  | Revision Requests | 2020 | 2800 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR879 | PPL | 2018-12-01 | SCED Base Point, Base Point Deviation, and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k-$250k | 6-9 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Very few IRRs provide Ancillary Services today | Reporting | 46% | 0% | ERCOT | DAIP, S&B, BI & Data Analytics, EMS, NMMS, Integration
Markets |  | Revision Requests | 2020 | 2815 | 2 - High Priority | 1 - High | NPRR963 | PPL | 2020-02-01 | Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model) | Execution | $150k-$200k | 8-12 months | N/A | 0 - In-Flight - Proceed | 3 - No action | Previously flagged as "High Priority" - perhaps not anymore - Combo model - we believe RTC+B implementation will strike this language | Reporting | 31% | 0% | Tenaska | DAIP, S&B, EMS, BI & Data Analytics, Integration
Markets |  | Revision Requests | 2020 | 2890 | 2 - High Priority | 1 - High | NPRR930 | PPL | 2019-10-01 | Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k-$200k | 5-7 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Post-RTC determination at March 2024 PRS | MMS | 74% | 39% | Citigroup | MMS, OS, DAIP, Data Access & Transparency, External Public
Grid |  | Revision Requests | 2020 | 2900 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | NPRR965 | PPL | 2019-12-01 | GREDP Shutdown Exemption | Execution | $10k-$20k | 3-5 months | N/A | 0 - In-Flight - Proceed | 1 - Proceed as planned | Investigating O&M implementation | BI & Data Analytics | 100% | 0% | Luminant | BI & Data Analytics
Grid |  | Revision Requests | 2020 | 3000 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR975 | PPL | 2020-06-01 | Load Forecast Model Transparency | Not Started | $75k-$100k | 6-9 months | TBD | 3 - No action | 3 - No action | ERCOT is reviewing options and will bring a recommendation to a future PRS meeting | EMS | 58% | 0% | Texas Competitive Power Associates | EMS, DAIP, BI & Data Analytics
Grid |  | Revision Requests | 2020 | 3010 | 2 - High Priority | 1 - High | NPRR987 | PPL | 2020-06-01 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | On Hold | $150k-$200k | 6-9 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Post-RTC determination at March 2024 PRS | MMS | 34% | 9% | ERCOT | MMS, S&B, EMS, Integration, BI & Data Analytics, DAIP
Grid |  | Revision Requests | 2020 | 3015 | 9 - No Action Needed | 2 - Medium | NPRR1029 | PPL | 2020-12-08 | BESTF-6 DC-Coupled Resources | Not Started | $800k-$1.2M | 16-24 months | TBD | 4 - Candidate for revision/removal | 4 - Candidate for revision/removal | Need being filled by the implementation of self-limiting resources | EMS | 33% | 36% | ERCOT | EMS, OS, S&B, MMS, RIOO, Integration, DAIP, OTS, NMMS, Registration
Markets |  | Revision Requests | 2020 | 3020 | 3 - Consider When Resources are Available | 1 - High | NPRR1006 | PPL | 2020-06-01 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | $140k-$180k | 6-9 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | March PRS: assess for near-term | MMS | 62% | 29% | TIEC | MMS, DAIP, EMS, S&B, BI & Data Analytics
Markets |  | Revision Requests | 2020 | 3030 | 2 - High Priority | 1 - High | NPRR1019 | PPL | 2020-06-01 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k-$140k | 5-7 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Post-RTC determination at March 2024 PRS | MMS | 98% | 44% | ERCOT | MMS, BI & Data Analytics
Grid |  | Revision Requests | 2020 | 3050 | 3 - Consider When Resources are Available | 2 - Medium | SCR810 | PPL | 2020-08-01 | EMS System Change to Count DC Ties towards the 2% Constraint Activation Criterion | Not Started | $15k-$25k | 3-5 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B |  | EMS | 100% | 0% | Rainbow | EMS
Grid |  | Revision Requests | 2020 | 3070 | 3 - Needed prior to RTC | 1 - High | NPRR1016 | PPL | 2020-08-01 | Clarify Requirements for Distribution Generation Resources (DGRs) and Distribution Energy Storage Resources (DESRs) | Complete | $400k-$550k | 12-18 months | N/A | 0 - Complete | 0 - Complete | Complete | OS | 41% | 16% | ERCOT | OS, EMS, BI & Data Analytics, DAIP, MMS, REG, NMMS, Integration
Grid |  | Revision Requests | 2020 | 3070 |  |  | PGRR082 | PPL | 2020-12-08 | Revise Planning Guide Section 5 and Establish Small Generation Interconnection Process | Complete | $700k-$900k | 18-24 months | N/A | 0 - Complete | 0 - Complete | Complete | RIOO | 92% | 0% | ERCOT | RIOO-RS, NMMS, DAIP
Markets |  | Securitization | 2021 | 320 |  |  | NPRR1103 | PPL | 2021-12-16 | Securitization – PURA Subchapter M Default Charges | Complete | $1.5M - $2M | 18 - 26 months | N/A | 0 - Complete | 0 - Complete | Complete | S&B | 74% | 0% | ERCOT | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems
Grid |  | Revision Requests | 2021 | 3195 |  |  | NPRR1093 | PPL | 2021-10-28 | Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 9 - 12 months | N/A | 0 - Complete | 0 - Complete | Complete | MMS | 68% | 29% | ERCOT | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems
Markets |  | Revision Requests | 2021 | 3220 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1020b | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - Data Agg | Not Started | $175k-$225k | 8-12 months | TBD | SMOGRR034 submitted to strike gray box | 4 - Candidate for revision/removal | All EPS Meter Entities utilize meters that can perform the calculation in the meter | EPS Meter | 86% | 0% | Tesla | S&B
Markets |  | Revision Requests | 2021 | 3260 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1032 | PPL | 2020-12-08 | Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k-$150k | 5-8 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Post-RTC determination at March 2024 PRS | MMS | 64% | 32% | ERCOT | MMS, S&B, DAIP, Integration
Markets |  | Revision Requests | 2021 | 3300 | 9 - No Action Needed | 3 - Low | NPRR1054 | PPL | 2021-02-09 | Removal of Oklaunion Exemption Language | Execution | $10k-$15k | 3-4 months | N/A | 0 - In-Flight - Proceed | 3 - No action | O&M - partially complete - Some of the clean ups will be handled with RTC+B. | S&B | 50% | 0% | American Electric Power | Credit Settlements & Billing Systems, Integration Systems
Markets |  | Revision Requests | 2021 | 3310 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1057 | PPL | 2021-04-13 | Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Post-RTC determination at March 2024 PRS | MMS | 100% | 0% | ERCOT | Market Operation Systems
Grid |  | Regulatory | 2022 | 310 | 1 - Regulatory | 1 - High | PGRR099 | PPL | 2022-03-31 | Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | Complete | $20k - $30k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | In Flight | RIOO | 100% | 0% | ERCOT | Resource Integration and Ongoing Operations
Markets |  | Securitization | 2022 | 320 |  |  | NPRR1114 | PPL | 2022-03-31 | Securitization – PURA Subchapter N Uplift Charges | Complete | $1.8M - $2.4M | 18 - 24 months | N/A | 0 - Complete | 0 - Complete | Complete | S&B | 62% | 0% | ERCOT | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems
Grid |  | Revision Requests | 2022 | 2650 | 2 - High Priority | 1 - High | NPRR1096 | PPL | 2022-03-31 | Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin | Complete | $30k - $50k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Previously flagged as "High Priority" | NDCRC | 65% | 0% | ERCOT | EMS, Grid Decision Support Systems, Grid Modeling Systems
Grid |  | Revision Requests | 2022 | 3020 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1105 | PPL | 2021-12-16 | Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Post-RTC determination at March 2024 PRS | MMS | 55% | 27% | ERCOT | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems
Grid |  | Revision Requests | 2022 | 3195 |  |  | NPRR1101 | PPL | 2021-12-16 | Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non-Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve | Complete | $30k - $50k | 3 - 5 months | N/A | 0 - Complete | 0 - Complete | Complete | BI & Data Analytics | 60% | 0% | ERCOT | Data Management & Analytic Systems, Market Operation Systems
Grid | Q3 2024 | Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | PGRR088 | PPL | 2021-06-08 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Complete | $20k- $40k | 3 - 5 months | N/A | 0 - Complete | 1 - Proceed as planned | O&M | RIOO | 53% | 0% | Reliant | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Grid | Q1 2025 | Revision Requests | 2022 | 3520 | 3 - Consider When Resources are Available | 2 - Medium | RRGRR028 | PPL | 2021-08-19 | Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months | TBD |  | 1 - Proceed as planned | Q4 2025 go-live target | RIOO | 93% | 0% | SPWG | Data Management & Analytic Systems, Resource Integration and Ongoing Operations
Grid | Q3 2025 | Revision Requests | 2022 | 3530 | 3 - Consider When Resources are Available | 2 - Medium | PGRR091 | PPL | 2021-08-19 | FIS Application Completion 60-Day Limit | Not Started | $15k - $30k | 3 - 5 months | TBD |  | 1 - Proceed as planned | Q4 2025 go-live target | RIOO | 100% | 0% | ERCOT | Resource Integration and Ongoing Operations
Grid | Q3 2024 | Revision Requests | 2022 | 3540 | 3 - Consider When Resources are Available | 2 - Medium | PGRR094 | PPL | 2021-10-28 | Clarify Notification Requirement for Generator Construction Commencement or Completion | Complete | $10k - $20k | 1 - 2 months | N/A | 0 - Complete | 1 - Proceed as planned | O&M | RIOO | 100% | 0% | ERCOT | Resource Integration and Ongoing Operations
Grid |  | Revision Requests | 2022 | 3550 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1077 | PPL | 2021-12-16 | Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B | Request at TWG to work into project plans | RIOO | 46% | 0% | ERCOT | EMS, Grid Modeling Systems, Resource Integration and Ongoing Operations
Markets |  | Revision Requests | 2022 | 3610 |  |  | NPRR1135 | PPL | 2022-09-15 | Add On-Line Status Check for Resources Telemetering OFFNS for Ancillary Service Imbalance Settlements | Complete | $15k - $25k | 3 - 4 months | N/A | 0 - Complete | 0 - Complete | Complete | EMS | 100% | 0% | ERCOT
Markets |  | Revision Requests | 2023 | 3715 |  |  | NPRR1058 | PPL | 2022-11-03 | Resource Offer Modernization | Complete | $100K - $150K | 6 - 8 months | N/A | 0 - Complete | 1 - Proceed as planned | Combining with NPRR1131 | MMS | 44% | 0% | Reliant, LCRA, Luminant, Calpine, STEC | MMS, Data Mgmt, S&B, ERCOT.com
Markets |  | Revision Requests | 2023 | 3800 |  |  | NPRR1165 | PPL | 2023-10-12 | Revisions to Requirements of Providing Audited Financial Statements and Providing Independent Amount | Complete | $50k - $100k | 5 - 8 months | N/A | 0 - Complete | 0 - In-Flight - Proceed | In Flight | CMM | 100% | 0% | ERCOT
Grid |  | Revision Requests | 2023 | 3810 |  |  | NPRR1164 | PPL | 2023-10-12 | Black Start and Isochronous Control Capable Identification | Complete | $75k - $150k | 6 - 9 months | N/A | 0 - Complete | 0 - Complete | Complete | NMMS | 46% | 0% | ERCOT
Grid |  | Revision Requests | 2024 | 3760 |  |  | NPRR1128 | PPL | 2023-01-26 | Allow FFR Procurement up to FFR Limit Without Proration | On Hold | $30k - $50k | 3 - 5 months | TBD | 5 - Post-RTC+B | 1 - Proceed as planned | March PRS: assess for near-term | MMS | 64% | 0% | Hunt Energy Network | Market Operation Systems, Data Management & Analytic Systems, Channel Management Systems, Content Delivery Systems
Grid |  | Revision Requests | 2024 | 4020 |  |  | PGRR103 | PPL | 2023-10-12 | Establish Time Limit for Generator Commissioning Following Approval to Synchronize | Not Started | $40k-$60k | 4 - 6 months | TBD | 3 - No action | 3 - No action |  | RIOO | 78% | 0% | ERCOT | RIOO, Registration, Data Mgmt
Markets |  | Revision Requests | 2024 | 4070 |  |  | NPRR1172 | PPL | 2024-02-01 | Fuel Adder Definition, Mitigated Offer Caps, and RUC Clawback | Execution | $65k - $85k | 4 - 7 months | N/A | 0 - In-Flight - Proceed | 1 - Proceed as planned | Final portion will go-live with RTC+B | S&B | 35% | 0% | Consumers | S&B, MMS, Data Mgmt, ERCOT.com
Markets |  | Revision Requests | 2024 | 4080 |  |  | NPRR1201 | PPL | 2024-02-01 | Limitations on Resettlement Timeline and Default Uplift Exposure Adjustments | Not Started | $40k - $70k | 4 - 6 months | TBD | 5 - Post-RTC+B | 5 - Post-RTC+B |  | CMM | 73% | 0% | ERCOT | CMM, S&B
Markets |  | Revision Requests | 2025 | 4500 | 9 - No Action Needed | 2 - Medium | NPRR995 | PPL | 2021-08-19 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k-$1.2M | 20-30 months | TBD | 3 - No action | 3 - No action | Market input needed - Only 2 registered SOESS's - is there a workaround? | RIOO | 44% | 4% | Broad Reach Power | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations
Other |  | Revision Requests | N/A | N/A |  |  | SCR824 | PPL | 2023-11-30 | Increase File Size and Quantity Limits for RIOO Attachments | Complete | <$10k | N/A | N/A | 0 - Complete | 0 - Complete | Complete | RIOO | 100% | 0% | Genesis Consolidated Industries
Markets |  | Regulatory | 2024 | 380 |  |  | NPRR1216 | PPL | 2024-09-26 | Implementation of Emergency Pricing Program | Not Started | $125k - $175k | 5 - 7 months | TBD | 3 - No action | 3 - No action | Already implemented manually. Significant risk until NPRR is approved and automated. | S&B | 39% | 0% | ERCOT | S&B, EMS, Data Mgmt
| 2024-11-06 | Regulatory | 2026 | 390 |  |  | NPRR1188 | PPL | 2024-11-21 | Implement Nodal Dispatch and Energy Settlement for Controllable Load Resources | Not Started | $1.8M - $2.5M | 18 - 24 months | TBD | 6 - Market Input Needed |  |  | MMS | 63% | 43% | ERCOT
|  | Revision Requests | 2025 | 3515 |  |  | NOGRR245 | PPL | 2024-09-26 | Inverter-Based Resource (IBR) Ride-Through Requirements | Planning | $150k - $250k | 6 - 9 months | N/A | 0 - In-Flight - Proceed |  |  | RIOO | 99% | 0% | ERCOT
|  | Revision Requests | 2025 | 4225 |  |  | NPRR1253 | PPL | 2025-03-13 | Incorporate ESR Charging Load Information into ICCP | Execution | $25k - $50k | 1 - 2 months | N/A | 0 - In-Flight - Proceed |  |  | Integration | 87% | 0% | Ammper Power | Integration, EMS
|  | Revision Requests | 2025 | 4550 |  |  | SCR828 | PPL | 2025-03-13 | Increase the Number of Resource Certificates Permitted for an Email Domain in RIOO | Not Started | $50k - $70k | 4 - 6 months | TBD | 6 - Market Input Needed |  |  | RIOO | 100% | 0% | NextEra Energy
|  | Revision Requests | 2025 | 4540 |  |  | NPRR1239 | PPL | 2025-01-16 | Access to Market Information | Not Started | $50k - $100k | 3 - 6 months | TBD | 6 - Market Input Needed |  |  | Reporting | 53% | 0% | ERCOT
|  | Revision Requests | 2025 | 4540 |  |  | NPRR1240 | PPL | 2025-01-16 | Access to Transmission Planning Information | Not Started | $40k - $60k | 3 - 6 months | TBD | 6 - Market Input Needed |  |  | Reporting | 44% | 0% | ERCOT
|  | Revision Requests | 2025 | 4520 |  |  | NPRR1198 | PPL | 2024-07-25 | Congestion Mitigation Using Topology Reconfigurations | Not Started | $50k - $80k | 4 - 7 months | TBD | 6 - Market Input Needed |  |  | EMS | 85% | 0% | EDF Renewables
|  | Revision Requests | 2025 | 4520 |  |  | NPRR1205 | PPL | 2024-06-13 | Revisions to Credit Qualification Requirements of Banks and Insurance Companies | Complete | $80k - $120k | 5 - 8 months | N/A | 0 - Complete |  |  | CMM | 85% | 0% | ERCOT
|  | Revision Requests | 2025 | 4560 |  |  | SCR829 | PPL | 2025-05-15 | API for the NDCRC Application | Not Started | $100k - $200k | 7 - 10 months | TBD | 6 - Market Input Needed |  |  | NDCRC | 96% | 0% | Joint Sponsors
|  | Revision Requests | 2026 | 4740 |  |  | NPRR1249 | PPL | 2025-01-16 | Publication of Shift Factors for All Active Transmission Constraints in the RTM | Not Started | $25k - $45k | 3 - 5 months | TBD | 6 - Market Input Needed |  |  | Reporting | 76% | 0% | CIM View Consulting
|  | Revision Requests | 2026 | 4710 |  |  | NPRR1244 | PPL | 2024-11-21 | Clarification of Controllable Load Resource Primary Frequency Response Responsibilities | Not Started | $70k - $100k | 5 - 7 months | TBD | 6 - Market Input Needed |  |  | EMS | 50% | 0% | Priority Power
|  | Revision Requests | 2026 | 4750 |  |  | SCR830 | Board |  | Expose Limited API Endpoints Using Machine-to-Machine Authentication | Not Started | $100k - $200k | 6 - 9 months | TBD | 6 - Market Input Needed |  |  | RIOO | 100% | 0% | AEP
|  | Revision Requests | 2026 | 4720 |  |  | VCMRR042 | PPL | 2025-05-15 | SO2 and NOx Emission Index Prices Used in Verifiable Cost Calculations | Not Started | $90k - $140k | 6 - 9 months | TBD | 6 - Market Input Needed |  |  | S&B | 63% | 0% | Luminant
|  | Revision Requests | 2026 | 4730 |  |  | NPRR1234 | PPL | 2025-05-15 | Interconnection Requirements for Large Loads and Modeling Standards for Loads 25 MW or Greater | Not Started | $600k-$800k | 12 - 18 months | TBD | 6 - Market Input Needed |  |  | RIOO | 30% | 0% | ERCOT
|  | Revision Requests | 2027 | 4800 |  |  | NPRR1256 | PPL | 2025-05-15 | Settlement of MRA of ESRs | Not Started | $25k - $50k | 3 - 5 months | TBD | 6 - Market Input Needed |  |  | S&B | 100% | 0% | ERCOT
|  | Revision Requests | 2028 | 5100 |  |  | NPRR1229 | Board |  | Real-Time Constraint Management Plan Cost Recovery Payment | Not Started | $100k - $200k | 8 - 10 months | TBD | 6 - Market Input Needed |  |  | S&B | 98% | 0% | STEC
|  | Revision Requests | 2026 | 4770 |  |  | NPRR1226 | Board |  | Estimated Demand Response Data | Not Started | $100k - $150k | 5 - 7 months | TBD | 6 - Market Input Needed |  |  | EMS | 38% | 0% | ERCOT Steel Mills | EMS, Reporting
|  | Revision Requests | 2026 | 4535 |  |  | NPRR1238 | TAC |  | Registration of Loads with Curtailable Load Capabilities | Not Started | $700k-$1M | 10 - 14 months | TBD | 6 - Market Input Needed |  |  | MMS | 69% | 21% | Golden Spread | MMS, EMS, NMMS
|  | Revision Requests | 2026 | 4760 |  |  | NPRR1267 | Board |  | Large Load Interconnection Status Report | Not Started | $100k - $150k | 5 - 8 months | TBD | 6 - Market Input Needed |  |  | RIOO | 49% | 0% | Joint Sponsors | RIOO, Public API
|  | Revision Requests | 2025 | 4570 |  |  | NPRR1277 | PRS |  | Revisions to EAL Formula | Not Started | $90k - $140k | 4 - 6 months | TBD | 6 - Market Input Needed |  |  | CMM | 93% | 0% | ERCOT | CMM, Reporting
|  | Revision Requests | 2026 | 4780 |  |  | NPRR1281 | PRS |  | Improvements to Alternate FFSS Resource Designation | Not Started | $75k-$100k | 6 - 8 months | TBD | 6 - Market Input Needed |  |  | S&B | 87% | 0% | LCRA | S&B, Reporting

## Summary Info
Count by Status |  | Count by 2024 Recommendation |  | Count by Priority |  | Complete by Priority |  | Not Started / On Hold by Priority |  | Not Started by Priority |  | Not Started by Priority - ERCOT Submitted
Complete | 76 | 0 - Complete | 53 | 2017 | 2 | 2017 | 2 | 2017 | 0 | 2017 | 0 | 2017 | 0
Execution | 11 | 0 - In-Flight - Proceed | 18 | 2018 | 1 | 2018 | 0 | 2018 | 1 | 2018 | 1 | 2018 | 0
Planning | 2 | 1 - Proceed as Planned | 24 | 2019 | 12 | 2019 | 6 | 2019 | 5 | 2019 | 1 | 2019 | 1
On Hold | 10 | 3 - No Action | 14 | 2020 | 36 | 2020 | 17 | 2020 | 14 | 2020 | 10 | 2020 | 5
Not Started | 56 | 4 - Candidate for revision/removal | 2 | 2021 | 21 | 2021 | 13 | 2021 | 6 | 2021 | 6 | 2021 | 4
|  | 5 - Post-RTC+B | 23 | 2022 | 23 | 2022 | 15 | 2022 | 7 | 2022 | 6 | 2022 | 4
|  | Blank | 21 | 2023 | 19 | 2023 | 16 | 2023 | 2 | 2023 | 2 | 2023 | 1
|  |  |  | 2024 | 15 | 2024 | 5 | 2024 | 9 | 2024 | 8 | 2024 | 5
|  |  |  | 2025 | 11 | 2025 | 1 | 2025 | 8 | 2025 | 8 | 2025 | 3
|  |  |  | 2026 | 11 | 2026 | 0 | 2026 | 11 | 2026 | 11 | 2026 | 3
|  |  |  | 2027 | 1 | 2027 | 0 | 2027 | 1 | 2027 | 1 | 2027 | 1
|  |  |  | 2028 | 1 | 2028 | 0 | 2028 | 1 | 2028 | 1 | 2028 | 0
|  |  |  | N/A | 2 | N/A | 1 | N/A | 1 | N/A | 1 | N/A | 1
Total | 155 | Total | 155 | Total | 155 | Total | 76 | Total | 66 | Total | 56 | Total | 28

## Prev List - Complete or Active (hidden)
REVISION REQUEST PRIORITIZATION - Previous List - Projects Complete or In-Flight | [14 empty] | Count = 10
Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2020 | 300 | 1 - Regulatory | 1 - High | NOGRR195 | PPL | 2020-08-01 | Generator Voltage Control Tolerance Band | Complete | $30k-$50k | 4-6 months | EMS | 67% | 0% | EMS, BI & Data Analytics | Implemented 2021-R1
Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 1 | Complete | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS | Single IA - split into multiple projects Phase 1 implemented in July 2021
Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 2 | Planning | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS | Single IA - split into multiple projects Phase 2 target implementation in late 2022
Revision Requests | 2019 | 2700 | 4 - Consider When Resources are Available | 1 - High | NPRR917 | PPL | 2019-08-01 | Nodal Pricing for Settlement Only Distribution Generators (SODGs) and Settlement Only Transmission Generators (SOTGs) | Complete | $300k-$400k | 9-12 months | S&B | 30% | 0% | S&B, Integration, MMS, DAIP, NMMS, CMM, REG, Data Access & Transparency, External Public, BI & Data Analytics | DGR/DESR Implementation - 2022-R1
Revision Requests | 2019 | 2770 | 2 - High Priority | 1 - High | NPRR939 | PPL | 2019-10-01 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k-$100k | 5-7 months | MMS | 70% | 0% | MMS, DAIP, Integration | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 2910 | 5 - Consider When Efficiencies Exist With Another Effort | 1 - High | SCR800 | PPL | 2019-12-01 | Addition of DC Tie Ramp to GTBD Calculation | Complete | $30k-$50k | 3-5 months | EMS | 38% | 0% | EMS, Data Management, MMS, BI & Data Analytics | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 2980 | 2 - High Priority | 1 - High | NPRR974 | PPL | 2020-02-01 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | Complete | $50k-$80k | 5-7 months | DAIP | 62% | 0% | DAIP, MMS, External Public | Implemented 2021-R3 | Can NPRR975 be worked alongside NPRR974?
Revision Requests | 2020 | 3040 | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | SCR809 | PPL | 2020-06-01 | Changes to External Telemetry Validations in Resource Limit Calculator | Complete | $40k-$60k | 4-6 months | EMS | 83% | 0% | EMS, BI & Data Analytics | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 3070 | 3 - Needed prior to RTC | 1 - High | NPRR1016 | PPL | 2020-08-01 | Clarify Requirements for Distribution Generation Resources (DGRs) and Distribution Energy Storage Resources (DESRs) | Complete | $400k-$550k | 12-18 months | OS | 41% | 16% | OS, EMS, BI & Data Analytics, DAIP, MMS, REG, NMMS, Integration | DGR/DESR Implementation - 2022-R1
Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - EPS Metering | Execution | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | EPS Meter | Single IA - split into multiple projects Specific resources were available for this portion of NPRR1020

## Prev List - Not Started (hidden)
REVISION REQUEST PRIORITIZATION - Previous List - Projects Not Started | [15 empty] | Count = 29
Category | Priority | Rank | Prioritization Category | Revised Prioritization Recommendation | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Contact (Remove before sending to PRS) | ERCOT Recommendation | ERCOT Comments / Additional Detail | PRS Comments
Revision Requests | 2018 | 2090 | 6 - Dependent on Other Project | 5 - Dependent on Other Project | 2 - Medium | NPRR825 | PPL | 2017-12-01 | Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k-$300k | 8-12 months | MMS | 82% | 0% | MMS, Data Access & Transparency, DAIP, Integration | Maggio | 9 - TBD | Dependent on internal ERCOT project with no clear timeline Partial delivery in Oct. 2018
Revision Requests | 2019 | 2510 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR829 | PPL | 2017-10-01 | Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k-$300k | 5-10 months | CMM | 26% | 0% | CMM, NMMS, EMS, REG, Integration, DAIP, Data Access & Transparency | Ruane | 9 - TBD | We would like to get this On Hold effort going again in 2022 but we need to figure out resource constraints with Securitization and the Treasury Management project first
Revision Requests | 2020 | 2515 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR1030 | PPL | 2020-08-01 | Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k-$225k | 8-12 months | S&B | 74% | 0% | S&B, DAIP, CMM, Integration | Ruane | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Lower priority then Securitization Manual workaround in place to monitor market activity
Revision Requests | 2019 | 2520 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR841 | PPL | 2018-02-01 | Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Not Started | $60k-$80k | 4-6 months | S&B | 88% | 0% | S&B, Integration, Data Access & Transparency, CRM & Registration System | Ruane | 6 - Candidate for deletion |  | Consider filing an NPRR to strike the grey-boxes for NPRR841 (or let RTC NPRRs strike it)
Revision Requests | 2019 | 2530 | 6 - Dependent on Other Project | 5 - Dependent on Other Project | 2 - Medium | NPRR857 | PPL | 2018-10-01 | Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k-$700k | 12-18 months | OS | 53% | 25% | OS, EMS, OTS, WAN, NMMS, External Public, Integration, BI & Data Analytics, REG, Data Access & Transparency, DAIP | Various | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2019 | 2580 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | PGRR066 | PPL | 2018-12-01 | Interconnection Request Cancellation and Creation of Inactive Status | Not Started | $100k-$150k | 4-6 months | RIOO | 100% | 0% | Resource Integration | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete ERCOT can keep the existing manual workaround until resources are available
Revision Requests | 2019 | 2710 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | SCR799 | PPL | 2019-06-01 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | $150k-$250k | 5-7 months | SOTE | 100% | 0% | SOTE | Huang | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Material impact on EMS Production Support team Low probability of fitting this into the plan in advance of the EMS Upgrade system freeze
Revision Requests | 2019 | 2720 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR904 | PPL | 2019-08-01 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $200k-$300k | 6-9 months | MMS | 85% | 41% | MMS, EMS, BI & Data Analytics, DAIP | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2019 | 2720 | 2 - High Priority | 2 - High Priority | 1 - High | OBDRR009 | PPL | 2019-08-01 | ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | On Hold | $30k-$50k | 4-6 months | MMS | 40% | 0% | MMS, DAIP, BI & Data Analytics | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2020 | 2800 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR879 | PPL | 2018-12-01 | SCED Base Point, Base Point Deviation, and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k-$250k | 6-9 months | DAIP | 46% | 0% | DAIP, S&B, BI & Data Analytics, EMS, NMMS, Integration | Billo | 3 - 2023 project candidate | Moved to 2023 - this cleared resources for higher priority reporting efforts such as NPRR1097, NPRR1040, and SCR812
Revision Requests | 2020 | 2815 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR963 | PPL | 2020-02-01 | Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model) | On Hold | $150k-$200k | 8-12 months | DAIP | 31% | 0% | DAIP, S&B, EMS, BI & Data Analytics, Integration | Sharma | 3 - 2023 project candidate | Battery Energy Storage (BES) PR353-01 component This work that can't be fit into the plan until after ECRS implementation
Revision Requests | 2020 | 2840 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR918 | PPL | 2019-10-01 | Validation for PTP Obligations with Links to an Option | Not Started | $30k-$50k | 4-6 months | MMS | 57% | 0% | MMS, DAIP, Integration | Sharma | 3 - 2023 project candidate | This NPRR introduces hourly submission validation versus current peak load value based validation.
Revision Requests | 2020 | 2850 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR936 | PPL | 2019-10-01 | CRR Account Holder Limits | Not Started | $150k-$250k | 8-10 months | CRR | 90% | 51% | CRR, DAIP | Sharma | 3 - 2023 project candidate | CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2020 | 2855 | 4 - Consider When Resources are Available | 2 - High Priority | 1 - High | SCR807 | PPL | 2020-06-01 | Increase CRR Transaction Capability | Not Started | $50k-$100k | 5-7 months | CRR | 95% | 60% | CRR, Integration | Sharma | 1 - Planned for 2022 start | Q3 2022 start CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2020 | 2860 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR941 | PPL | 2019-12-01 | Create a Lower Rio Grande Valley Hub | Not Started | $250k-$350k | 6-8 months | MMS | 91% | 75% | MMS, DAIP, EMS, External Public | Maggio | 7 - Market input requested | Consistent with the August 2020 discussion, this is lower priority and can be reconsidered when critical efforts are complete
Revision Requests | 2020 | 2870 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR962 | PPL | 2019-10-01 | Publish Approved DC Tie Schedules | Not Started | $15k-$30k | 3-4 months | DAIP | 86% | 0% | DAIP, BI & Data Analytics | Maggio | 7 - Market input requested | Impact is relatively low and limited to reporting. Data seems useful but the usefulness is dependent on the market participants' points of view.
Revision Requests | 2020 | 2890 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR930 | PPL | 2019-10-01 | Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k-$200k | 5-7 months | MMS | 74% | 39% | MMS, OS, DAIP, Data Access & Transparency, External Public | Maggio | 7 - Market input requested | Partially implemented. Remaining component has a work-around that's a behavior rule for QSEs.
Revision Requests | 2020 | 2900 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | NPRR965 | PPL | 2019-12-01 | GREDP Shutdown Exemption | Not Started | $10k-$20k | 3-5 months | BI & Data Analytics | 100% | 0% | BI & Data Analytics | Billo | 9 - TBD | Consider bundling this with NPRR879 which also has a BI & Data Analytics portion that impacts GREDP.
Revision Requests | 2020 | 2920 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | SCR805 | PPL | 2019-12-01 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k-$60k | 4-6 months | DAIP | 97% | 0% | DAIP, Data Access & Transparency | Billo | 7 - Market input requested
Revision Requests | 2020 | 2970 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR826 | PPL | 2020-02-01 | Mitigated Offer Caps for RMR Resources | Not Started | $100k-$200k | 6-8 months | MMS | 70% | 68% | MMS, DAIP, External Public, Data Access & Transparency | Maggio | 7 - Market input requested | Priority is less clear due to not currently having any RMR contracts in place.
Revision Requests | 2020 | 3000 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR975 | PPL | 2020-06-01 | Load Forecast Model Transparency | Not Started | $75k-$100k | 6-9 months | EMS | 58% | 0% | EMS, DAIP, BI & Data Analytics | Billo | 9 - TBD | ERCOT is evaluating options for replacing the A3 and A6 models.
Revision Requests | 2020 | 3010 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR987 | PPL | 2020-06-01 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | On Hold | $150k-$200k | 6-9 months | MMS | 34% | 9% | MMS, S&B, EMS, Integration, BI & Data Analytics, DAIP | Sharma | 3 - 2023 project candidate | Battery Energy Storage (BES) PR353-01 component "ESR Contribution to PRC" already in-flight targeting 2022-R5 This row represents the remaining work that can't be fit into the plan until after ECRS implementation
Revision Requests | 2020 | 3020 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR1006 | PPL | 2020-06-01 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | $140k-$180k | 6-9 months | MMS | 62% | 29% | MMS, DAIP, EMS, S&B, BI & Data Analytics | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2020 | 3030 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR1019 | PPL | 2020-06-01 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k-$140k | 5-7 months | MMS | 98% | 44% | MMS, BI & Data Analytics | Maggio | 7 - Market input requested | Partially implemented. Remaining component has a work-around that's a behavior rule for QSEs.
Revision Requests | 2020 | 3050 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | SCR810 | PPL | 2020-08-01 | EMS System Change to Count DC Ties towards the 2% Constraint Activation Criterion | Not Started | $15k-$25k | 3-5 months | EMS | 100% | 0% | EMS | Huang | 9 - TBD | This SCR adds logic to ERCOT’s EMS system to remove the flag that indicates to the ERCOT Operator that a unit representing a DC Tie does not count toward the 2% criterion for activating transmission constraints
Revision Requests | 2020 | 3060 | 3 - Needed prior to RTC | 3 - Consider When Resources are Available | 1 - High | NPRR1002 | PPL | 2020-08-01 | BESTF-5 Energy Storage Resource Single Model Registration and Charging Restrictions in Emergency Conditions | On Hold | $100k-$200k | 7-10 months | RIOO | 83% | 0% | Resource Integration, Integration, DAIP | Blevins | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Battery Energy Storage (BES) PR353-01 component "Charging Restrictions in Emergency Conditions" already in-flight targeting 2022-R5 This row is a potential stand-alone project to run alongside RARF Replacement to leverage resources as they become free for development and testing by end of 2022
Revision Requests | 2021 | 3200 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | PGRR076 | PPL | 2020-08-01 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Not Started | $50k-$75k | 6-9 months | RIOO | 57% | 0% | Resource Integration, Integration, Data Access & Transparency | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2021 | 3210 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR1004 | PPL | 2020-08-01 | Load Distribution Factor Process Update | Not Started | $45k-$65k | 5-7 months | MMS | 41% | 0% | MMS, Integration, DAIP, External Public | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | IMM has asked about the status of this RR MMS impacts
Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - Data Agg | Not Started | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | S&B | Ruane | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Data Agg portion of NPRR1020 Same solution is available with current EPS meter configuration schemes EPS Metering portion is already in-flight

## New Items - Complete or Active (hidden)
REVISION REQUEST PRIORITIZATION - New Items - Projects Complete or In-Flight | [14 empty] | Count = 12
Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2022 | 310 | 1 - Regulatory |  | PGRR099 | PPL | 2022-03-31 | Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | Execution | $20k - $30k | 3 - 5 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations
Securitization | 2021 | 320 | 1 - Regulatory |  | NPRR1103 | PPL | 2021-12-16 | Securitization – PURA Subchapter M Default Charges | Execution | $1.5M - $2M | 18 - 26 months | S&B | 74% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | Manual solution implemented Automation project expected to start later in 2022
Securitization | 2022 | 320 | 1 - Regulatory |  | NPRR1114 | PPL | 2022-03-31 | Securitization – PURA Subchapter N Uplift Charges | Execution | $1.8M - $2.4M | 18 - 24 months | S&B | 62% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | Implemented late March 2022 Currently in Stabilization Included NPRR1122, NPRR1123, and NPRR1125
Regulatory | 2022 | 320 | 1 - Regulatory |  | NPRR1108 | PPL | 2022-04-28 | ERCOT Shall Approve or Deny All Resource Outage Requests | Execution | $275k-$375k | 7-10 months | OS | 58% | 27% | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems | Target implementation - 2022-R4
Regulatory | 2022 | 330 | 1 - Regulatory |  | NPRR1120 | PPL | 2022-03-31 | Create Firm Fuel Supply Service | Planning | $250k-$400k | 9-12 months | S&B | 70% | 0% | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems | Expected implementation in Q4 2022
Revision Requests | 2021 | 2705 |  |  | NPRR1051 | PPL | 2021-02-09 | Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k-$20k | 3-5 months | MMS | 100% | 0% | Market Operation Systems | Implemented 2021-R3
Revision Requests | 2020 | 3010 |  |  | NPRR1026 | PPL | 2020-12-08 | BESTF-7 Self-Limiting Facilities | Execution | $200k-$250k | 7-10 months | RIOO | 58% | 0% | RIOO-RS, EMS, OTS, DAIP, External Public | RIOO portion is in progress
Revision Requests | 2020 | 3070 |  |  | PGRR082 | PPL | 2020-12-08 | Revise Planning Guide Section 5 and Establish Small Generation Interconnection Process | Complete | $700k-$900k | 18-24 months | RIOO | 92% | 0% | RIOO-RS, NMMS, DAIP | DGR/DESR Implementation - 2022-R1
Revision Requests | 2020 | 3080 |  |  | SCR811 | PPL | 2020-10-13 | Integrate Solar (PVGR) Forecasts and Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation | Complete | $60k-$90k | 5-7 months | MMS | 76% | 35% | MMS, EMS | Implemented 2021-R3
Revision Requests | 2021 | 3195 |  |  | NPRR1093 | PPL | 2021-10-28 | Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 9 - 12 months | MMS | 68% | 29% | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2021 | 3340 |  |  | NPRR1081 | PPL | 2021-06-28 | Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | MMS | 45% | 0% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Manual solution implemented on 7/1/2021 Automation completed in September 2021
Revision Requests | 2021 | 3350 |  |  | SCR814 | PPL | 2021-10-28 | Point-to-Point (PTP) Obligation Bid Interval Limit | Complete | $10k-$25k | 3 - 5 months | MMS | 100% | 0% | Market Operation Systems | Implemented 2022-R3 Currently in Stabilization

## New Items - Not Started (hidden)
REVISION REQUEST PRIORITIZATION - New Items - Projects Not Started | [14 empty] | Count = 34
Category | Priority | Rank | Prioritization Category Recommendation | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Contact (Remove before sending to PRS) | ERCOT Recommendation | ERCOT Comments / Additional Details | PRS Comments
Regulatory | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1007 | PPL | 2020-12-08 | Real-Time Co-Optimization (RTC) | On Hold | $50M-$55M | 3.5-4.5 years | MMS | 53% | 24% | MMS, EMS, Integration, DAIP, S&B, NMMS, CMM, OTS, Registration | Maggio | 9 - TBD | Pending further direction from PUCT Represents NPRRs 1007-1013, NOGRR211, and OBDRR020
Regulatory | 2022 | 325 | 1 - Regulatory | 1 - High | NPRR1097 | PPL | 2022-03-31 | Create Resource Forced Outage Report | Not Started | $20k-$40k | 3-5 months | DAIP | 90% | 0% | Data Management & Analytic Systems, ERCOT Website and MIS Systems | Huang | 1 - Planned for 2022 start | Q3 2022 start Need to implement by end of 2022 to meet PUCT target Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2022 | 2530 | 9 - No Action Needed | 2 - Medium | NPRR1098 | PPL | 2022-03-31 | DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | BI & Data Analytics | 100% | 0% | Grid Decision Support Systems | Various | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2022 | 2650 | 2 - High Priority | 1 - High | NPRR1096 | PPL | 2022-03-31 | Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin | Not Started | $30k - $50k | 3 - 5 months | NDCRC | 65% | 0% | Energy Management Systems, Grid Decision Support Systems, Grid Modeling Systems | Billo | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | ECRS portion - 2023 Non-Spin portion - 2022 candidate
Revision Requests | 2022 | 2855 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | SCR816 | PPL | 2022-03-31 | CRR Auction Bid Credit Enhancement | Not Started | $50k - $80k | 4 - 6 months | CRR | 100% | 52% | Congestion Revenue Rights (CRR) | Sharma | 1 - Planned for 2022 start | Q3 2022 start CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2022 | 3005 | 2 - High Priority | 1 - High | NPRR1092 | PPL | 2022-04-28 | Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Not Started | $50k - $100k | 4 - 6 months | MMS | 100% | 0% | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | "Reduce RUC Offer Floor" change implemented on 5/13/2022 This project implements the "Limit RUC Opt-Out Provision" portion
Revision Requests | 2020 | 3015 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1014 | PPL | 2020-12-08 | BESTF-4 Energy Storage Resource Single Model | Not Started | $3.5M-$4.5M | 2-3 years | EMS | 60% | 49% | EMS, MMS, DAIP, S&B, OS, Integration, NMMS, RIOO, Registration | Sharma | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | NPRR was written with RTC design. This work can't be fit in to the plan until after EMS upgrade.
Revision Requests | 2020 | 3015 | 9 - No Action Needed | 2 - Medium | NPRR1029 | PPL | 2020-12-08 | BESTF-6 DC-Coupled Resources | Not Started | $800k-$1.2M | 16-24 months | EMS | 33% | 36% | EMS, OS, S&B, MMS, RIOO, Integration, DAIP, OTS, NMMS, Registration | Sharma | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | NPRR was written with RTC design. This work can't be fit in to the plan until after EMS upgrade.
Revision Requests | 2022 | 3020 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1105 | PPL | 2021-12-16 | Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months | MMS | 55% | 27% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2022 | 3195 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1091 | PPL | 2021-12-16 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | MMS | 73% | 40% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Maggio | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2021 | 3230 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR1035 | PPL | 2020-10-13 | DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k-$40k | 3-5 months | DAIP | 83% | 0% | DAIP, External Public | Maggio | 7 - Market input requested | Impact is relatively low and limited to reporting. Data seems useful but the usefulness is dependent on the market participants' points of view.
Revision Requests | 2021 | 3250 | 3 - Consider When Resources are Available | 1 - High | SCR812 | PPL | 2020-12-08 | Create Intermittent Renewable Generation Integration Report | Not Started | $30k-$60k | 5-7 months | DAIP | 68% | 0% | DAIP, Reporting | Billo | 1 - Planned for 2022 start | Q3 2022 start Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2021 | 3260 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1032 | PPL | 2020-12-08 | Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k-$150k | 5-8 months | MMS | 64% | 32% | MMS, S&B, DAIP, Integration | Maggio | 3 - 2023 project candidate | Addresses a known operational issue/inefficiency
Revision Requests | 2021 | 3270 | 3 - Consider When Resources are Available | 2 - Medium | NPRR945 | PPL | 2020-12-08 | Net Metering Requirements | Not Started | $10k-$20k | 3-4 months | RIOO | 64% | 0% | RIOO-RS, External Public | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2021 | 3280 | 9 - No Action Needed | 2 - Medium | NPRR1034 | PPL | 2021-02-09 | Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k-$70k | 5-7 months | Pi | 64% | 0% | Pi, EIS, NoticeBuilder, MIS | Various | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2021 | 3290 | 3 - Consider When Resources are Available | 1 - High | NPRR1040 | PPL | 2021-02-09 | Compliance Metrics for Ancillary Service Supply Responsibility | Not Started | $20k-$30k | 3-5 months | BI & Data Analytics | 90% | 0% | Data Management & Analytic Systems | Billo | 1 - Planned for 2022 start | Q3 2022 start Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2021 | 3300 | 9 - No Action Needed | 3 - Low | NPRR1054 | PPL | 2021-02-09 | Removal of Oklaunion Exemption Language | Not Started | $10k-$15k | 3-4 months | S&B | 50% | 0% | Credit Settlements & Billing Systems, Integration Systems | Ruane | 8 - Work into other projects where possible | Not urgent Work this into other projects where possible
Revision Requests | 2021 | 3310 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1057 | PPL | 2021-04-13 | Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months | MMS | 100% | 0% | Market Operation Systems | Maggio | 3 - 2023 project candidate | Impact is relatively low and would like to address this issue, even though it's a low probability event
Revision Requests | 2021 | 3330 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1063 | PPL | 2021-08-19 | Dynamic Rating Transparency | Not Started | $15k - $25k | 3 - 4 months | MIS | 100% | 0% | ERCOT Website and MIS Systems | Blevins | 1 - Planned for 2022 start | Q4 2022 start Posting the proposed information will increase transparency of these changes and thereby improve Market Participants’ ability to assess and hedge risk
Revision Requests | 2021 | 3360 | 2 - High Priority | 1 - High | NPRR1090 | PPL | 2021-10-28 | ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Not Started | $15k - $25k | 3 - 5 months | MMS | 71% | 0% | Data Management & Analytic Systems, Market Operation Systems | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Impact is relatively low and would like to address this issue.
Revision Requests | 2022 | 3500 | 3 - Consider When Resources are Available | 1 - High | NPRR1023 | PPL | 2021-04-13 | Change to CRR Repossession Process | Not Started | $250k - $350k | 10 - 14 months | CRR | 100% | 65% | Congestion Revenue Rights (CRR) | Sharma | 3 - 2023 project candidate | CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | PGRR088 | PPL | 2021-06-08 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Not Started | $20k- $40k | 3 - 5 months | RIOO | 53% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Desired to start after completion of NMMS Tech Health project - Q1 2023
Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | SCR813 | PPL | 2021-10-28 | NMMS Jointly-Rated Equipment Coordination Confirmation | Not Started | $100k - $150k | 5 - 7 months | NMMS | 100% | 40% | Network Management Systems | Blevins | 3 - 2023 project candidate | Desired to start after completion of NMMS Tech Health project - Q1 2023
Revision Requests | 2022 | 3520 | 3 - Consider When Resources are Available | 2 - Medium | RRGRR028 | PPL | 2021-08-19 | Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months | RIOO | 93% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3530 | 3 - Consider When Resources are Available | 2 - Medium | PGRR091 | PPL | 2021-08-19 | FIS Application Completion 60-Day Limit | Not Started | $15k - $30k | 3 - 5 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3540 | 3 - Consider When Resources are Available | 2 - Medium | PGRR094 | PPL | 2021-10-28 | Clarify Notification Requirement for Generator Construction Commencement or Completion | Not Started | $10k - $20k | 1 - 2 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3550 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1077 | PPL | 2021-12-16 | Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months | RIOO | 46% | 0% | Energy Management Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations | Blevins | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3570 | 2 - High Priority | 2 - Medium | SCR819 | PPL | 2022-03-31 | Improving IRR Control to Manage GTC Stability Limits | Not Started | $40k - $60k | 4 - 6 months | EMS | 70% | 0% | Energy Management Systems, Market Operation Systems | Billo | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | This SCR will improve the dispatch of Base Points to Resources to account for the ramping of uncurtailed IRRs and will reduce the chance of violating Generic Transmission Limits (GTLs)
Revision Requests | 2022 | 3590 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1121 | Pending PUCT Approval |  | Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Not Started | $25k - $45k | 3 - 5 months | DAIP | 85% | 0% | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems | Maggio | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Impact is relatively low and limited to reporting. Would like to address this manual process.
Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | NPRR1095 | PPL | 2022-03-31 | Texas SET V5.0 Changes | Not Started | $1.0M - $1.5M | 16 - 20 months | Registration | 80% | 0% | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems | Ruane | 1 - Planned for 2022 start | Q3 2022 start Align with restart of MCT Requirement defining in 2022 Development underway in 2023 Testing and Go-live expected in first half of 2024
Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | SCR817 | PPL | 2022-03-31 | Related to NPRR1095 MarkeTrak Validation Revisions Aligning with Texas SET V5_0 | Not Started | $400k - $600k | 10 - 15 months | Retail | 65% | 0% | CRM & Registration Systems, Integration Systems, Retail Systems | Ruane | 1 - Planned for 2022 start | Q3 2022 start Align with restart of MCT Requirement defining in 2022 Development underway in 2023 Testing and Go-live expected in first half of 2024
Revision Requests | 2023 | 3710 | 3 - Consider When Resources are Available | 1 - High | SCR818 | PPL | 2022-04-28 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started | $300k - $500k | 9 - 12 months | NMMS | 100% | 64% | Grid Modeling Systems | Blevins | 1 - Planned for 2022 start | Q4 2022 start Desired to be split into two efforts: 1 - NMMS data collection (Q4 2022 start) 2 - MOD data collection and software enhancements (Q2 2023 start)
Revision Requests | 2023 | 3720 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1131 | Pending Board Approval |  | Controllable Load Resource Participation in Non-Spin | Not Started | $100k - $150k | 6 - 9 months | MMS | 40% | 0% | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems | Sharma | 3 - 2023 project candidate | Target 2023 start after ECRS implementation Revisit if there is an increase in the number of CLRs that are qualified to participate in Non-Spin
Revision Requests | 2025 | 4500 | 9 - No Action Needed | 2 - Medium | NPRR995 | PPL | 2021-08-19 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k-$1.2M | 20-30 months | RIOO | 44% | 4% | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations | Blevins | 9 - TBD | 2025 Priority