## Slide 1
Project Update
June 11, 2025
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2025 Release Targets
  Major Projects
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1214 – Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk
    NPRR1277 – Revisions to EAL Formula
    NPRR1281 – Improvements to Alternate FFSS Resource Designation
  Technology Working Group (TWG)
    Next meeting is 6/26/2025
  Aging Projects Related to Revision Requests
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 | NPRR1254 RTC+B Market Trials Sandbox Deployed | NPRR1145 | RTC+B Market Trials begin on 5/5/2025 | NPRR1253 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
 |  |  |  |  | RTC+B Stabilization begins
R7
R8
R10
R11
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR965
NPRR1000
NPRR1014
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216
NPRR1236
NPRR1245
NPRR1246
NOGRR211
NOGRR268
OBDRR020
OBDRR052
PGRR118
E
NPRR963(a) – Portion of NPRR
NPRR1253(a) – ICCP
NPRR1253(b) – Public API
ü
ü
1/1
3/1
ü
3/7
ü
ü
ü

## Slide 4: Major Projects
Other Project Highlights

## Slide 5: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1214 | Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | TBD | TBD | $800k-$1.2M, 12-18 months Impacted Systems: MMS, Settlements, Reporting ERCOT requests a continued table at PRS due to RTC+B resource constraints and design concerns
NPRR1277 | Revisions to EAL Formula | 2025 | 4570 | $90k-$140k, 4-6 months Impacted Systems: CMM, Reporting No RTC+B resource impacts; if approved, potential implementation before summer 2026
NPRR1281 | Improvements to Alternate FFSS Resource Designation | 2026 | 4780 | $75k-$100k, 6-8 months Impacted Systems: S&B, Reporting Candidate for priority discussion compared to other Settlements items in the project queue
Recommendations for…
PPL Rank Information
Next 2025 Rank in Business Strategy = 4570 Next 2028 Rank in Business Strategy = 5110
Next 2026 Rank in Business Strategy = 4780 Next 2029 Rank in Business Strategy = 5300
Next 2027 Rank in Business Strategy = 4900 Next Rank in Regulatory = 400

## Slide 6: Technology Working Group (TWG)
Agenda for TWG meeting held on 5/29/2025:
Next TWG scheduled for 6/26/2025

## Slide 7: Aging Revision Request Project Review
After the RTC+B project goes live, it will be valuable to have a reprioritized list of pending Revision Request projects
The “Aging Projects Relating to Revision Requests” list used in 2024 has been updated for recent activity
Multi-month review at PRS
  May: Review the contents of the posted aging list
  June: PRS members are asked to be prepared for a priority discussion
  July/August:
    Coordination with TAC on an Initiative Workshop
    Follow-up discussion after ERCOT assesses resources on highest priority items
Legislative priorities will be an important consideration

## Slide 8: Aging Revision Request Project Review Approach
Categorize RRs into “Tiers”
  Tier 1 Critical Must-have items (PUCT/Board directives, etc.)
  Tier 2 High Priority Highest priority after Tier 1
  Tier 3 Medium Priority Fit in without impacting Tier 1 and 2 projects
  Tier 4 Candidate for Removal May move to another tier after evaluation
Important Point
  Some aging RRs are expected to require language changes to bring them up to current market or system constructs
    Language updates would be made with a new RR
    ERCOT suggests this analysis be limited to aging items that are prioritized high enough to be queued for implementation

## Slide 9: Aging Revision Request Review at PRS – Stats
Category | June 2025
1 – Critical | 
2 – High Priority | 
3 – Medium Priority | 
4 – Candidate for Removal | 
TBD | 66
Total | 66
Posted Excel file details
  Retained notes from prior year prioritization discussions
  Updated for latest status
  Column added to capture “Tier”
During the PRS meeting we will attempt to categorize as many aging RR projects as possible
This will be the first of several iterations
Note: Currently there are 24 Revision Requests in-flight for delivery, including RTC+B