## Slide 1
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
FTPS and API Security Upgrade Project
Update
Esther Kent and Andrea OFlaherty
RMS Meeting June 12, 2025

## Slide 2
SMART METER ¯¯¯¯¯ TEXAS™ ¯¯¯¯¯
Project Purpose, Scope, and Call to Action
Purpose
Upgrade the following security protocols for the data delivery integration points at SMT:
Move from File Transfer Protocol Secure (“FTPS”) to SSH File Transfer Protocol “SFTP” for Retail Electric Provider (REP) and Competitive Service Provider (CSP) LSE file downloads, enrollment reporting downloads, and subscription reporting downloads.
Add JSON Web Tokens (“JWT”) tokens to the APIs for ad hoc reporting data retrieval.
Scope
The scope of the upgrade will impact FTP and API functionality only – affecting the REP’s and CSP’s integration points to access and download data from their FTP folders and ad hoc data retrieval via APIs.
The upgrade does not affect any SMT Website portal access for any user types (residential, business, REPs, CSPs etc.).
Market Participant Action Required
REPs and CSPs will be required to upgrade their FTP and API integration points to continue downloading and requesting ad hoc data via API from SMT.

## Slide 3: SMT FTPS and API Upgrade
Timeline
May 2025
6th May- Help Desk Communication and Enablement
13th May - RMS Meeting Presentation
14th May – Initial Market Notice (90 Day)
19th May - Commence Development Efforts
20th May – First Market Technical Q and A Web Conference
June 2025
3rd June – Second Market Technical Q and A Web Conference
12th June RMS Update
22nd June – Second Market Notice (60 Day)
27th June - Complete Development
30th June - Commence System Integration Testing
July 2025
1st July - Third Market Technical Q and A Web Conference
18th July - Complete System Testing
21st July - Commence UAT
22nd July – Third Market Notice (30 Day)
30th July – Fourth Market Technical Q and A Web Conference
August 2025
8th August - Complete UAT
13th August - Help Desk Enablement
14th Aug – Fifth Market Technical Q and A Web Conference
19th August - Fourth Market Notice (3 Day)
22nd Aug - Final Market Technical Q and A Web Conference
23rd August - Go Live
September 2025
22nd August thru 11th September - Market Transition Support – REPs, IT vendors and CSPs to upgrade to the new Services. New and replaced services running in parallel
13th September - Decommission replaced FTPS and API services
Help desk tickets can be opened by Market Participants at any time for one-on-one support