## Slide 1
Weekly
RTC+B Market Trials Update
ERCOT Staff
July 7, 2025

## Slide 2: Outline
Antitrust Admonition
Reminder of Key Document Postings
Expectations of QSEs for the Week
Provide Update of Cumulative QSE Scorecards for May/June
Communicate any known Issues within On-going Trial
Discuss Transition to July 7th Activities
Support any Technical and/or Business Questions

## Slide 3
WebEx Meeting reminders (same as other ERCOT forums):
Please keep line muted
If you have a question, please use the chat feature to either:
  Type in your question, or
  Type in “Question” and wait to be recognized to state question

## Slide 4
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 5: Market Trials Framework:
TAC Approved the Market Trials Plan in October 2024
Discussions with RTC+B Task Force have shaped the Handbooks
Handbook #1- QSE Submission Testing
Handbook #2- QSE Telemetry Tests
Handbook #3- Open Loop SCED
Handbook #4- QSE Telemetry Tests
Handbook #5- Close-Loop LFC Tests (draft)
Handbook #6- Day-Ahead Market Tests (draft)
All are posted on the
RTCBTF Homepage
under Market Trials banner

## Slide 6: Market Trials Technical Details
Detailed discussions with TWG have provided technical content details
Digital Certificate details
Connectivity/URL details to User Interfaces and APIs
Reminder of how to submit new ICCP requests
RTC and Production Telemetry connectivity
Network Model Load Schedule
All are posted on the
RTCBTF Homepage
under Technical Details banner

## Slide 7: Reminder of RTC+B FAQ (updated 7/3/2025)
Worksheets for categories
Posted on RTCBTF Home Page under Key Documents
Common questions/responses in Excel Workbook (target weekly updates)
Search workbook for Key Words

## Slide 8: Resources for May-June Market Trials
Everything needed for current market trials is on RTCBTF home page
May/June
July/Aug

## Slide 9: Summary of Market Trial activities for May-June WRAP-UP
Handbook 1- QSE connectivity and market submissions
  Submit to Market Management System and Outage Scheduler
  Goal to submit at least one successful transaction for each requested transaction type per QSE once during the 8-week period
Handbook 2- QSE telemetry set-up and check-out
  Submit all ICCP requests to ERCOT to add telemetry points
  Check-out will be for a sampling of resources within the QSE portfolio to ensure data flowing between ERCOT/QSE
Scoring continues into July to accommodate 3-week processing of new telemetry into systems.

## Slide 10: Scorecard 1 for Handbook 1- Market submissions:
7/3 Scores for QSEs with Resources – successful submissions for resource types specified in Handbook 1
Scoring: Complete

## Slide 11: Scorecard 2A for Handbook 2- 100% of ICCP Telemetry points added by QSE:
7/3 Scores for QSE with Resources - ICCP Telemetry points added in current model.
98% of 26k points complete
Scoring:

## Slide 12: Scorecard 2B for Handbook 2- Telemetry checkout meetings completed with ERCOT staff for sample of live data transfer capability
7/3 Scores for QSEs with Resources – Scheduling Check-out and Check-out complete
Scoring: Complete

## Slide 13: This Week in Market Trials for July-August
Current topics:
No current software issues
Reminder of Outage Schedule details for ESR / Single Model Battery
  Single model resources have new Equipment IDs. For outage submissions on the OSUI, only equipment name is needed and Equipment ID is not needed. If the Equipment ID is unknown and needed for API submission testing, use the Outage Scheduler UI (OSUI) to submit an outage for the ESR, and on the outage details/history file, the Equipment ID can be seen. If still experiencing issues, request help from RTCB@ercot.com.

## Slide 14: Transitioning to July 7 – August 30 Market Trials
Thank you for getting us to this point successfully!
Starting today, what the next 2 months will look like…..

## Slide 15
QSE will support “parallel production” 2days/week by entering $bids/offers for non-binding RTC energy and A/S awards and dispatch (Open-loop test)
Scorecard to demonstrate successful submissions and telemetry reflective of production, and mitigation plans in place for any outliers.
Coordination of individual QSE tests on subset of resources to ensure resources can follow new UDSP telemetry point from ERCOT.
Scorecard goal for QSEs to successfully demonstrate, and mitigation plans in place to address in next trial phase.
July & August:
Initial Real-Time Market execution and verify QSE ability to follow ERCOT frequency signals

## Slide 16: July/August Market Trials Summary
Handbook #3 - Dual “production-like” data entry two days per week
  Market Trials environments for
    Submissions (TPO/COP/ASOffer etc.)
    Telemetry (current and new telemetry points)
  Tuesdays/Thursdays 9AM – 5PM Required Activities
  Systems will be running 7x24 so submissions encouraged all days
Scoring data submissions all QSEs for all Resources each day starting Operating Day 7/22 – 8/28
Handbook #4 - Coordinated QSE Tests for following UDSP
  ERCOT will schedule meetings with all QSEs
  Please contact ERCOT if you are ready to test early in the trials window
  Single successful test to complete.
10 OpDays Scored

## Slide 17
RTC+B Market Submissions - Systems configurations
RTC QSE
Submission Testing
Open-loop
RTC SCED
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
Start
03/2025
Start
05/2025
Start
09/2025
Go-Live
12/5/25*
Apr 2025
Mar 2025
Feb 2025
Optional: RTC QSE/Vendor Developer
Submission Testing
Start
07/2025
Certificate: Current MOTE
Env: ERCOT RTC Market Trial
URL: RTC MIS MOTE URL
Certificate: Current Production
Env: ERCOT RTC Market Trial
URL: RTC MIS Market Trial
Cert: Production
Env: Prod
URL: MIS Prod
QSE/Vendor developer can use MOTE certificates & RTC MIS MOTE API URL to test the submissions until end of submission testing phase (end of June) as needed. At the start of the Open Loop testing, RTC MOTE MIS URLs will be disabled.
URL links: RTC MOTE and Market Trial URL links to be used for MMSUI, OSUI and API submissions. Actual links are provided in next slide.
For notifications/responses to MPs from RTC Market Trials environment, MP will need to provide the listener URL to ERCOT

## Slide 18: RTC+B Market Submissions - Systems configurations (Updated with URLs)
RTC+B Market Trials and Go-live
RTC Phase | Digital Certificate | MMSUI / OSUI URL | API / WAN URL
Vendor/QSE Submissions Testing | Current MOTE | RTC MOTE MIS URLs https://testmarkettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://testmarkettrials.ercot.com/osrui/osrui/Summary.action | RTC MOTE API/WAN URL https://testmarkettrialsapi.ercot.com/NodalAPI/EWS/ https://testmarkettrialsapi.wan.ercot.com/NodalAPI/EWS/
Open Loop and Closed Loop Testing | Current Production | RTC Market Trial URL https://markettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://markettrials.ercot.com/osrui/osrui/Summary.action | RTC Market Trial API/WAN URL https://markettrialsapi.ercot.com/NodalAPI/EWS/ https://markettrialsapi.wan.ercot.com/NodalAPI/EWS/
From RTC Go-live onwards | Current Production | Current Prod MIS URL mis.ercot.com/mmsui mis.ercot.com/osui | New Production API/WAN URL

## Slide 19: RTC+B Market Submissions - Systems configurations Public Key Update for WAN/API submissions
For API/WAN submissions into Market Trials environments, need to download public keys and place into the keystore location in system being used for RTC+B submissions.
No change to digital user certificates – continue to use existing MOTE and Production Certificates
Market Trial API Public key location: https://www.ercot.com/services/mdt/webservices

## Slide 20: RTC+B New Reports Posted to the ERCOT Website
Links to the available RTC+B versions of Real-Time reports posted on Real-Time Market Information page.

## Slide 21: Wrap-Up and Questions
Remainder of meeting for questions-
First round of questions specifically about July/Aug
Last round of questions for more general RTC+B as time allows
Can always email the RTC+B Program mailbox: RTCB@ercot.com
FAQ is also a resource for questions that other have asked.
Announcement- Tentative plan for Closed-Loop LFC Workshop WebEx Thursday July 23rd from 2-4pm (same day as RTCBTF but a deep dive focused on Closed Loop LFC Testing expectations and details to address any questions, details, and concerns for September test)
Thanks for your support!