## Sheet1
TEXAS SET
2025-06-17
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes June 2025-- TX SET
| No changes were made to the May meeting notes. | SET Leadership will have these posted to the June meeting page.
ERCOT Updates
Flight 0625 | 9 new CRs and 8 existing CRs testing. BDE brought up request from TNMP for banking information prior to testing. SET will wrap this topic into the TMTP discussion.
RMS Update
Texas SET Assessment - TAC Assignment | SET reviewed the TAC assignement and answered questions related to
TXSETCC854 | Reviewed proposed change control 854 that would add a new indicator for Move Ins due to Safety Net Transactions. Texas SET voted to approve the Change Control for RMS review next month with a future release.
Texas Market Test Plan Review
| Continued reviewing proposed TMTP edits. Starting with Section 4, with a focus on preflight and during flight activities. The review process of the TMTP will continue over the next few Texas SET meetings. | TMTP Draft will be sent to TX SET listserv
Other Business
Next Meeting
July 22nd, In Person at ERCOT MetCenter and WebEx |  | SET leadership to request for space at ERCOT MetCenter for June 17th and will send notification to SET listserve.
Attendees F-T-F
Kyle Patrick - NRG | Paul Yockey - ERCOT | Stephen Wilson - Vistra
Monica Jones - CNP | Sheri Wiegand- Vistra | Steven Pliler - Vistra
Bill Snyder - AEP | Jeff Chen - CenterPoint
Attendees Webex
Angela Ghormley - Calpine | Catherine Meiners - ERCOT | Jordan Troublefield - ERCOT
Joe Lindsay | Eric Lotter - Grid Monitor | Kathryn Thurman - ERCOT
Laura Gomez LPL | JB - ESG | William Butler - LPL
Carrie Roher - BDE | Kathy Scott - CenterPoint | Kim Wall - Hansen
David Michelsen - ERCOT | Nick Reedy (CimView) | Vivian Valdez - LPL
Sam Pak - Oncor | Amy Sue Stirland - LPL | Rita Cardenas - AEP