## Slide 1
Project Update
August 13, 2025
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2025 Release Targets
  Major Projects
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1265 – Unregistered Distributed Generator
    NPRR1290 – Gap Resolutions and Clarifications for the Implementation of RTC+B
    NPRR1291 – Modify Annual Demand Response Report Posting Date and Include Language to Address PUCT SUBST. R. 25.186
    SCR831 – Short Circuit Model Integration
  Technology Working Group (TWG)
    Next meeting is 8/28/2025
  Initiative Ranking Workshop
    8/25/2025 at 12:30pm
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 | NPRR1254 RTC+B Market Trials Sandbox Deployed | NPRR1145 | RTC+B Market Trials begin on 5/5/2025 | NPRR1253 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
NPRR1234(a) |  |  | NOGRR245 |  | PGRR091 SCR828
R7
R8
R10
R11
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR965
NPRR1000
NPRR1014
NPRR1029(a)
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216
NPRR1236
NPRR1245
NPRR1246
NPRR1268
NPRR1269
NPRR1270
NPRR1282
NOGRR211
NOGRR268
NOGRR277
OBDRR020
OBDRR052
PGRR118
E
NPRR963(a) – Portion of NPRR
NPRR1029(a) – Market suspension of ESRs portion
NPRR1234(a) – Section 3.10.7.2, paragraphs 14-19
NPRR1253 – ICCP/Public API
ü
ü
1/1
3/1
ü
3/7
ü
ü
ü
RTC+B Stabilization begins
E
E
E
7/21
ü

## Slide 4: Major Projects
Other Project Highlights

## Slide 5: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Ra2nk | Comments
NPRR1214 | Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | TBD | TBD | $800k-$1.2M, 12-18 months Impacted Systems: MMS, Settlements, Reporting ERCOT requests a continued table at PRS due to RTC+B resource constraints and design concerns
NPRR1265 | Unregistered Distributed Generator | 2026 | 400 | $75k-$125k, 6-9 months Impacted Systems: NMMS, MIS, ERCOT.com REGULATORY – HB 3390
NPRR1290 | Gap Resolutions and Clarifications for the Implementation of RTC+B | 2026 | 4800 | RTC+B portion is “no impact” – delivered with RTC Remaining portion: $75k-$100k, 5-7 months IA targeted for posting on 8/12/2025
NPRR1291 | Modify Annual Demand Response Report Posting Date and Include Language to Address PUCT SUBST. R. 25.186 | 2026 | 410 | $60k-$90k, 4-6 months Impacted Systems: Retail Systems REGULATORY – Manual approach until system changes can be completed
SCR831 | Short Circuit Model Integration | 2026 | 4810 | $100k-$200k, 7-10 months Impacted Systems: NMMS – combine w/SCR818
Recommendations for…
PPL Rank Information
Next 2025 Rank in Business Strategy = 4580 Next 2028 Rank in Business Strategy = 5110
Next 2026 Rank in Business Strategy = 4800 Next 2029 Rank in Business Strategy = 5300
Next 2027 Rank in Business Strategy = 4910 Next Rank in Regulatory = 400

## Slide 6: Technology Working Group (TWG)
Agenda for TWG meeting held on 7/31/2025:
Next TWG scheduled for 8/28/2025

## Slide 7: Aging Revision Request Project Review Approach
Initiative Prioritization Workshop on Monday 8/25/2025 at 12:30pm
Categorize RRs into “Tiers”
  Tier 1 Critical Must-have items (PUCT/Board directives, etc.)
  Tier 2 High Priority Highest priority after Tier 1
  Tier 3 Medium Priority Fit in without impacting Tier 1 and 2 projects
  Tier 4 No Action Not ready for immediate action
  Tier 5 Candidate for Removal May move to another tier after evaluation
Important Point
  Some aging RRs are expected to require language changes to bring them up to current market or system constructs
    Language updates would be made with a new RR
    ERCOT suggests this analysis be limited to aging items that are prioritized high enough to be queued for implementation

## Slide 8: Aging Revision Request Review at PRS – Stats
Tier | Aug 2025
1 – Critical | 1
2 – High Priority | 7
3 – Medium Priority | 39
4 – No Action | 9
5 – Candidate for Removal | 9
TBD | 1
Total | 66
Posted Excel file details
  Retained notes from prior year prioritization discussions
  Updated for latest status
  Column added to capture “Tier”
An initial draft Tier has been applied to each item as a starting point for the August 25 prioritization workshop
This will be the first of several iterations
Note: Currently there are 38 Revision Requests in-flight for delivery, including RTC+B