## RTCBTF
Issue to resolve | Type | Protocol needed? | Approval level | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Parameters for Ancillary Service proxy offers NPRR1269 | Policy | Yes | PUCT | 2025-04-01: BOARD; 2025-05-01: PUC
Scaling Factor Values for RegUp/RegDown - NPRR1269 | Other | Yes | PUCT | 2025-04-01: BOARD; 2025-05-01: PUC
ASDCs for use in Reliability Unit Commitment (RUC) studies- NPRR1269 | Policy | Yes | PUCT | 2025-04-01: BOARD; 2025-05-01: PUC
RTC SOC/AS duration parameter discussion- NPRR1282/NOGRR277 | Policy | Yes | PUCT | 2025-06-01: BOARD; 2025-07-01: PUC
Clean-up Revision Requests to address as-builts and clarifications, as needed- NPRR1290/NOGRR278 | Other | Yes | PUCT | 2025-09-01: Board; 2025-10-01: PUC
RTC Simulator Analysis for periodic analysis comparing RTC and the current ORDC design – KP 1.1(8) - Historical Operating Days identified by RTCBTF - Additional review of transmission constraint max. shadow price values (Sec 22/per NPRR1211) - Review of AS Demand Curve in context of current policy- NPRR1268 - Consider AS Indifference | Analysis | N/A | N/A | bar: 2024-04-01 to 2024-07-01; 2024-10-01 to 2025-03-01
Market Readiness
- Release Market Trials Sequence and Potential Dates (May 2024) |  |  |  | 2024-09-01: Complete
- RTC+B Technical Workshops and release interface specifications (May-June 2024) |  |  |  | 2024-09-01: Complete
Explanation of ICCP Changes (Abhi Gari Masanna- May RTCBTF) |  |  |  | 2024-09-01: Complete
Explanation of Market Submission (Nathan Smith- August RTCBTF) |  |  |  | 2024-09-01: Complete
- Release and review Market Trials Plan with RTCBTF (TAC endorsed October 2024) | Other | No | TAC | 2024-10-01: Complete
- Execute QSE Attestation (completed August 2024) |  |  |  | 2024-09-01: Complete
- Announce Planned Go-Live Date (September 2024) |  |  |  | 2024-09-01: Complete
- Outline of Readiness Training modules |  |  |  | 2024-10-01: Complete
- Delivery of Training modules to RTCBTF Training page |  |  |  | 2025-06-01: Complete
- Market Trials Handbooks for 5/5/25 Trials (Market Submission and Telemetry Check-out) |  |  |  | 2025-02-01: Complete
- Market Trials Handbook for 7/7/25 Trials (OpenLoop SCED and QSE Telemetry Testing) |  |  |  | 2025-04-01: Complete
- Market Trials Handbook for 9/2/25 Trials (Closed-Loop Test and Day-Ahead Market) |  |  |  | 2025-06-01: Complete
- Annual Operations Training Seminar (6-weeks) |  |  |  | 2025-04-01: Complete
- Go-Live Transition Plan |  |  |  | 2025-07-01: earlier
- Any protocol and/or PUCT waivers needed for market trials and/or transition to Go-Live |  |  |  | 2025-07-01: earlier
- RTCBTF issues- a. Operation Procedures (e.g., removing SASM and HASL/LASL), note to include any needed discussion on triggers for initiating off-cycle SCED execution, b. Business Practice Manuals (e.g., changes to COP and telemetry), c. Market trials/training/annual seminar engagement (release plans/dates for market trials), d. Any details MPs need for designing their control systems | bar: 2025-08-01 to 2025-10-01

## Resolution
Resolved Issues
Id | Source | Issue to resolve | Resolution or next steps
4 | RTCTF issue | Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3)) | TAC approval of following language at May 2024 TAC: Given that Hydro Resources operating in synchronous condenser mode are not dispatched by SCED, ERCOT proposes setting the Mitigated Offer Cap for all Hydro Resources to RTSWCAP. This will be done in protocol and verifiable cost manual by 1) setting the O&M value in the MOC to RTSWCAP and 2) Setting the heat rate to 0 MMBtu/MWh.
8 | RTCTF issue | Mapping of bill determinants to extracts and reporting for developing shadow settlement | Completed in deep-dive at Aug 2024 RTCBTF
9 | RTCTF issue | Changes to ICCP handbook, and documentation for non-ICCP market submissions | Complete- Technical workshops May-June and Market Notice sent 6/28/2024
13 | ERCOT 2023 | How DRRS would work in an RTC paradigm | Complete- DRRS after RTC so out of scope.
14 | ERCOT 2023 | Inclusion of firm load shed in the pricing run - (RTC changes to align with NPRR1081) | Complete- part of NPRR1245
15 | ERCOT 2023 | Various protocol references need to be updated | Complete- part of NPRR1245
17 | ERCOT 2023 | RUC Capacity Short Calculations with SOC | TAC approval of RUC Capacity Whitepaper at April 2024 TAC. ERCOT has submitted NPRR1236 to support whitepaper.
19 | RTCBTF 1/12/24 | Emergency Price Program alignment to RTC (imbedded within NPRR1216, monitor only for RTCBTF) | Complete- part of NPRR1216
20 | RTCBTF 4/10/24 | Review of the Energy and AS Offer Caps in the context of current policy. | Complete- May 2024 RTCBTF