## Slide 1
Resource Integration Topics
Jenifer Fernandes
ERCOT
Resource Integration Working Group
August 20th , 2025

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.3.5
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.3.5, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic/PSCAD Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test, Unit Model Validation and Template is required. PSCAD template is required starting August 1st QSA.
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM and should include MQT

## Slide 4: QSA 45 day deadline
FIS studies finalized and posted in RIOO-IS 45 days prior to quarterly stability assessment deadline.
Dynamic models (PSEE, PSCAD, TSAT (UDM)) and MQT report submitted in RIOO-IS.
From Planning guide Section 5.3.5 (2): Last Day for an IE to meet prerequisites as listed in paragraph (4) below | 45 day deadline
Prior August 1 | June 17
Prior November 1 | September 17
Prior February 1 | December 18
Prior May 1 | March 17

## Slide 5: Registering as a Resource Entity
1. Applicants planning to register with ERCOT as a Resource Entity are strongly encouraged to submit their application at least 60 days in advance to allow sufficient time for review and processing. Processing times can vary depending on volume and application-specific factors.
2. Submissions for RE registration should include:
  Standard Form Market Participant Agreement
  Resource Entity (RE) Application for Registration
  Managed Capacity Declaration Form
  Attestation Regarding Market Participant Citizenship, Ownership, or Headquarters
  Reporting and Attestation Regarding Purchase of Critical Electric Grid Equipment (CEGE) and Critical Electric Grid Services (CEGS) from a Lone Star Infrastructure Protection Act (LSIPA) Designated Company or LSIPA Designated Country

## Slide 6: Registering as a Resource Entity- Timeline
120 day RE must submit initial Registration Data per Nodal Protocol 3.10.1 (4).
Must be a Qualified Resource Entity.
10/01/2025
11/01/2025
02/04/2026
Applications are generally estimated to take up to two months for completion. LSIPA-related applications may take longer depending on complexity. To account for this, please plan to submit your applications 60 days in advance.
Production Load Date
Final full registration data submitted before the deadline.
The example below is for February 4th, 2026, Production Load Date

## Slide 7: Active RR’s
NPRR1272: Voltage Support at Private Use Networks
PGRR120:SSO Risk Reduction for Generator Interconnection
NOGRR272: Advanced Grid Support Requirements for Inverter-Based ESRs
PGRR124: ESR Maintenance Exception to Modifications

## Slide 8: Generation Interconnection Requests
2,066 active generation interconnection requests totaling 433 GW as of July 31st, 2025 (Solar 163 GW, Wind 45 GW, Gas 40 GW, Battery 181 GW, and Other 4 GW) (Excludes capacity associated with projects designated as Inactive per Planning Guide Section 5.7.6)
Chart: Monthly Capacity by Fuel Type plus Project Count, 13-Month Rolling Basis
| Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25
Natural Gas | 22.1599 | 25.328 | 25.967 | 25.9537 | 27.1595 | 27.5775 | 28.7739 | 32.1902 | 33.5785 | 33.5831 | 32.4898 | 35.2601 | 39.5577
Nuclear | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wind | 33.7315 | 33.8535 | 34.8385 | 33.4671 | 35.3073 | 34.4496 | 38.223 | 39.8929 | 39.7951 | 42.4834 | 40.8855 | 41.4141 | 45.0483
Solar | 154.4072 | 154.7705 | 153.6583 | 154.8604 | 155.6757 | 154.4871 | 153.6071 | 155.9895 | 156.6854 | 159.4258 | 158.4904 | 161.6767 | 162.7027
Biomass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Battery | 151.811 | 154.799 | 154.2643 | 152.5799 | 156.5298 | 160.0434 | 165.9327 | 168.836 | 171.592 | 172.4856 | 173.9969 | 177.9286 | 181.3938
Other | 2.5619 | 2.5619 | 2.9609 | 3.7128 | 3.1132 | 2.9129 | 2.7809 | 2.7809 | 2.9129 | 3.0629 | 3.2084 | 3.5013 | 3.5013
Total Project Count | 1858 | 1886 | 1881 | 1872 | 1903 | 1917 | 1952 | 1987 | 2018 | 2037 | 2031 | 2054 | 2066
Cancelled Project Count | 5 | 8 | 19 | 29 | 11 | 14 | 17 | 16 | 18 | 38 | 26 | 17 | 21

## Slide 9: Generation Interconnection Requests
Small Gen- 23 projects Not Model Ready, 52 projects Model Ready
Chart: Small Generator Monthly Capacity by GIM Milestone plus Project Count, 13-Month Rolling Basis
| Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25
# Not Model Ready | 31 | 27 | 29 | 35 | 33 | 32 | 30 | 24 | 26 | 32 | 31 | 28 | 23
# Model Ready | 46 | 49 | 48 | 44 | 48 | 46 | 46 | 50 | 50 | 50 | 50 | 50 | 52
MW Capacity | 715.94 | 708.34 | 725.62 | 745.8 | 755.62 | 726.03 | 701.78 | 682.08 | 706.9 | 767.07 | 762.84 | 733.06 | 703.44

## Slide 10: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 11: Questions?
Thank you!