## Recent History - 2020-2025
| 2020 | [5 empty] | 2021 | [5 empty] | 2022 | [6 empty] | 2023 | [5 empty] | 2024 |  |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
| Q1 |  | Q2 |  | Q3 | Q4 | Q1 | Q2 | Q3 |  | Q4 |  | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
EMS Upgrade (started 10/24/2019)
MMS OS Tech Refresh (started 1/4/2019)
FFR / FFRA - Fast Frequency Response (NPRR863) - FFR Advancement
Energy Storage Resource Combo Model (NPRR986,971,1043)
DGR / DESR Implementation (NPRR917,1016,1052,1065, NOGRR212, PGRR082, RRGRR026)
[9 empty] | Securitization M and N (NPRR1103, NPRR1114) | [9 empty] | Securitization Phase 2A | [6 empty] | Securitization Phase 2B | [10 empty] | Securitization Ph3
Load Resources in Non-Spin (NPRR1093,1101)
ERCOT Approval of Outage Requests (NPRR1108)
ERCOT Contingency Reserve Service (ECRS) (NPRR863,1085,1096,1148)
Firm Fuel Supply Service (NPRR1120)
Interim State of Charge (NPRR1186)
NPRR1131 / NPRR1058 (1)
IBR Ride-Through Requirements (NOGRR245)
[26 empty] | DRRS Concept & Protocol Development (NPRR1235) | [9 empty] | DRRS Implementation (project timeline TBD)
PCM (Perf. Credit Mechanism) Concept Development
[6 empty] | Passport | [6 empty] | Intermittent Activities | [6 empty] | Pre-work |  | RTC+B (Real-Time Co-optimization + Batteries) (NPRR1007-NPRR1014, NPRR1204 and others)
|  |  |  | Project Status |  |  | Events |  |  | Code Freezes | [5 empty] | Go-Live Dates | [7 empty] | Additional Notes
Legend: |  |  |  | Complete |  |  | Winter Storm Uri |  |  | EMS Freeze | [13 empty] | 1 - | NPRR1131 = Controllable Load Resources Participation in Non-Spin
|  |  |  | In-Flight | [5 empty] | RTC+B Freeze | [14 empty] | NPRR1058 = Resource Offer Modernization
Not Started
Non-Project Work
Current Date

## DRAFT Release Plan v1
System
| 2026 | [7 empty] | 2027 |  |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | [5 empty] | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034
| Q1 |  |  | Q2 |  | Q3 |  | Q4 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |  | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
MMS | RTC+B Stabilization |  |  |  |  | RDPA analysis: NPRR1006, NPRR1091, NPRR904
| Pre-work |  |  |  | DRRS (replacement for NPRR1235 to be filed)
| NPRR1188, NPRR1244 CLR Improvements | [20 empty] | "High" TBD: NPRR1004
| Pre-work | [6 empty] | SB6
| NPRR1238 Large Load Loadshed | [11 empty] | NPRR1171, NPRR1213 DGR/DESR Load Shedding | [8 empty] | "High/Medium" TBD: NPRR1128
NPRR1290 Ph2 Changes to pricing during scarity events
[7 empty] | MMS/OS Tech Refresh | [6 empty] | CODE FREEZE?
EMS | RTC+B Stabilization
| Pre-work |  |  |  | DRRS (replacement for NPRR1235 to be filed)
|  | NPRR1198 Congestion Mitigation | [19 empty] | "High/Medium" TBD: NPRR1226
NPRR1238 Large Load Loadshed
Future Case Builder
SCR820 Operator Real-Time Messaging
[8 empty] | EMS Upgrade | [14 empty] | CODE FREEZE?
S&B | RTC+B Stabilization
| Pre-work |  |  |  | DRRS (replacement for NPRR1235 to be filed) | [16 empty] | "High" TBD: NPRR1216 |  |  |  |  | LEGEND | Planning |  | Execution
|  | NPRR1281 Firm Fuel Improvements | [25 empty] | IA cost > $1M
| NPRR1188, NPRR1244 CLR Improvements | [26 empty] | IA cost $500k-$1M
| Pre-work |  |  |  | NPRR1296 Residential Demand | [22 empty] | IA cost $100k-$500k
| Treasury Single Source of Truth | [26 empty] | IA cost <$100k
| Settlements Resource Data Input Automation | [26 empty] | O&M work (RR drafting, stakeholder process, etc.)
| Pre-work | [6 empty] | SB6 | [19 empty] | Project In Flight
| Pre-work | [5 empty] | Firming | [20 empty] | To Be Determined (TBD)
Reporting | RTC+B Stabilization
| Pre-work |  |  |  | DRRS (replacement for NPRR1235 to be filed) | [16 empty] | "High/Medium" TBD: NPRR1226
|  |  | Others in progress… | [18 empty] | "High/Medium" TBD: NPRR1249
RIOO
|  |  | Estimates in progress… | [18 empty] | "High" TBD: NPRR1234
"High/Medium" TBD: NPRR1267
CMM | NPRR1277
| NPRR1188, NPRR1244 CLR Improvements | [20 empty] | "High/Medium" TBD: NPRR1201
Treasury Single Source of Truth
CMM Tech Health
CRR | NPRR1288, NPRR936 | [7 empty] | NPRR1289 | [12 empty] | TBD: NPRR1023
[6 empty] | CRR Tech Refresh | [15 empty] | TBD: NPRR1292, SCR833, NPRR1297
NMMS
SCR818 Phase 2
Other
IMPORTANT
This first draft is based on priority, not feasibility

## DRAFT Release Plan v2
System
| 2026 | [7 empty] | 2027 |  |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | [5 empty] | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034
| Q1 |  |  | Q2 |  | Q3 |  | Q4 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |  | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
MMS | RTC+B Stabilization |  |  |  |  | RDPA analysis: NPRR1006, NPRR1091, NPRR904, NPRR1105
| Pre-work |  |  |  |  | DRRS (replacement for NPRR1235 to be filed)
| NPRR1188, NPRR1244 CLR Improvements | [20 empty] | "High" TBD: NPRR1004
| Pre-work | [6 empty] | SB6
| NPRR1238 Large Load Loadshed | [11 empty] | NPRR1171, NPRR1213 DGR/DESR Load Shedding | [8 empty] | "High/Medium" TBD: NPRR1128
NPRR1290 Ph2 Changes to pricing during scarity events
NPRR1214 RDPA Fix
[7 empty] | MMS/OS Tech Refresh | [6 empty] | CODE FREEZE?
EMS | RTC+B Stabilization
| Pre-work |  |  |  |  | DRRS (replacement for NPRR1235 to be filed)
[9 empty] | NPRR1198 Congestion Mitigation | [12 empty] | "High/Medium" TBD: NPRR1226
Large Load Curtailment Manager
NPRR1238 Large Load Loadshed
Future Case Builder
SCR820 Operator Real-Time Messaging
[8 empty] | EMS Upgrade | [14 empty] | CODE FREEZE?
S&B | RTC+B Stabilization
| Pre-work |  |  |  |  | DRRS (replacement for NPRR1235 to be filed) | [15 empty] | "High" TBD: NPRR1216 |  |  |  |  | LEGEND | Planning |  | Execution
|  | NPRR1281 Firm Fuel Improvements | [25 empty] | IA cost > $1M
| NPRR1188, NPRR1244 CLR Improvements | [26 empty] | IA cost $500k-$1M
| Pre-work |  |  |  | NPRR1296 Residential Demand | [22 empty] | IA cost $100k-$500k
| Treasury Single Source of Truth | [26 empty] | IA cost <$100k
| Settlements Resource Data Input Automation | [26 empty] | O&M work (RR drafting, stakeholder process, etc.)
| Pre-work | [6 empty] | SB6 | [19 empty] | Project In Flight
| Pre-work | [5 empty] | Firming | [20 empty] | To Be Determined (TBD)
Reporting | RTC+B Stabilization
| Pre-work |  |  |  | DRRS (replacement for NPRR1235 to be filed)
NPRR1214 RDPA Fix
|  |  | Others in progress… | [5 empty] | NPRR1226 Est. Demand Response Data | [12 empty] | "High/Medium" TBD: NPRR1249
Reporting Tech Health
RIOO
|  |  | Estimates in progress… | [18 empty] | "High" TBD: NPRR1234
"High/Medium" TBD: NPRR1267
CMM | NPRR1277
| NPRR1188, NPRR1244 CLR Improvements | [20 empty] | "High/Medium" TBD: NPRR1201
Treasury Single Source of Truth
CMM Tech Health
CRR | NPRR1288, NPRR936 | [7 empty] | NPRR1289 | [12 empty] | TBD: NPRR1023
[6 empty] | CRR Tech Refresh | [15 empty] | TBD: NPRR1292, SCR833, NPRR1297
NMMS
SCR818 Phase 2 + SCR831
NDCRC
NDCRC Tech Health
SCR831 NDCRC API
IMPORTANT
This second draft is still a work in progress