## Open Loop Testing Plan - QSEs
RTC+B - Open Loop Testing Plan ( QSEs/External) - 10/16/2025 09:00 - 12:00
Step | Start Time | End Time | Tasks / Steps | Responsible Entity/Resources | Status | Notes
Pre Steps
1 | 2025-10-13 | 2025-10-15 | QSEs to verify that RTC+B ICCP/EMS and Market systems are updated with latest model. | QSEs
2 | 2025-10-13 | 2025-10-15 | QSEs to verify all their resources RTC+B Resource Status (RSTR) telemetry point in their ICCP/SCADA is setup correctly and sending good quality RSTR telemetry to ERCOT ICCP. | QSEs |  | ERCOT has been sending out the emails with failed telemetry points report to fix those issues as soon as possible.
3 | 2025-10-13 | 2025-10-15 | QSEs to verify all their resources UDSP telemetry point in their ICCP/SCADA is setup correctly and receiving good quality UDSP signal from ERCOT ICCP. | QSEs
4 | 2025-10-13 | 2025-10-15 | QSEs to to submit production quality real-time market submissions (COP, TPO, AS Offers, ESR Bids/Offers, Output Schedules etc.) utilizing their parallel RTC+B Market Systems for Operating Day 10/16. | QSEs |  | ERCOT will start reaching out to QSEs starting from 4pm on 10/15 to resolve any market submission issues
Communication
5 | 2025-10-16 09:00 | 2025-10-16 09:00 | Webex Conference Call will be open for QSEs IT/OT staff | ERCOT |  | ERCOT will send out Open Loop Testing Webex conference call details to QSEs AR, BAR, RTC+B AE on 10/13/2025.
6 | 2025-10-16 09:00 | 2025-10-16 09:15 | QSEs IT/OT staff to join the Webex Conference Call | QSEs IT/OT Staff |  | ERCOT prefers 2-3 participants from each company (to keep the population of attendees limited). These participants should be staff that can provide EMS AGC & SCADA applications etc. support to resolve any QSE telemetry and market submissions issues during this open loop testing. If you are a QSE and data agent for other QSEs (providing ICCP telemetry services and/or having EMS/GMS applications services, and/or market submissions services), you are expected to provide updates & support in the webex call as mentioned above for those QSEs. QSE participants are requested to join the call with Participant name <QSE Name - Participant Name>
7 | 2025-10-16 09:00 | 2025-10-16 12:00 | QSEs to communicate any specific issues/observations/feedback to individual ERCOT SMEs in the Webex and ERCOT does the same. General information can be shared in the Webex chat all the participants. | QSEs/ERCOT
RTC+B Open Loop Testing - Monitor and Report Issues
Please note that all the common telemetry points between currrent production and RTC+B are being updated from current production during this Open Loop Testing. BP/LMP/SBBH/SCCT/NDPL/RDPL/MMEC/KVM/KVT
8 | 2025-10-16 10:00 | 2025-10-16 12:00 | Monitor UDSP signals for each resource and report any issues (example: large deviations from current production UDBP + Regulation, UDSP being outside of HSL/LSL) | QSEs
9 | 2025-10-16 10:00 | 2025-10-16 12:00 | Monitor AS Awards and AS Price (being sent out through telemetry) and report any inconsistencies/unexpected AS Awards based on prices (example: discrepencies between AS Awards vs telemetry & offers etc.) | QSEs
10 | 2025-10-16 10:00 | 2025-10-16 12:00 | Review UDSP for IRRs and verify if they are comparable to current production. ERCOT will provide the curtailment flag information directly to QSE contacts in the webex call as needed. | QSEs
11 | 2025-10-16 10:00 | 2025-10-16 12:00 | Battery Resources - Review UDSP signal based on expected charging/discharging patterns and report any discrepencies. | ERCOT
12 | 2025-10-16 10:00 | 2025-10-16 12:00 | Battery Resources - Monitor telemetry limits, AS ramp rates, NetMW, SOC telemtry and other input telemetry and identify any UDSP and AS Awards inconsistencies. | ERCOT
13 | 2025-10-16 10:00 | 2025-10-16 12:00 | Verify NCLR AS Awards with respective to Self provision, capability telemetry and AS Offers. | QSEs
14 | 2025-10-16 10:00 | 2025-10-16 12:00 | Verify Combined Cycle UDSP and AS Awards with respective to their PAUG telemetry | QSEs
15 | 2025-10-16 10:00 | 2025-10-16 12:00 | Verify RRS and Non-Spin Awards with respect to telemetered resource status | QSEs
16 | 2025-10-16 10:00 | 2025-10-16 12:00 | Verify System and Unit level FFAC, OECA, and ORRA Telemetry points sent to QSEs and report any telemetry quality issues. | QSEs
17 | 2025-10-16 10:00 | 2025-10-16 12:00 | Monitor "RTC Market Trials Settlement Point Prices at Resource Nodes, Hubs and Load Zones" Report at below link and ask any questions on price discrepencies. https://www.ercot.com/mp/data-products/data-product-details?id=NP6-905-RTCMT | QSEs
18 | 2025-10-16 10:00 | 2025-10-16 12:00 | Update TPO, AS Offers during operating period for testing purpose (QSEs normally submit until end of adjustment period) | QSEs
19 | 2025-10-16 10:00 | 2025-10-16 12:00 | Monitor Expected generation deviations, compare with current production, report any issues to QSEs | ERCOT
20 | 2025-10-16 11:55 | 2025-10-16 12:00 | Collect QSEs feedback/observations/isssues from Webex and conclude the open loop testing. | ERCOT