## Slide 1
Prioritization Update
October 22, 2025
Troy Anderson
ERCOT Portfolio Management

## Slide 2: Aging Revision Request Project Review Approach
Initiative Prioritization Workshop held on 8/25/2025
Categorized Revision Requests into “Tiers”
  Tier 1 Critical Must-have items (PUCT/Board directives, etc.)
  Tier 2 High Priority Highest priority after Tier 1
  Tier 3 Medium Priority Fit in without impacting Tier 1 and 2 projects
  Tier 4 No Action Not ready for immediate action
  Tier 5 Candidate for Removal May move to another tier after evaluation
Important Point
  Some aging RRs are expected to require language changes to bring them up to current market or system constructs
    Language updates would be made with a new RR
    ERCOT suggests this analysis be limited to aging items that are prioritized high enough to be queued for implementation

## Slide 3: Aging Revision Request Review at PRS – Status
Draft #2 depicts the latest view of the release plan (see next slide)
  Still very much in progress
  Full spreadsheet posted to the 10/8 PRS meeting page
Impact Analyses loaded for NPRR1188 and NPRR1244 as a single project targeting an early 2026 start (perhaps even December 2025)
  Resource analysis underway
  Pre-project discussions with vendor are underway
  Considering approaches that would reduce the 18-24 month project duration
In support of SB6, ERCOT is envisioning a Large Load Curtailment Manager project that may include elements of NPRR1238
  Candidate for early 2026 project start (go-live target is TBD)
  Impact Analysis is getting underway (for portion other than NPRR1238)
  Internal ERCOT discussion taking place on connection with NPRR1238
Smaller projects temporarily moved from 2026 to 2027 until we have a better feel for pockets of resource availability in 2026
  NPRR1198, NPRR1290 Phase 2

## Slide 4: Draft #2 – Making Progress
Additional Notes:
All “High” items considered
Color coding reflects IA project cost estimates
Light and dark shading reflects potential project phase durations
Includes internal ERCOT projects drawing on similar resources
Spreadsheet posted for stakeholder review

## Slide 5: Additional Prioritization Notes
Labor estimates from Impact Analysis documents are used to assess our ability to deliver additional Revision Requests
MMS, EMS and Settlements have the highest levels of demand and present the greatest challenge
Some impacted systems have a dedicated development queue
  Examples: CRR and RIOO
The count of Aging Revision Requests (see table at right) will continue to be tracked as projects are kicked off
Aging Revision Requests | 
Tier | Aug 2025
1 – Critical | 1
2 – High Priority | 7
3 – Medium Priority | 39
4 – No Action | 9
5 – Candidate for Removal | 9
TBD | 1
Total | 66

## Slide 6: Priority Projects in Recent Years