## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
October 22, 2025

## Slide 2: Outline
Update on RTCBTF Issues List
Update on RTC NPRRs
Market Trials Update
  Phase 1 Completed
  Phase 2 Completed
  Phase 3 Began 9/2/2025
Path to Go-Live in 43 days
Next Steps

## Slide 3: RTCBTF Remaining Items for Go-Live
RTCBTF- Completing market trials and transition plan details
Market Trials

## Slide 4: Summary and Timeline of NPRRs
NPRRs set for PUCT May 15 Open Meeting (PUCT approved)
  NPRR1268 for ASDC Modifications (IMM sponsor)
  NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  NPRR1270 for AS Qualification details (ERCOT sponsor)
AS Duration / State of Charge (NPRR1282 / NOGRR277)
  Approved at Board and PUCT
Final Clarifying NPRR1290/NOGRR278
  Approved at PRS
  On to August TAC and Sep Board
Remaining Stakeholder path to Board Meetings before Go-Live:
  PRS Aug 13 > TAC Aug 27 > Board Sep 23

## Slide 5: Summary and Timeline of NPRRs
NPRRs approved at PUCT May 15 Open Meeting
  NPRR1268 for ASDC Modifications (IMM sponsor)
  NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  NPRR1270 for AS Qualification details (ERCOT sponsor)
AS Duration / State of Charge (NPRR1282 / NOGRR277)
  Began discussion March 25 June Board approval
  PUCT July 31 consideration
Final Clarifying Revisions – NPRR1290/NOGRR278 (Sept Board)
  NPRR1290 included Hunt Energy revisions for post go-live and approved at PRS (unanimous)
  TAC consideration today and potentially Sept Board consideration
Remaining Stakeholder path to Board Meetings before Go-Live:
  PRS Aug 13 > TAC Aug 27 > Board Sep 23
Note that ERCOT filed Good Cause Exception with PUCT for Closed-Loop LFC Test(s)
  Exception for ERCOT to not charge for Base Point Deviation Charges during RTC+B LFC test

## Slide 6: RTC+B Scope
Final 2025 Refinements for Go-Live
Related NPRRs
within Program

## Slide 7
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 8
QSE will test their market submissions for defined subset transactions that are new or modified by RTC+B.
Scorecard goal is for 95% of QSEs to demonstrate successful submissions and have mitigation plans in place for remaining 5% to address in next trial phase.
QSE will add telemetry points for Energy Management System (EMS) system interface with ERCOT (such as Updated Desired Set Points (UDSP), New Ramp Rates, and ESR Telemetry)
Scorecard goal is for 98% of QSEs to demonstrate successful telemetry additions, and mitigation plans in place for remaining 2% to address in next trial phase. (Note 3-week lag in telemetry migrating through network model validation and into trials environment).
May & June:
Establishing Connectivity
COMPLETED

## Slide 9
QSE will support “parallel production” 2days/week by entering $bids/offers for non-binding RTC energy and A/S awards and dispatch (Open-loop test)
Scorecard goal for 100% of QSEs to demonstrate successful submissions and telemetry reflective of production, and mitigation plans in place for any outliers.
Coordination of individual QSE tests on subset of resources to ensure resources can follow new UDSP telemetry point from ERCOT.
Scorecard goal is for 98% of QSEs to successfully demonstrate, and mitigation plans in place for remaining 2% to address in next trial phase.
July & August:
Initial Real-Time Market execution and verify QSE ability to follow ERCOT frequency signals
COMPLETED

## Slide 10
Voluntary Day-Ahead Market for all QSEs will be conducted at least 2 times.
QSE can test their market submissions for Day-Ahead AS Self-Arrangement, AS Only Offers, Trades and normal submissions.
DAM participation is strongly encouraged but not required in Readiness metrics since RTC procures AS in Real-Time.
Participation includes much broader QSE population (marketers and load-only QSEs).
ERCOT and QSEs will conduct live-production tests of RTC-SCED and Load Frequency Control (LFC) prior to go-live.
RTC-SCED and frequency control dispatch during the tests will be binding to manage the reliable operations of the grid for2-4 hours.
ERCOT will coordinate with QSEs on how to submit RTC offers and telemetry for Energy and AS for the two systems (current and RTC system).
ERCOT will provide a summary of the test and use analysis and engineering judgement to assess if the test was successful in controlling frequency.
Sep 11 & Oct 30:
Required live-production test to ensure effective frequency dispatch and control.
Sep & Oct:
Optional Day-Ahead Market
IN FLIGHT
Market Notice sent regarding DAM for all QSEs

## Slide 11: Market Trials in-flight
Trials meeting every Monday 10-10:30am until December
  Standalone calendar page each week with WebEx
    RTCBTF Home Page houses all market trials documentation
  Averaging 150-200 participants
  Weekly presentation walk-through with Q&A
    Heavy use of RTCB@ercot.com email -> FAQ (160+)
Link to this past week’s market trials meeting
  Outcome of Open-Loop Testing on Oct 16 (last week)
  Production Closed-Loop Testing on Oct 30 (next week)
    Closed-Loop Workshop Oct 27 (Monday)
  Outage Schedule Submissions testing end Oct 31
  Cutover Workshop Nov 13

## Slide 12: Market Trials and Transition through Go-Live
We are here….
NCLR s/provide = NCLR can use self-provision in SCED

## Slide 13: Last week’s RTCBTF:
ASDC Update (reviewed updated AORDC and Excel Tool for ASDCs)
Reviewed updated values for AORDC and Excel Tool for creating ASDCs
Posted on RTCBTF Page (bottom 2 files)
AS Deployment Factors Discussion (more on next slide)
ERCOT analysis to assess Operator parameters and procedures for setting values
Based on discussion convening follow-up meeting to discuss in more depth (October 27)
Market Readiness
Review of September 11 Closed-Loop Testing Results Whitepaper (complete)
Transition/Cutover Handbook (complete)
Posting of Report XSDs (complete)

## Slide 14: AS Deployment Factor Discussion
Part of the RTC+B Design was to modify the RUC study to account for the potential deployment of Ancillary Services and the associated impact on State-Of-Charge (SOC) over the RUC study period
    Ancillary Service Deployment Factors (ASDFs) - Hourly parameters for each Ancillary Service type between 0 and 1 (or 0% to 100%) that indicate an assumed Ancillary Service deployment [energy reservation] and may be based on system conditions such as forecasts for Demand and Intermittent Renewable Resources (IRRs). These factors are used in the Reliability Unit Commitment (RUC) studies.
ERCOT has been evaluating historical data to determine potential ASDFs and has run studies to observe the impacts of the potential ASDFs on RUC results.
As of October 15 RTCBTF ERCOT was able to share its initial study and findings ahead of Go-Live.
  Reg-Up and Reg-Down set = range of values from 10%-70% depending on month and hour
  Responsive Reserve set = 0
  Non-Spin and ECRS set = 1
A special RTCBTF follow-up meeting has been scheduled to go deeper into the ERCOT analysis and planned values. Shams will be presenting alternative value at the Oct 27 RTCBTF meeting.
  Note these values do not need approval (ERCOT operator parameters)

## Slide 15: Wrap-Up
Upcoming activities:
Monday October 27- three meetings on Monday
- 10am Weekly Trial Call
- 1-3pm LFC Workshop for Oct 30 WebEx
- 3-5pm RTCBTF Discussion of AS Deployment Factors WebEx
Thursday October 30- Closed Loop LFC Test 10:35am-12:35pm
Thursday November 13- RTCBTF and Go-Live Cutover Workshop
Monday December 1-5 Go-Live week
Questions on RTC+B activities?
Can be directed to:
mmereness@ercot.com
RTCB@ERCOT.com