## Slide 1
Project Update
October 8, 2025
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  2025 Release Targets
  Priority/Rank Recommendations for Revision Requests with Impacts
    None
  Technology Working Group (TWG)
    Next meeting is 10/23/2025
  Initiative Ranking Workshop Update
    Draft #2 – Making Progress
    Status Notes
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 | NPRR1254 RTC+B Market Trials Sandbox Deployed | NPRR1145 | RTC+B Market Trials begin on 5/5/2025 | NPRR1253 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
NPRR1234(a) |  |  | NOGRR245 |  | PGRR091 PGRR115 SCR828
R7
R8
R10
R11
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR965
NPRR1000
NPRR1014
NPRR1029(a)
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216(a)
NPRR1236
NPRR1245
NPRR1246
NPRR1268
NPRR1269
NPRR1270
NPRR1282
NOGRR211
NOGRR268
NOGRR277
OBDRR020
OBDRR052
PGRR118
E
NPRR963(a) – Portion of NPRR
NPRR1029(a) – Market suspension of ESRs portion
NPRR1216(a) – Invoice workaround
NPRR1234(a) – Section 3.10.7.2, paragraphs 14-19
NPRR1253 – ICCP/Public API
ü
ü
1/1
3/1
ü
3/7
ü
ü
ü
RTC+B Stabilization begins
E
E
E
E
7/21
ü

## Slide 4: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1214 | Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | TBD | TBD | $800k-$1.2M, 12-18 months Impacted Systems: MMS, Settlements, Reporting ERCOT requests a continued table at PRS due to RTC+B resource constraints and design concerns
NPRR1294 | Move OBD to Section 22 – Demand Response Data Definitions and Technical Specifications | N/A | N/A | <$5k O&M
NPRR1299 | Clarifications to Emergency Response Service (ERS) | N/A | N/A | <$5k O&M
Recommendations for…
PPL Rank Information
Next 2025 Rank in Business Strategy = 4580 Next 2028 Rank in Business Strategy = 5110
Next 2026 Rank in Business Strategy = 4820 Next 2029 Rank in Business Strategy = 5300
Next 2027 Rank in Business Strategy = 4910 Next Rank in Regulatory = 420

## Slide 5: Technology Working Group (TWG)
Agenda for TWG meeting held on 9/25/2025:
Next TWG scheduled for 10/23/2025

## Slide 6: Draft #2 – Making Progress
Additional Notes:
All “High” items considered
Color coding reflects IA project cost estimates
Light and dark shading reflects potential project phase durations
Includes internal ERCOT projects drawing on similar resources
Spreadsheet posted for stakeholder review

## Slide 7: Aging Revision Request Review at PRS – Status
Draft #2 depicts the latest view of the release plan
  Still very much in progress
Impact Analyses loaded for NPRR1188 and NPRR1244 as a single project targeting an early 2026 start (perhaps even December 2025)
  Resource analysis underway
  Pre-project discussions with vendor are underway
  Considering approaches that would reduce the 18-24 month project duration
In support of SB6, ERCOT is envisioning a Large Load Curtailment Manager project that may include elements of NPRR1238
  Candidate for early 2026 project start (go-live target is TBD)
  Impact Analysis is getting underway (for portion other than NPRR1238)
Smaller projects temporarily moved from 2026 to 2027 until we have a better feel for pockets of resource availability in 2026
  NPRR1198, NPRR1290 Phase 2

## Slide 8: Aging Revision Request Project Review Approach
Initiative Prioritization Workshop held on 8/25/2025
Categorize RRs into “Tiers”
  Tier 1 Critical Must-have items (PUCT/Board directives, etc.)
  Tier 2 High Priority Highest priority after Tier 1
  Tier 3 Medium Priority Fit in without impacting Tier 1 and 2 projects
  Tier 4 No Action Not ready for immediate action
  Tier 5 Candidate for Removal May move to another tier after evaluation
Important Point
  Some aging RRs are expected to require language changes to bring them up to current market or system constructs
    Language updates would be made with a new RR
    ERCOT suggests this analysis be limited to aging items that are prioritized high enough to be queued for implementation