## Slide 1
Weekly
RTC+B Market Trials Update
ERCOT Staff
October 27, 2025

## Slide 2: Outline
Antitrust Admonition
Upcoming Activities
  October 30 Production LFC Test #2
  Daylight Savings Time this weekend
  Outage Scheduler submissions ending after October 31
  Connectivity Testing first week of November
Expectations of QSEs for the Week
Known Issues
Scorecards
DAM and Self-Provision Summary
Upcoming Schedule / LFC Prep Activities
AS Qualification Transition to ESR Single model
Q&A
Appendix- Supporting Materials:
  Summary of SCED Functionality
  SCED Analysis/Results for prior week
  DAM and AS Self-Provision Education
  Telemetry Screening
  New RTC Pricing Reports location
  NPRR1290 Validation Changes
  Links to Handbooks
  FAQ Updated
  Connectivity and Configuration (digital certs)

## Slide 3
WebEx Meeting reminders (same as other ERCOT forums):
Please keep line muted
If you have a question, please use the chat feature to either:
  Type in your question, or
  Type in “Question” and wait to be recognized to state question

## Slide 4
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 5
Voluntary Day-Ahead Market for all QSEs will be conducted at least 2 times.
QSE can test their market submissions for Day-Ahead AS Self-Arrangement, AS Only Offers, Trades and normal submissions.
DAM participation is strongly encouraged but not required in Readiness metrics since RTC procures AS in Real-Time.
Participation includes much broader QSE population (marketers and load-only QSEs).
ERCOT and QSEs will conduct live-production tests of RTC-SCED and Load Frequency Control (LFC) prior to go-live.
RTC-SCED and frequency control dispatch during the tests will be binding to manage the reliable operations of the grid for2-4 hours.
ERCOT will coordinate with QSEs on how to submit RTC offers and telemetry for Energy and AS for the two systems (current and RTC system).
ERCOT will provide a summary of the test and use analysis and engineering judgement to assess if the test was successful in controlling frequency.
Sep & Oct: Sep11 & Oct 30
Required live-production test to ensure effective frequency dispatch and control.
Sep & Oct:
Optional Day-Ahead Market
Market Notice sent regarding DAM for all QSEs

## Slide 6: Market Trials and Transition through Go-Live
We are here….
NCLR s/provide = NCLR can use self-provision in SCED
DST Nov 2
DAM run Nov2 DST

## Slide 7: October 30, 2025 Production Closed-Loop LFC Test Link to market notice: https://www.ercot.com/services/comm/mkt_notices/M-A100925-01

## Slide 8: RTC+B Daylight Saving Time Support (DST)
ERCOT will do it’s best to support DST in DAM and Real-Time
  Production support takes priority
QSEs are encouraged to submit RTM and DAM offers prior to or during the weekend to test DST
ERCOT plans to execute DAM on Saturday for OD Sunday Nov 2
DST will be observable in market trial systems, awards, and reports

## Slide 9: RTC+B Final Outage Submissions Testing Window
Latest RTC+B Outage Scheduler model is loaded into RTC+B and outages are synced from current production.
RTC+B Outage Scheduler will be available for QSEs/TSPs outage submissions testing (using API/OS UI) until end of this month only.
From November 1st, RTC+B Outage Scheduler will be made “Read-Only” until Go-Live. This means QSEs/TSPs can only query outages but can not make any changes from 11/01/2025.
Above change is required to allow ERCOT outage coordination team begin 60-day and 90-day ahead outages studies utilizing RTC+B Outage Scheduler.
  Starting from November 1st until Go-Live on Dec 4th night, RTC+B outage scheduler system outages will be updated periodically from current production (including converting combo model ESR outages to Single Model) to keep RTC+B outage scheduler in sync with current production outages.
  Please refer to Market notice was sent out on 10/03/2025 for more details
    https://www.ercot.com/services/comm/mkt_notices/M-A092624-04

## Slide 10: RTC+B QSEs Cutover Connectivity Testing
Some QSEs are using current production to support dual real-time market submissions into ERCOT RTC+B Market Trial Production System in parallel to Current Production.
Some QSEs are using parallel RTC+B Production and/or QA/Dev systems to support dual Real-Time and Day-Ahead Market Submissions into ERCOT RTC+B Market Trial Production System in parallel to current production.
QSEs Cutover Connectivity Testing window will be Open on November 3rd – November 7th to provide QSEs an opportunity to test out go-live cutover configurations and connectivity against ERCOT RTC+B Market Trials Systems.
  This testing window allows QSEs who are currently using parallel RTC+B systems for market submissions into RTC+B to test out their cutover software configurations without impacting current production market submissions.
  This test helps QSEs minimize risks with Go-Live cutover steps of their market systems.
  No changes will be made to ERCOT RTC+B market trial systems.
  QSEs are expected to use ongoing RTC+B market trials URLs and Production Certs for this connectivity test and submit production quality market submission into ERCOT RTC+B system.

## Slide 11: Market Trials known issues/updates
Current issues/updates:
  Issues resolved with release this week:
    MMS and EMS release deployments to RTC Market Trials includes fixes for issues that were previously identified in Closed Loop #1:​
      Received Non-Spin awards for a unit that is offline and cannot provide offline non-spin​
      Received RRS awards for unit on STARTUP​
      BLR resource not getting awarded ECRSM ​
      Unexpected AS Awards based on MCPC - Defect identified due to incorrect AS proxy offers for MT SCED intervals 9/11 10:30 - 11:00 AM
  Update:
    DAM submissions timeline extended to noon for each RTC DAM OD
      Prevent confusion with production
      Give more time after Prod DAM to populate RTC DAM

## Slide 12: Scorecards
Expectations similar to August “Monitored Operating Days”
See next 2 slides for prior week performance

## Slide 13: Scorecard 3A for Handbook 3- Market submission:
Scores for QSEs with Resources – Appropriate submissions made for each owned resources.
COP – ALL
TPO – Gen, ESR, CLR
ASO – AS Qualified Resources
System Wide Score last week:
Scoring:

## Slide 14: Scorecard 3B for Handbook 3- Acceptable Telemetry point values received by ERCOT for active resources
10/27 Scores for QSE with Resources – Accurate telemetry data sent to ERCOT
Scoring:

## Slide 15: Day-Ahead Market Results (pre-RTC/Current vs RTC)
Reminder Appendix has more details of Day-Ahead Market mechanics

## Slide 16: AS Self-Provision Observations for prior week
Reminder Appendix has more details of Self-Provision mechanics
Hour Ending 17 (10/22/25):
  734 MW of RRS awarded to NCLRs in the Day-Ahead Market
  During the hour, NCLRs telemetered ~1084 MW of RRS capability
Real-Time RRS Awards Breakdown:
  ~940 MW of RRS awarded to NCLRs
  ~991 MW self-provision telemetered
  ~700 MW of self-provision were awarded (95% of the DA Awards)
Deployment Flags Reminder
  Group deployments go away with RTC+B
  Individual NCLR (Resource Specific) deployment and recall XML messages remain unchanged for RRS, ECRSM, Non-Spin

## Slide 17: SCED Analysis/Observations in Appendix
See Appendix for Prior Week SCED Results

## Slide 18: Completing October Trials
Oct 27 LFC Workshop Link
Oct 30 Production 2-hour LFC Test

## Slide 19: Upcoming Testing
October 27 LFC Workshop Today 1-3pm
  https://www.ercot.com/calendar/10272025-RTCBTF_TWG-Workshop-_-Detailed
October 30 production Closed-Loop LFC Test
  Market Notice Link https://www.ercot.com/services/comm/mkt_notices/M-A100925-01
  Current Plan on timing 10:35am - 12:35pm
  Will essentially be a repeat of September 11 test (similar structure and expectations)
  Exceptions allowed (sideline resources)
  ERCOT will observe Frequency tuning changes in production
  Both ERCOT and QSE opportunity to test any fixes
  Repeat the critical cutover process that will be used 35 days later for go-live
1-Day Market Notice will also be sent Oct 29
Emailing secure WebEx later today to AR, BAR, RTC AE

## Slide 20: November/December
Link to current Transition/Cutover Details at RTCBTF
RTC+B Market Trials Outage Scheduler turns to READONLY for transitional purposes
System connectivity Test Week 1 (go-live market submission configuration testing)
Week 2 RTCBTF Workshop on Nov 13 for December go-live Cutover
Weeks 2 & 3 Continue Trial Activity
Currently minimal plans week of Thanksgiving

## Slide 21: Special Topic
Separate slide deck to discuss AS Qualification Transition to ESR Single model

## Slide 22: Wrap-Up and Questions
Prepare your staff for production support this week!
    Production LFC Test on October 30 (scripted AS Offers!)
    DST this weekend
Three meetings today:
- 10am Weekly Trial Call
- 1-3pm LFC Workshop for Oct 30 WebEx
- 3-5pm RTCBTF Discussion of AS Deployment Factors WebEx
Remainder of meeting for Q&A
Can always email the RTC+B Program mailbox: RTCB@ercot.com
Reminder of Appendix- SCED analysis, Education, Connectivity

## Slide 23: APPENDIX- Supporting Materials
Summary of SCED Functionality
SCED Analysis/Results for prior week
DAM and AS Self-Provision Education
Telemetry Screening
New RTC Pricing Reports location
NPRR1290 Validation Changes
Links to Handbooks
FAQ Updated 8/8/2025
Connectivity and Configuration (digital certs)

## Slide 24: Summary of SCED functionality
What is RTC SCED using to solve in trials?
  Production Network model from NMMS
  QSE submitted offers (energy and A/S)
  QSE production telemetry
    ERCOT performs some overrides for stale data from QSE sites- improving each week
  Outages in prod telemetry would be outage in RTC SCED
  July 31 improvements implemented:
    NPRR1268/1269 ASDC and Proxies logic implemented
    AS Plan improved and now same as Prod
  Aug 4 improvements implemented:
    IRR Forecast synchronization has been manual, but now automated
  Aug 18 improvements implemented :
    Active constraints flag being manually copied (automation planned for Aug 18)
    Load Forecasts being fed into RTC, but ERCOT manually aligns which forecast is being used based on operator selection in Prod (automation planned for Aug 18)

## Slide 25: RTC+B Market Trials Summary 10-22-2025
Due to a bug causing the MCPC values to fail to publish when the pricing run is disabled in SCED, MCPC values for the Operating Day are missing. The bug has been flagged, and a fix is being delivered.

## Slide 26: System Lambda (plus Adders)

## Slide 27: Ancillary Service Prices

## Slide 28: AS Awards* Summary by Resource Type
* Pre-RTC (RTM AS Schedule)

## Slide 29: AS Awards* Summary by Resource Type
* Pre-RTC (RTM AS Schedule)
* Pre-RTC (RTM AS Schedule)

## Slide 30: SPP by Hub and Competitive Load Zone

## Slide 31: Congestion Rent

## Slide 32: Dispatchable Capacity

## Slide 33: RTC+B Market Trials Summary 10-23-2025
Due to a bug causing the MCPC values to fail to publish when the pricing run is disabled in SCED, MCPC values for the Operating Day are missing. The bug has been flagged, and a fix is being delivered.

## Slide 34: System Lambda (plus Adders)

## Slide 35: Ancillary Service Prices

## Slide 36: AS Awards* Summary by Resource Type
* Pre-RTC (RTM AS Schedule)
* Pre-RTC (RTM AS Schedule)

## Slide 37: AS Awards* Summary by Resource Type
* Pre-RTC (RTM AS Schedule)

## Slide 38: SPP by Hub and Competitive Load Zone

## Slide 39: Congestion Rent

## Slide 40: Dispatchable Capacity

## Slide 41: Ancillary Service Demand Curves

## Slide 42: Day-Ahead Market

## Slide 43: DAM Operating Day (OD) Test
Testing strongly encouraged, but not required for all QSEs
  Handbook #6 Day-Ahead Market
  The DAM will run on Tuesdays
  DAM submission window closes at noon.
By 0600 QSEs can validate and confirm report posting:
  Advisory AS Obligation: Available on Market Trials MMSUI (5 significant digits after decimal point)
  ASDCs: Available on Production MIS
  Load Ratio Share and PSS/e files will change with RTC cutover, but will not be visible for OD 9/17
For successful DAM completion, and meaningful results, market participants are strongly encouraged to submit various submission types, and not only submission types listed above (E.g., PTPs, EOOs, EBs, AS Self-Arrangement, non-ESR AS and non-ESR TPO submissions).

## Slide 44: DAM Operating Day (OD) Test – Pre DAM
Key DAM Submission Changes
  AS Obligation – no self-arrangement will be allowed over QSE’s Advisory AS Obligation.
    Example: RRS Advisory AS Obligation = 2.18368 -> maximum Self-AS submission = 2.1
  COP – can submit negative LSL/HSL for ESR. Can submit values for AS Capability within the existing AS fields.
  TPO (EB/OC) – negative MW quantity reflects ESR EB/OC. ESR startup and minimum energy costs are not allowed and ESRs are considered self-committed.
  Resource-Specific AS Offers – FRRSUP and FRRSDN offers not allowed. Offers must be between $0 and DAM SWCAP. For ESRs, RRSUFR and ECRSM offers not allowed. All AS offers from ESRs are inclusive of EB/OCs.
  AS Only Offers – Offers must be between $0 and DAM SWCAP. REGUP, REGDN, RRSPFR, Online NSPIN, and Online ECRS are allowed. Other AS types are not allowed. Multi-hour and fixed blocks are not allowed.

## Slide 45: DAM Operating Day (OD) Test – Post DAM
Post Publish Report Verification
  AS-Only Awards
  ESR Resource-Specific AS awards
  TPO(EB/OC) awards
  QSEs with Advisory AS Obligations and AS awards can download/review their Final AS Obligations and ensure observe/handle values with up to 5 significant digits after the decimal
  DAM LMPs
  DAM MCPCs
  DAM Constraint Shadow Prices
  Other DAM Awards

## Slide 46: DAM ASDC Price Setting Example
OD 9/17/2025 HE 21
NSPIN MCPC : $38.52
  AS Award stack intersected the ASDC @ 2536.6 MW
  NSPIN AS Plan @ HE 21 : 2339 MW

## Slide 47: DAM ASDC Price Setting Example
OD 9/17/2025 HE 18
ECRS MCPC : $80.51
  AS Award stack intersected the ASDC @ 1888.6 MW
  ECRS AS Plan @ HE 18 : 2877 MW

## Slide 48: NCLR Self-Provision Reminder: AS Self-Provision is a special design to allow Non-Controllable Load Resources to self-provide their AS Responsibilities into/through SCED/Real-Time Market

## Slide 49: NCLR Resource Status Codes
Pre-RTC
  Resource Status Codes (RST)
  OUTL = 260
  ONRL = 259
  ONECL = 264
RTC+B
  Updated Resource Status Codes (RSTR)
  OUTL = 258
  ONL = 257

## Slide 50: Ramp Rates and Capabilities
Pre-RTC
  AS Responsibility and Schedule
  RRRS
  RRSC
  ECRS
  ECSC
  NSRS
  NSSC
RTC+B
  Ramp Rates & Awards
  UFRC (UFR Capability)
  UFRA (UFR Award)
  ECRR (ECRS RR Capability *10 Min)
  ECRA (ECRS Award)
  NSRR (NSPIN RR Capability *30 Min)
  NSRA (NSPIN Award)
QSE to ERCOT Telemetry
ERCOT to QSE ICCP

## Slide 51: Self-Provision Achieved via Telemetry Points for NCLRs
QSEs will be able to self-provide in real-time via telemetered ICCP points
LEGEND
ICCP Change Request Example RTC+B V1.4 on RTC ERCOT webpage

## Slide 52: The Self-Provision Checklist
Scenario: My Load Resource was awarded 15 MW in the DAM, and I purchased 5 MW via a trade.
My total RRS AS Position is 20 MW.
How to correctly self-provide 20 MW:
    Is my resource qualified?
    Telemetry Points
      RSTR set to ONL (257)
      UFR must be Armed
      Can I cover my obligation?
        Qualified MW Amount ≥ Self-provided amount
        NPF - LPC ≥ Self-provided amount
        Capability to Provide AS ≥ Self-provided amount
      Final Step: Telemeter Self-provision
      “your offers explain your extra”

## Slide 53: Scenario 1
Scenario ** Assume AS qualified for All Headroom (NPF-LPC) | Max Power Cons. | Net Power Flow | Low Power Cons. | Resource Status | Under Freq. Relay | Self-provided RRS UFR (MW) | Self-provided ECRS (MW) | Current Capability to provide UFR (MW) | ECRS (10min) Ramp Rate (MW/min) | RRS UFR AS Award | ECRS AS Award | Notes
 | MPC | NPF | LPC | RSTR | UFR | SPUF | SPEC | UFRC | ECRR | UFRA | ECRA | 
NCLR_1 is qualified to provide 20 MW. DAM awards NCLR_1 with 15MW RRS. QSE also has additional 5MW RRS Position via RRS Trades. | 20 | 20 | 0 | ONL | Arm | 20 | 0 | 20 | 0 | 20 | 0 | NCLR_1 Telemetry needs to show: Status = ONL, MPC >= NPF >= 20 MW, NPF-LPC >= 20 MW, RRS capability >= 20 MW, RRS self-provided telemetry = 20 MW SCED will respect the 20 MW self-provided RRS and award the resource 20 MW RRS UFR.
QSE to ERCOT Telemetry
ERCOT to QSE ICCP
NCLR_1 has a 20 MW RRS AS Position, 15 MW from DAM award and 5 MW from RRS Trade

## Slide 54: Telemetry Screening for Scorecard 3B for Handbook 3 Acceptable Telemetry Point values received by ERCOT for active resources.
Key points for Telemetry scorecard check
  Device types checked - Units, CLRs, NCLRs, ESRs for each QSE
  RTCB Telemetry status should be “Good” quality
  RTCB Units / CLRs / NCLRs Telemetry values should be within “Expected Range” or an expected value. Details are provided in next few slides.
  Expected values are derived from equivalent analogs in current production, based on defined criteria.
  RTCB ESR telemetry values are checked against corresponding combo model Battery Unit / CLR counterparts in production.
Scoring:

## Slide 55: RTC+B Telemetry points screening/validation

## Slide 56: RTC+B New Reports Posted to the ERCOT Website
Links to the available RTC+B versions of Real-Time reports posted on Real-Time Market Information page.

## Slide 57: Submission validation update - PROD vs RTC+B
NPRR1290 :
  cleaned up protocol language around submitting offer curves and bid curves
  disallows having more than 2 price/quantity points in a flat/vertical segment of the curve.
Impacts to QSEs during dual-submission – some submissions accepted in Production will be rejected in Market Trials environment:
RTM Energy bids – protocol requiring “increasing quantities” now enforced.
  Reverted this change to validation. Further discussion highlighted protocol should be brought in line to long-standing practice, not validation.
  Example: Bid with Q1=0mw, Q2=10mw, Q3=10mw will be rejected as Q3 does not increase from Q2.
TPO & RTM Bid – more than 2 price/quantity pairs with same price or quantity will be rejected
Market Submission Validation
Rules document updated.

## Slide 58: Submission validation update - PROD vs RTC+B
TPO – EB/OC - EOC
RTM EB
RTM EB

## Slide 59: Market Trials Framework:
TAC Approved the Market Trials Plan in October 2024
Discussions with RTC+B Task Force have shaped the Handbooks
Handbook #1- QSE Submission Testing
Handbook #2- QSE Telemetry Tests
Handbook #3- Open Loop SCED
Handbook #4- QSE Telemetry Tests
Handbook #5- Close-Loop LFC Tests
Handbook #6- Day-Ahead Market Tests
All are posted on the
RTCBTF Homepage
under Market Trials banner

## Slide 60: Market Trials Technical Details
Detailed discussions with TWG have provided technical content details
Digital Certificate details
Connectivity/URL details to User Interfaces and APIs
Reminder of how to submit new ICCP requests
RTC and Production Telemetry connectivity
Network Model Load Schedule
All are posted on the
RTCBTF Homepage
under Technical Details banner

## Slide 61: Reminder of RTC+B FAQ
Worksheets for categories
Posted on RTCBTF Home Page under Key Documents
Common questions/responses in Excel Workbook (target weekly updates)
Search workbook for Key Words

## Slide 62
RTC+B Market Submissions - Systems configurations
RTC QSE
Submission Testing
Open-loop
RTC SCED
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
Start
03/2025
Start
05/2025
Start
09/2025
Go-Live
12/5/25*
Apr 2025
Mar 2025
Feb 2025
Optional: RTC QSE/Vendor Developer
Submission Testing
Start
07/2025
Certificate: Current MOTE
Env: ERCOT RTC Market Trial
URL: RTC MIS MOTE URL
Certificate: Current Production
Env: ERCOT RTC Market Trial
URL: RTC MIS Market Trial
Cert: Production
Env: Prod
URL: MIS Prod
QSE/Vendor developer can use MOTE certificates & RTC MIS MOTE API URL to test the submissions until end of submission testing phase (end of June) as needed. At the start of the Open Loop testing, RTC MOTE MIS URLs will be disabled.
URL links: RTC MOTE and Market Trial URL links to be used for MMSUI, OSUI and API submissions. Actual links are provided in next slide.
For notifications/responses to MPs from RTC Market Trials environment, MP will need to provide the listener URL to ERCOT

## Slide 63: RTC+B Market Submissions - Systems configurations (Updated with URLs)
RTC+B Market Trials and Go-live
RTC Phase | Digital Certificate | MMSUI / OSUI URL | API / WAN URL
Vendor/QSE Submissions Testing | Current MOTE | RTC MOTE MIS URLs https://testmarkettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://testmarkettrials.ercot.com/osrui/osrui/Summary.action | RTC MOTE API/WAN URL https://testmarkettrialsapi.ercot.com/NodalAPI/EWS/ https://testmarkettrialsapi.wan.ercot.com/NodalAPI/EWS/
Open Loop and Closed Loop Testing | Current Production | RTC Market Trial URL https://markettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://markettrials.ercot.com/osrui/osrui/Summary.action | RTC Market Trial API/WAN URL https://markettrialsapi.ercot.com/NodalAPI/EWS/ https://markettrialsapi.wan.ercot.com/NodalAPI/EWS/
From RTC Go-live onwards | Current Production | Current Prod MIS URL mis.ercot.com/mmsui mis.ercot.com/osui | New Production API/WAN URL

## Slide 64: RTC+B Market Submissions - Systems configurations Public Key Update for WAN/API submissions
For API/WAN submissions into Market Trials environments, need to download public keys and place into the keystore location in system being used for RTC+B submissions.
No change to digital user certificates – continue to use existing MOTE and Production Certificates
Market Trial API Public key location: https://www.ercot.com/services/mdt/webservices